## Baseline Schedule
General |  | Relations |  | Baseline |  |  | Resource Demand | Baseline Costs
ID | Name | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Fixed Cost | Cost/Hour | Variable Cost
0 | Railway Station Ghent |  |  | 2010-10-04 08:00 | 2015-05-07 16:53 | 1676d 8h |  | 0 | 0 | 0
5 | Voorbereiding uitvoering |  | FS22+-320;FS12+-80;FS6+-360;FS18+824 | 2010-10-04 08:00 | 2011-02-15 17:00 | 92d |  | 0 | 0 | 0
6 | Werfinstallatie | 5FS+-360 | SS7+0;FS23+40;FS27+80;FS31+120 | 2010-12-09 08:00 | 2011-01-05 17:00 | 15d |  | 0 | 0 | 0
7 | Bronbemaling | 6SS+0 |  | 2011-03-23 08:00 | 2011-06-01 17:00 | 46d |  | 0 | 0 | 0
14 | Grondwerken en infrastructuur |  |  | 2010-12-20 08:00 | 2015-05-07 16:53 | 1599d 8h |  | 0 | 0 | 0
22 | Voorbereiding & verwijdering ballast | 5FS+-320 | FS23+-1400 | 2010-12-20 08:00 | 2011-10-04 17:00 | 182d |  | 0 | 0 | 0
26 | Zone 2: As 84-88 |  |  | 2015-04-27 16:53 | 2015-05-07 16:53 | 10d |  | 0 | 0 | 0
30 | Zone 3: As 84-79 |  |  | 2015-04-27 16:53 | 2015-05-07 16:53 | 10d |  | 0 | 0 | 0
34 | Zone 4: As 79-74 |  |  | 2011-02-01 08:00 | 2011-10-17 17:00 | 258d 9h |  | 0 | 0 | 0
31 | Afbraakwerken | 6FS+120 | FS33+-240 | 2011-02-01 08:00 | 2011-06-06 17:00 | 85d |  | 0 | 0 | 0
32 | Grondwerken | 28FS+-120 | FS33+-56 | 2011-05-11 08:00 | 2011-06-14 17:00 | 25d |  | 0 | 0 | 0
33 | Infrastructuur | 32FS+-56;31FS+-240 | FS21+-360 | 2011-06-07 08:00 | 2011-10-17 17:00 | 80d |  | 0 | 0 | 0
17 | Superstructuur station |  |  | 2011-02-02 08:00 | 2012-03-01 17:00 | 393d 9h |  | 0 | 0 | 0
12 | Zone 1: As 88-97 | 5FS+-80 |  | 2011-02-02 08:00 | 2012-03-01 17:00 | 257d |  | 0 | 0 | 0
13 | Zone 2: As 84-88 | 25FS+-360 | FS15+-160;FS16+-120;FS18+-144 | 2011-05-16 08:00 | 2011-09-21 17:00 | 78d |  | 0 | 0 | 0
15 | Zone 3: As 84-79 | 29FS+-800;13FS+-160 | FS21+-800;FS18+-760 | 2011-08-25 08:00 | 2012-01-10 17:00 | 94d |  | 0 | 0 | 0
16 | Zone 4: As 79-74 | 13FS+-120 | FS21+-960;FS18+-920 | 2011-09-02 08:00 | 2012-02-06 17:00 | 107d |  | 0 | 0 | 0
18 | Perron en overkappingen | 5FS+824;13FS+-144;15FS+-760;16FS+-920 |  | 2011-08-29 08:00 | 2012-08-17 17:00 | 230d |  | 0 | 0 | 0
21 | Grote overkapping | 25FS+80;29FS+-360;33FS+-360;15FS+-800;16FS+-960 |  | 2011-08-18 08:00 | 2012-08-08 17:00 | 230d |  | 0 | 0 | 0

## Resources
General |  |  |  | Resource Cost
ID | Name | Type | Availability | Cost/Use | Cost/Unit

## Risk Analysis
General |  | Activity Duration Distribution Profiles
ID | Name | Description | Optimistic | Most Probable | Pessimistic
0 | Railway Station Ghent | manual - absolute | 0 | 0 | 0
5 | Voorbereiding uitvoering | manual - absolute | 667 | 736 | 982
6 | Werfinstallatie | manual - absolute | 105 | 120 | 125
7 | Bronbemaling | standard - symmetric | 80 | 100 | 120
14 | Grondwerken en infrastructuur | manual - absolute | 0 | 0 | 0
22 | Voorbereiding & verwijdering ballast | standard - symmetric | 80 | 100 | 120
26 | Zone 2: As 84-88 | manual - absolute | 0 | 0 | 0
30 | Zone 3: As 84-79 | manual - absolute | 0 | 0 | 0
34 | Zone 4: As 79-74 | manual - absolute | 0 | 0 | 0
31 | Afbraakwerken | standard - symmetric | 80 | 100 | 120
32 | Grondwerken | standard - symmetric | 80 | 100 | 120
33 | Infrastructuur | manual - absolute | 588 | 640 | 768
17 | Superstructuur station | manual - absolute | 0 | 0 | 0
12 | Zone 1: As 88-97 | standard - symmetric | 80 | 100 | 120
13 | Zone 2: As 84-88 | standard - symmetric | 80 | 100 | 120
15 | Zone 3: As 84-79 | manual - absolute | 651 | 752 | 782
16 | Zone 4: As 79-74 | manual - absolute | 731 | 856 | 903
18 | Perron en overkappingen | manual - absolute | 1725 | 1840 | 2208
21 | Grote overkapping | manual - absolute | 1726 | 1840 | 2208

## Agenda
Working Hours |  | Working Days |  | Holidays
0:00 - 1:00 | No | Monday | Yes | 19042013
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor