## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost
1 | App Dev | 1 |  | FS2 | 2015-04-14 20:23 | 2015-04-19 20:23 | 5d | Programmer [10.0 #]; Tester [5.0 #] | 0 | 1000 | 0 | 1000 | 0
2 | Testing | 1.1 | FS1 |  | 2015-04-14 20:23 | 2015-04-24 20:23 | 10d | Tester [50.0 #] | 0 | 10000 | 10 | 100 | 0