## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost
0 | PROJECT CLAEYS-VERHELST | 1 |  |  | 2006-04-17 08:00 | 2007-12-26 10:00 | 442d 2h |  | 0 | 2700210.5 | 0 | 0 | 3027133.25
46 | preparation | 1.1 |  |  | 2006-04-17 08:00 | 2006-12-08 17:00 | 170d |  | 0 | 216786.9844 | 0 | 0 | 253804.5938
2 | building permit | 1.1.1 |  | FS3 | 2006-04-17 08:00 | 2006-07-07 17:00 | 60d |  | 0 | 75 | 0 | 0 | 75
3 | hire contractor | 1.1.2 | FS2 | FS16 | 2006-07-10 08:00 | 2006-08-04 17:00 | 20d |  | 0 | 210000 | 0 | 0 | 210000
4 | temporary offices | 1.1.3 |  |  | 2006-04-17 08:00 | 2006-05-12 17:00 | 20d |  | 0 | 3765.3101 | 0 | 0 | 3765.3101
5 | temporary facilities | 1.1.4 |  |  | 2006-04-17 08:00 | 2006-07-07 17:00 | 60d |  | 0 | 1876.54 | 0 | 0 | 1876.54
16 | preparation contractor | 1.1.5 | FS3 | FS6 | 2006-08-07 08:00 | 2006-10-27 17:00 | 60d |  | 0 | 0.01 | 0 | 0 | 0.01
6 | demolition | 1.1.6 | FS16 | FS17;FS69 | 2006-10-30 08:00 | 2006-12-08 17:00 | 30d | team subcontractor [4.0 #8] | 37017.6016 | 1070.11 | 0 | 0 | 38087.7109
47 | foundation | 1.2 |  |  | 2006-12-11 08:00 | 2007-02-01 17:00 | 39d |  | 0 | 362567.875 | 0 | 0 | 401436.375
17 | excavation | 1.2.1 | FS6 | FS18;FS21 | 2006-12-11 08:00 | 2006-12-28 17:00 | 14d | team subcontractor | 4318.7207 | 26000 | 0 | 0 | 30318.7207
69 | soil analyses | 1.2.2 | FS6 | FS18 | 2006-12-11 08:00 | 2006-12-12 17:00 | 2d | team subcontractor | 616.96 | 2000 | 0 | 0 | 2616.96
18 | foundation beam | 1.2.3 | 17FS;FS69 | FS19 | 2006-12-29 08:00 | 2007-02-01 17:00 | 25d | team subcontractor [3.0 #8] | 23136 | 98523.7266 | 0 | 0 | 121659.7266
21 | placing sewerage | 1.2.4 | FS17 | FS23 | 2006-12-29 08:00 | 2007-01-11 17:00 | 10d | team subcontractor [3.0 #8] | 9254.4004 | 1224.73 | 0 | 0 | 10479.1309
23 | foundation plate | 1.2.5 | FS21 | FS19 | 2007-01-12 08:00 | 2007-01-12 17:00 | 1d | team subcontractor [5.0 #8] | 1542.4062 | 234819.4375 | 0 | 0 | 236361.8438
48 | shell | 1.3 |  |  | 2007-02-02 08:00 | 2007-04-26 17:00 | 60d |  | 0 | 472804.4375 | 0 | 0 | 542212.4375
19 | steelframe I | 1.3.1 | 18FS;FS23 | FS20 | 2007-02-02 08:00 | 2007-03-01 17:00 | 20d | team subcontractor [4.0 #8] | 24678.3984 | 118992.5078 | 0 | 0 | 143670.9062
20 | concrete vaults I | 1.3.2 | FS19 | FS22 | 2007-03-02 08:00 | 2007-03-15 17:00 | 10d | team subcontractor [4.0 #8] | 12339.2031 | 117409.7188 | 0 | 0 | 129748.9219
22 | steelframe II | 1.3.3 | FS20 | FS24 | 2007-03-16 08:00 | 2007-04-05 17:00 | 15d | team subcontractor [3.0 #8] | 13881.6016 | 118992.5078 | 0 | 0 | 132874.1094
24 | concrete vaults II | 1.3.4 | FS22 | FS25;FS49 | 2007-04-06 08:00 | 2007-04-26 17:00 | 15d | team subcontractor [4.0 #8] | 18508.7969 | 117409.7188 | 0 | 0 | 135918.5156
50 | wind and water proof | 1.4 |  |  | 2007-04-27 08:00 | 2007-06-07 17:00 | 30d |  | 0 | 560844.1875 | 0 | 0 | 597047.375
25 | facades | 1.4.1 | FS24 | FS26 | 2007-04-27 08:00 | 2007-05-24 17:00 | 20d | team subcontractor [2.0 #8] | 12339.1875 | 339314 | 0 | 0 | 351653.1875
26 | outside windows | 1.4.2 | FS25 | FS28;FS29 | 2007-05-25 08:00 | 2007-06-07 17:00 | 10d | carpenter [3.0 #3] | 9120 | 150750.5938 | 0 | 0 | 159870.5938
49 | roof | 1.4.3 | FS24 |  | 2007-04-27 08:00 | 2007-05-10 17:00 | 10d | roofer [4.0 #4] | 11520 | 70779.5703 | 40.3 | 3224 | 85523.5703
62 | warehouse | 1.5 |  |  | 2007-06-08 08:00 | 2007-10-31 10:00 | 103d 2h |  | 0 | 257044.9688 | 0 | 0 | 301814.5625
28 | v0 concrete | 1.5.1 | FS26 | FS30;FS27;FS59;FS52;FS45;FS34;FS60;FS51 | 2007-06-08 08:00 | 2007-06-21 17:00 | 10d | team subcontractor [5.0 #8] | 15424 | 134400 | 0 | 0 | 149824
30 | v0 sanitary | 1.5.2 | 31FS;FS28 | FS35 | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673
27 | v0 masonry | 1.5.3 | 31FS;FS28 |  | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 40.65 | 3252 | 37704.9609
59 | v0 heating | 1.5.4 | 31FS;FS28 | FS35 | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | heating engineer | 6912 | 11651 | 0 | 0 | 18563
29 | v0 electricity | 1.5.5 | 26FS;FS31 | FS35 | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400
35 | v0 floors | 1.5.6 | 59FS;29FS;FS30 | FS41;FS37 | 2007-10-03 10:00 | 2007-10-31 10:00 | 20d | floor layer | 6649.6016 | 75000 | 0 | 0 | 81649.6016
66 | construction leave | 1.6 |  |  | 2007-08-15 10:00 | 2007-08-29 10:00 | 10d |  | 0 | 0.01 | 0 | 0 | 0.01
31 | construction leave | 1.6.1 |  | FS53;FS55;FS56;FS61;FS54;FS30;FS27;FS59;FS52;FS45;FS34;FS60;FS51;FS29 | 2007-08-15 10:00 | 2007-08-29 10:00 | 10d |  | 0 | 0.01 | 0 | 0 | 0.01
63 | level 1 | 1.7 |  |  | 2007-08-29 10:00 | 2007-10-24 10:00 | 40d |  | 0 | 226284.9844 | 0 | 0 | 262542.5938
52 | v1 sanitary | 1.7.1 | 31FS;FS28 |  | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673
45 | v1 masonry | 1.7.2 | 31FS;FS28 |  | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 40.65 | 3252 | 37704.9609
34 | v1 screed | 1.7.3 | 31FS;FS28 | FS67 | 2007-08-29 10:00 | 2007-09-19 10:00 | 15d | screed layer [2.0 #3] | 0 | 106140 | 0 | 0 | 106140
60 | v1 heating | 1.7.4 | 31FS;FS28 |  | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | heating engineer | 6912 | 11651 | 43.2 | 6912 | 25475
51 | v1 electricity | 1.7.5 | 31FS;FS28 |  | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400
67 | v1 drying screed | 1.7.6 | FS34 | FS57;FS32 | 2007-09-19 10:00 | 2007-09-26 10:00 | 5d |  | 0 | 0.01 | 0 | 0 | 0.01
57 | v1 flooring | 1.7.7 | FS67 | FS41;FS37;FS36 | 2007-09-26 10:00 | 2007-10-24 10:00 | 20d | floor layer | 6649.6016 | 72500 | 0 | 0 | 79149.6016
64 | level 2 | 1.8 |  |  | 2007-08-29 10:00 | 2007-10-24 10:00 | 40d |  | 0 | 125260.9688 | 0 | 0 | 149562.5625
53 | v2 sanitary | 1.8.1 | FS31 |  | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673
55 | v2 masonry | 1.8.2 | FS31 |  | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 0 | 0 | 34452.9609
56 | v2 screed | 1.8.3 | FS31 | FS68;FS36 | 2007-08-29 10:00 | 2007-09-19 10:00 | 15d | screed layer | 0 | 46116 | 0 | 0 | 46116
61 | v2 heating | 1.8.4 | FS31 |  | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | electrician | 5120 | 11651 | 0 | 0 | 16771
54 | v2 electricity | 1.8.5 | FS31 |  | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400
68 | v2 drying screed | 1.8.6 | FS56 | FS58;FS32 | 2007-09-19 10:00 | 2007-09-26 10:00 | 5d |  | 0 | 0.01 | 0 | 0 | 0.01
58 | v2 flooring | 1.8.7 | FS68 | FS41;FS37;FS36 | 2007-09-26 10:00 | 2007-10-24 10:00 | 20d | floor layer | 6649.6016 | 31500 | 0 | 0 | 38149.6016
65 | completion | 1.9 |  |  | 2007-09-26 10:00 | 2007-12-26 10:00 | 65d |  | 0 | 478615.9062 | 0 | 0 | 518712.7188
32 | stucco | 1.9.1 | 68FS;FS67 | FS41;FS37 | 2007-09-26 10:00 | 2007-10-17 10:00 | 15d | plasterer [3.0 #4] | 14896.8008 | 8642 | 0 | 0 | 23538.8008
36 | drywall | 1.9.2 | 58FS;57FS;FS56 |  | 2007-10-24 10:00 | 2007-11-28 10:00 | 25d |  | 0 | 48000 | 0 | 0 | 48000
41 | kitchen and bar | 1.9.3 | 32FS;58FS;57FS;FS35 |  | 2007-10-31 10:00 | 2007-11-21 10:00 | 15d |  | 0 | 87000 | 0 | 0 | 87000
37 | techniques | 1.9.4 | 32FS;58FS;57FS;FS35 | FS38;FS42;FS43;FS44 | 2007-10-31 10:00 | 2007-11-21 10:00 | 15d |  | 0 | 2156.0601 | 0 | 0 | 2156.0601
44 | stairs | 1.9.5 | FS37 |  | 2007-11-21 10:00 | 2007-12-05 10:00 | 10d |  | 0 | 33000 | 0 | 0 | 33000
42 | entrance doors | 1.9.6 | FS37 |  | 2007-11-21 10:00 | 2007-12-05 10:00 | 10d |  | 0 | 16000 | 0 | 0 | 16000
43 | elevator | 1.9.7 | FS37 |  | 2007-11-21 10:00 | 2007-11-28 10:00 | 5d |  | 0 | 38817.8516 | 0 | 0 | 38817.8516
38 | suspended ceiling | 1.9.8 | FS37 | FS39 | 2007-11-21 10:00 | 2007-11-28 10:00 | 5d |  | 0 | 32000 | 0 | 0 | 32000
39 | painting | 1.9.9 | FS38 | FS40 | 2007-11-28 10:00 | 2007-12-19 10:00 | 15d | painter [4.0 #6] | 16800 | 83000 | 0 | 0 | 99800
40 | furniture | 1.9.10 | FS39 |  | 2007-12-19 10:00 | 2007-12-26 10:00 | 5d | joiner [5.0 #5] | 8400 | 130000 | 0 | 0 | 138400