## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost
0 | PROJECT CLAEYS-VERHELST | 1 |  |  | 2006-04-17 08:00 | 2007-12-26 10:00 | 442d 2h |  |  | 2700210.5 |  |  | 3027133.25
46 | preparation | 1.1 |  |  | 2006-04-17 08:00 | 2006-12-08 17:00 | 170d |  |  | 216786.9844 |  |  | 253804.5938
2 | building permit | 1.1.1 |  | FS3 | 2006-04-17 08:00 | 2006-07-07 17:00 | 60d |  | 0 | 75 | 0 | 0 | 75 | Legend
3 | hire contractor | 1.1.2 | 2FS | FS16 | 2006-07-10 08:00 | 2006-08-04 17:00 | 20d |  | 0 | 210000 | 0 | 0 | 210000 |  | Necessary input
4 | temporary offices | 1.1.3 |  |  | 2006-04-17 08:00 | 2006-05-12 17:00 | 20d |  | 0 | 3765.3101 | 0 | 0 | 3765.3101 |  | Alternative input*
5 | temporary facilities | 1.1.4 |  |  | 2006-04-17 08:00 | 2006-07-07 17:00 | 60d |  | 0 | 1876.54 | 0 | 0 | 1876.54 |  | Additional input
16 | preparation contractor | 1.1.5 | 3FS | FS6 | 2006-08-07 08:00 | 2006-10-27 17:00 | 60d |  | 0 | 0.01 | 0 | 0 | 0.01 | other fill | Output; can be calculated from input (or already entered in previous tab)
6 | demolition | 1.1.6 | 16FS | FS17;FS69 | 2006-10-30 08:00 | 2006-12-08 17:00 | 30d | team subcontractor[4,00 #8] | 37017.6016 | 1070.11 | 0 | 0 | 38087.7109
47 | foundation | 1.2 |  |  | 2006-12-11 08:00 | 2007-02-01 17:00 | 39d |  |  | 362567.875 |  |  | 401436.375 | * Baseline End is an alternative input for (Baseline) Duration,
17 | excavation | 1.2.1 | 6FS | FS18;FS21 | 2006-12-11 08:00 | 2006-12-28 17:00 | 14d | team subcontractor | 4318.7207 | 26000 | 0 | 0 | 30318.7207 | Cost/Hour is an alternative input for Variable (Baseline) Cost
69 | soil analyses | 1.2.2 | 6FS | FS18 | 2006-12-11 08:00 | 2006-12-12 17:00 | 2d | team subcontractor | 616.96 | 2000 | 0 | 0 | 2616.96
18 | foundation beam | 1.2.3 | 17FS;69FS | FS19 | 2006-12-29 08:00 | 2007-02-01 17:00 | 25d | team subcontractor[3,00 #8] | 23136 | 98523.7266 | 0 | 0 | 121659.7266 | For further explanation, see Guideline for project data input (extended version)
21 | placing sewerage | 1.2.4 | 17FS | FS23 | 2006-12-29 08:00 | 2007-01-11 17:00 | 10d | team subcontractor[3,00 #8] | 9254.4004 | 1224.73 | 0 | 0 | 10479.1309
23 | foundation plate | 1.2.5 | 21FS | FS19 | 2007-01-12 08:00 | 2007-01-12 17:00 | 1d | team subcontractor[5,00 #8] | 1542.4062 | 234819.4375 | 0 | 0 | 236361.8438
48 | shell | 1.3 |  |  | 2007-02-02 08:00 | 2007-04-26 17:00 | 60d |  |  | 472804.4375 |  |  | 542212.4375
19 | steelframe I | 1.3.1 | 18FS;23FS | FS20 | 2007-02-02 08:00 | 2007-03-01 17:00 | 20d | team subcontractor[4,00 #8] | 24678.3984 | 118992.5078 | 0 | 0 | 143670.9062
20 | concrete vaults I | 1.3.2 | 19FS | FS22 | 2007-03-02 08:00 | 2007-03-15 17:00 | 10d | team subcontractor[4,00 #8] | 12339.2031 | 117409.7188 | 0 | 0 | 129748.9219
22 | steelframe II | 1.3.3 | 20FS | FS24 | 2007-03-16 08:00 | 2007-04-05 17:00 | 15d | team subcontractor[3,00 #8] | 13881.6016 | 118992.5078 | 0 | 0 | 132874.1094
24 | concrete vaults II | 1.3.4 | 22FS | FS25;FS49 | 2007-04-06 08:00 | 2007-04-26 17:00 | 15d | team subcontractor[4,00 #8] | 18508.7969 | 117409.7188 | 0 | 0 | 135918.5156
50 | wind and water proof | 1.4 |  |  | 2007-04-27 08:00 | 2007-06-07 17:00 | 30d |  |  | 560844.1875 |  |  | 597047.375
25 | facades | 1.4.1 | 24FS | FS26 | 2007-04-27 08:00 | 2007-05-24 17:00 | 20d | team subcontractor[2,00 #8] | 12339.1875 | 339314 | 0 | 0 | 351653.1875
26 | outside windows | 1.4.2 | 25FS | FS28;FS29 | 2007-05-25 08:00 | 2007-06-07 17:00 | 10d | carpenter[3,00 #3] | 9120 | 150750.5938 | 0 | 0 | 159870.5938
49 | roof | 1.4.3 | 24FS |  | 2007-04-27 08:00 | 2007-05-10 17:00 | 10d | roofer[4,00 #4] | 11520 | 70779.5703 | 40.3 | 3224 | 85523.5703
62 | warehouse | 1.5 |  |  | 2007-06-08 08:00 | 2007-10-31 10:00 | 103d 2h |  |  | 257044.9688 |  |  | 301814.5625
28 | v0 concrete | 1.5.1 | 26FS | FS30;FS27;FS59;FS52;FS45;FS34;FS60;FS51 | 2007-06-08 08:00 | 2007-06-21 17:00 | 10d | team subcontractor[5,00 #8] | 15424 | 134400 | 0 | 0 | 149824
30 | v0 sanitary | 1.5.2 | 31FS;28FS | FS35 | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673
27 | v0 masonry | 1.5.3 | 31FS;28FS |  | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 40.65 | 3252 | 37704.9609
59 | v0 heating | 1.5.4 | 31FS;28FS | FS35 | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | heating engineer | 6912 | 11651 | 0 | 0 | 18563
29 | v0 electricity | 1.5.5 | 26FS;31FS | FS35 | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400
35 | v0 floors | 1.5.6 | 59FS;29FS;30FS | FS41;FS37 | 2007-10-03 10:00 | 2007-10-31 10:00 | 20d | floor layer | 6649.6016 | 75000 | 0 | 0 | 81649.6016
66 | construction leave | 1.6 |  |  | 2007-08-15 10:00 | 2007-08-29 10:00 | 10d |  |  | 0.01 |  |  | 0.01
31 | construction leave | 1.6.1 |  | FS53;FS55;FS56;FS61;FS54;FS30;FS27;FS59;FS52;FS45;FS34;FS60;FS51;FS29 | 2007-08-15 10:00 | 2007-08-29 10:00 | 10d |  | 0 | 0.01 | 0 | 0 | 0.01
63 | level 1 | 1.7 |  |  | 2007-08-29 10:00 | 2007-10-24 10:00 | 40d |  |  | 226284.9844 |  |  | 262542.5938
52 | v1 sanitary | 1.7.1 | 31FS;28FS |  | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673
45 | v1 masonry | 1.7.2 | 31FS;28FS |  | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 40.65 | 3252 | 37704.9609
34 | v1 screed | 1.7.3 | 31FS;28FS | FS67 | 2007-08-29 10:00 | 2007-09-19 10:00 | 15d | screed layer[2,00 #3] | 0 | 106140 | 0 | 0 | 106140
60 | v1 heating | 1.7.4 | 31FS;28FS |  | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | heating engineer | 6912 | 11651 | 43.2 | 6912 | 25475
51 | v1 electricity | 1.7.5 | 31FS;28FS |  | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400
67 | v1 drying screed | 1.7.6 | 34FS | FS57;FS32 | 2007-09-19 10:00 | 2007-09-26 10:00 | 5d |  | 0 | 0.01 | 0 | 0 | 0.01
57 | v1 flooring | 1.7.7 | 67FS | FS41;FS37;FS36 | 2007-09-26 10:00 | 2007-10-24 10:00 | 20d | floor layer | 6649.6016 | 72500 | 0 | 0 | 79149.6016
64 | level 2 | 1.8 |  |  | 2007-08-29 10:00 | 2007-10-24 10:00 | 40d |  |  | 125260.9688 |  |  | 149562.5625
53 | v2 sanitary | 1.8.1 | 31FS |  | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673
55 | v2 masonry | 1.8.2 | 31FS |  | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 0 | 0 | 34452.9609
56 | v2 screed | 1.8.3 | 31FS | FS68;FS36 | 2007-08-29 10:00 | 2007-09-19 10:00 | 15d | screed layer | 0 | 46116 | 0 | 0 | 46116
61 | v2 heating | 1.8.4 | 31FS |  | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | electrician | 5120 | 11651 | 0 | 0 | 16771
54 | v2 electricity | 1.8.5 | 31FS |  | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400
68 | v2 drying screed | 1.8.6 | 56FS | FS58;FS32 | 2007-09-19 10:00 | 2007-09-26 10:00 | 5d |  | 0 | 0.01 | 0 | 0 | 0.01
58 | v2 flooring | 1.8.7 | 68FS | FS41;FS37;FS36 | 2007-09-26 10:00 | 2007-10-24 10:00 | 20d | floor layer | 6649.6016 | 31500 | 0 | 0 | 38149.6016
65 | completion | 1.9 |  |  | 2007-09-26 10:00 | 2007-12-26 10:00 | 65d |  |  | 478615.9062 |  |  | 518712.7188
32 | stucco | 1.9.1 | 68FS;67FS | FS41;FS37 | 2007-09-26 10:00 | 2007-10-17 10:00 | 15d | plasterer[3,00 #4] | 14896.8008 | 8642 | 0 | 0 | 23538.8008
36 | drywall | 1.9.2 | 58FS;57FS;56FS |  | 2007-10-24 10:00 | 2007-11-28 10:00 | 25d |  | 0 | 48000 | 0 | 0 | 48000
41 | kitchen and bar | 1.9.3 | 32FS;58FS;57FS;35FS |  | 2007-10-31 10:00 | 2007-11-21 10:00 | 15d |  | 0 | 87000 | 0 | 0 | 87000
37 | techniques | 1.9.4 | 32FS;58FS;57FS;35FS | FS38;FS42;FS43;FS44 | 2007-10-31 10:00 | 2007-11-21 10:00 | 15d |  | 0 | 2156.0601 | 0 | 0 | 2156.0601
44 | stairs | 1.9.5 | 37FS |  | 2007-11-21 10:00 | 2007-12-05 10:00 | 10d |  | 0 | 33000 | 0 | 0 | 33000
42 | entrance doors | 1.9.6 | 37FS |  | 2007-11-21 10:00 | 2007-12-05 10:00 | 10d |  | 0 | 16000 | 0 | 0 | 16000
43 | elevator | 1.9.7 | 37FS |  | 2007-11-21 10:00 | 2007-11-28 10:00 | 5d |  | 0 | 38817.8516 | 0 | 0 | 38817.8516
38 | suspended ceiling | 1.9.8 | 37FS | FS39 | 2007-11-21 10:00 | 2007-11-28 10:00 | 5d |  | 0 | 32000 | 0 | 0 | 32000
39 | painting | 1.9.9 | 38FS | FS40 | 2007-11-28 10:00 | 2007-12-19 10:00 | 15d | painter[4,00 #6] | 16800 | 83000 | 0 | 0 | 99800
40 | furniture | 1.9.10 | 39FS |  | 2007-12-19 10:00 | 2007-12-26 10:00 | 5d | joiner[5,00 #5] | 8400 | 130000 | 0 | 0 | 138400

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availibility | Cost/Use | Cost/Unit | Assigned To | Total Cost
1 | plumber | Renewable | 4,00 #4 | 0 | 36 | 30;52;53 | 8640
2 | electrician | Renewable | 4,00 #4 | 0 | 32 | 29;54;51;61 | 24320
3 | team subcontractor | Renewable | 8,00 #8 | 0 | 38.56 | 6[4,00 #8];17;18[3,00 #8];19[4,00 #8];20[4,00 #8];21[3,00 #8];22[3,00 #8];24[4,00 #8];25[2,00 #8];28[5,00 #8];69;23[5,00 #8] | 173057.2812
4 | mason | Renewable | 4,00 #4 | 0 | 40.65 | 27;45;55 | 9756
5 | heating engineer | Renewable | 2,00 #2 | 0 | 43.2 | 59;60 | 13824
6 | roofer | Renewable | 4,00 #4 | 0 | 36 | 49[4,00 #4] | 11520
7 | carpenter | Renewable | 3,00 #3 | 0 | 38 | 26[3,00 #3] | 9120
8 | floor layer | Renewable | 4,00 #4 | 0 | 41.56 | 35;57;58 | 19948.8008
9 | screed layer | Renewable | 3,00 #3 | 0 | 0 | 34[2,00 #3];56 | 0
10 | plasterer | Renewable | 4,00 #4 | 0 | 41.38 | 32[3,00 #4] | 14896.8008
11 | painter | Renewable | 6,00 #6 | 0 | 35 | 39[4,00 #6] | 16800
12 | joiner | Renewable | 5,00 #5 | 0 | 42 | 40[5,00 #5] | 8400

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic
0 | PROJECT CLAEYS-VERHELST | 3538h
46 | preparation | 1360h
2 | building permit | 480h | manual - absolute | 402 | 480 | 812
3 | hire contractor | 160h | manual - absolute | 127 | 160 | 326
4 | temporary offices | 160h | standard - symmetric | 80 | 100 | 120
5 | temporary facilities | 480h | standard - symmetric | 80 | 100 | 120
16 | preparation contractor | 480h | standard - no risk | 99 | 100 | 101
6 | demolition | 240h | manual - absolute | 219 | 240 | 302
47 | foundation | 312h
17 | excavation | 112h | standard - symmetric | 80 | 100 | 120
69 | soil analyses | 16h | standard - symmetric | 80 | 100 | 120
18 | foundation beam | 200h | manual - absolute | 159 | 200 | 363
21 | placing sewerage | 80h | manual - absolute | 63 | 80 | 98
23 | foundation plate | 8h | manual - absolute | 6 | 8 | 10
48 | shell | 480h
19 | steelframe I | 160h | manual - absolute | 104 | 120 | 166
20 | concrete vaults I | 80h | manual - absolute | 32 | 40 | 48
22 | steelframe II | 120h | manual - absolute | 64 | 80 | 113
24 | concrete vaults II | 120h | manual - absolute | 66 | 80 | 121
50 | wind and water proof | 240h
25 | facades | 160h | manual - absolute | 128 | 160 | 463
26 | outside windows | 80h | manual - absolute | 64 | 80 | 175
49 | roof | 80h | standard - symmetric | 80 | 100 | 120
62 | warehouse | 826h
28 | v0 concrete | 80h | standard - symmetric | 80 | 100 | 120
30 | v0 sanitary | 80h | standard - no risk | 99 | 100 | 101
27 | v0 masonry | 80h | standard - no risk | 99 | 100 | 101
59 | v0 heating | 160h | standard - no risk | 99 | 100 | 101
29 | v0 electricity | 200h | standard - no risk | 99 | 100 | 101
35 | v0 floors | 160h | manual - absolute | 128 | 163 | 543
66 | construction leave | 80h
31 | construction leave | 80h | standard - no risk | 99 | 100 | 101
63 | level 1 | 320h
52 | v1 sanitary | 80h | standard - no risk | 99 | 100 | 101
45 | v1 masonry | 80h | standard - no risk | 99 | 100 | 101
34 | v1 screed | 120h | standard - no risk | 99 | 100 | 101
60 | v1 heating | 160h | standard - no risk | 99 | 100 | 101
51 | v1 electricity | 200h | standard - no risk | 99 | 100 | 101
67 | v1 drying screed | 40h | standard - skewed left | 80 | 110 | 120
57 | v1 flooring | 160h | manual - absolute | 128 | 160 | 577
64 | level 2 | 320h
53 | v2 sanitary | 80h | standard - no risk | 99 | 100 | 101
55 | v2 masonry | 80h | standard - no risk | 99 | 100 | 101
56 | v2 screed | 120h | standard - skewed left | 80 | 110 | 120
61 | v2 heating | 160h | standard - skewed left | 80 | 110 | 120
54 | v2 electricity | 200h | standard - no risk | 99 | 100 | 101
68 | v2 drying screed | 40h | standard - skewed left | 80 | 110 | 120
58 | v2 flooring | 160h | manual - absolute | 128 | 160 | 556
65 | completion | 520h
32 | stucco | 120h | manual - absolute | 96 | 120 | 451
36 | drywall | 200h | manual - absolute | 160 | 200 | 528
41 | kitchen and bar | 120h | standard - symmetric | 80 | 100 | 120
37 | techniques | 120h | standard - symmetric | 80 | 100 | 120
44 | stairs | 80h | standard - symmetric | 80 | 100 | 120
42 | entrance doors | 80h | standard - symmetric | 80 | 100 | 120
43 | elevator | 40h | standard - symmetric | 80 | 100 | 120
38 | suspended ceiling | 40h | standard - symmetric | 80 | 100 | 120
39 | painting | 120h | standard - symmetric | 80 | 100 | 120
40 | furniture | 40h | standard - symmetric | 80 | 100 | 120

## Project Control - TP1
| TP Status Date | 2006-07-07 08:00 |  | TP Name | Preparation1
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [15 empty] | protrack | [5 empty] | copied values from baseline
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Werkelijke Duurtijd | PAC | PRC | Resterende Duurtijd | PAC Dev | PRC Dev | Werkelijke Kost | Resterende Kost | Percentage Compleet | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost
0 | PROJECT CLAEYS-VERHELST | 2006-04-17 08:00 | 2007-12-26 10:00 | 442d 2h |  |  | 2700210.5 |  |  | 3027133.25 | [9 empty] | 0% |  | 5716.8501 | 5716.8501 | [8 empty] | 0% | 2006-04-17 08:00 | 2007-12-26 10:00 | 442d 2h | 0 | 0 | 2700210.5 | 0 | 0 | 3027133.25
46 | preparation | 2006-04-17 08:00 | 2006-12-08 17:00 | 170d |  |  | 216786.9844 |  |  | 253804.5938 | [9 empty] | 2% |  | 5716.8501 | 5716.8501 | [8 empty] | 2% | 2006-04-17 08:00 | 2006-12-08 17:00 | 170d | 0 | 0 | 216786.9844 | 0 | 0 | 253804.5938
2 | building permit | 2006-04-17 08:00 | 2006-07-07 17:00 | 60d |  | 0 | 75 | 0 | 0 | 75 | 2006-04-17 08:00 | 100d | 75 | 0 | 1d | 0 | 0 | 75 | 0 | 99% | Finished | 75 | 75 | 100d | 75 | 0 | 1d | 0 | 0 | 75 | 0 | 99% | 2006-04-17 08:00 | 2006-07-07 17:00 | 60d | 0 | 0 | 75 | 0 | 0 | 75
3 | hire contractor | 2006-07-10 08:00 | 2006-08-04 17:00 | 20d |  | 0 | 210000 | 0 | 0 | 210000 |  | 0 | 0 | 210000 | 20d | 0 | 0 | 0 | 210000 | 0% | Not Started | 0 | 0 | 0 | 0 | 210000 | 20d | 0 | 0 | 0 | 210000 | 0% | 2006-07-10 08:00 | 2006-08-04 17:00 | 20d | 0 | 0 | 210000 | 0 | 0 | 210000
4 | temporary offices | 2006-04-17 08:00 | 2006-05-12 17:00 | 20d |  | 0 | 3765.3101 | 0 | 0 | 3765.3101 | 2006-04-17 08:00 | 20d | 3765.3101 | 0 | 0 | 0 | 0 | 3765.3101 | 0 | 100% | Finished | 3765.3101 | 3765.3101 | 20d | 3765.3101 | 0 | 0 | 0 | 0 | 3765.3101 | 0 | 100% | 2006-04-17 08:00 | 2006-05-12 17:00 | 20d | 0 | 0 | 3765.3101 | 0 | 0 | 3765.3101
5 | temporary facilities | 2006-04-17 08:00 | 2006-07-07 17:00 | 60d |  | 0 | 1876.54 | 0 | 0 | 1876.54 | 2006-04-17 08:00 | 60d | 1876.54 | 0 | 1d | 0 | 0 | 1876.54 | 0 | 98% | Finished | 1876.54 | 1876.54 | 60d | 1876.54 | 0 | 1d | 0 | 0 | 1876.54 | 0 | 98% | 2006-04-17 08:00 | 2006-07-07 17:00 | 60d | 0 | 0 | 1876.54 | 0 | 0 | 1876.54
16 | preparation contractor | 2006-08-07 08:00 | 2006-10-27 17:00 | 60d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 60d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 0 | 0 | 0.01 | 60d | 0 | 0 | 0 | 0.01 | 0% | 2006-08-07 08:00 | 2006-10-27 17:00 | 60d | 0 | 0 | 0.01 | 0 | 0 | 0.01
6 | demolition | 2006-10-30 08:00 | 2006-12-08 17:00 | 30d | team subcontractor[4,00 #8] | 37017.6016 | 1070.11 | 0 | 0 | 38087.7109 |  | 0 | 0 | 38087.7109 | 30d | 0 | 0 | 0 | 38087.7109 | 0% | Not Started | 0 | 0 | 0 | 0 | 38087.7109 | 30d | 0 | 0 | 0 | 38087.7109 | 0% | 2006-10-30 08:00 | 2006-12-08 17:00 | 30d | team subcontractor[4,00 #8] | 37017.6016 | 1070.11 | 0 | 0 | 38087.7109
47 | foundation | 2006-12-11 08:00 | 2007-02-01 17:00 | 39d |  |  | 362567.875 |  |  | 401436.375 | [9 empty] | 0% |  | 0 | 0 | [8 empty] | 0% | 2006-12-11 08:00 | 2007-02-01 17:00 | 39d | 0 | 0 | 362567.875 | 0 | 0 | 401436.375
17 | excavation | 2006-12-11 08:00 | 2006-12-28 17:00 | 14d | team subcontractor | 4318.7207 | 26000 | 0 | 0 | 30318.7207 |  | 0 | 0 | 30318.7207 | 14d | 0 | 0 | 0 | 30318.7207 | 0% | Not Started | 0 | 0 | 0 | 0 | 30318.7207 | 14d | 0 | 0 | 0 | 30318.7207 | 0% | 2006-12-11 08:00 | 2006-12-28 17:00 | 14d | team subcontractor | 4318.7207 | 26000 | 0 | 0 | 30318.7207
69 | soil analyses | 2006-12-11 08:00 | 2006-12-12 17:00 | 2d | team subcontractor | 616.96 | 2000 | 0 | 0 | 2616.96 |  | 0 | 0 | 2616.96 | 2d | 0 | 0 | 0 | 2616.96 | 0% | Not Started | 0 | 0 | 0 | 0 | 2616.96 | 2d | 0 | 0 | 0 | 2616.96 | 0% | 2006-12-11 08:00 | 2006-12-12 17:00 | 2d | team subcontractor | 616.96 | 2000 | 0 | 0 | 2616.96
18 | foundation beam | 2006-12-29 08:00 | 2007-02-01 17:00 | 25d | team subcontractor[3,00 #8] | 23136 | 98523.7266 | 0 | 0 | 121659.7266 |  | 0 | 0 | 121659.7266 | 25d | 0 | 0 | 0 | 121659.7266 | 0% | Not Started | 0 | 0 | 0 | 0 | 121659.7266 | 25d | 0 | 0 | 0 | 121659.7266 | 0% | 2006-12-29 08:00 | 2007-02-01 17:00 | 25d | team subcontractor[3,00 #8] | 23136 | 98523.7266 | 0 | 0 | 121659.7266
21 | placing sewerage | 2006-12-29 08:00 | 2007-01-11 17:00 | 10d | team subcontractor[3,00 #8] | 9254.4004 | 1224.73 | 0 | 0 | 10479.1309 |  | 0 | 0 | 10479.1309 | 10d | 0 | 0 | 0 | 10479.1309 | 0% | Not Started | 0 | 0 | 0 | 0 | 10479.1309 | 10d | 0 | 0 | 0 | 10479.1309 | 0% | 2006-12-29 08:00 | 2007-01-11 17:00 | 10d | team subcontractor[3,00 #8] | 9254.4004 | 1224.73 | 0 | 0 | 10479.1309
23 | foundation plate | 2007-01-12 08:00 | 2007-01-12 17:00 | 1d | team subcontractor[5,00 #8] | 1542.4062 | 234819.4375 | 0 | 0 | 236361.8438 |  | 0 | 0 | 236361.8438 | 1d | 0 | 0 | 0 | 236361.8438 | 0% | Not Started | 0 | 0 | 0 | 0 | 236361.8438 | 1d | 0 | 0 | 0 | 236361.8438 | 0% | 2007-01-12 08:00 | 2007-01-12 17:00 | 1d | team subcontractor[5,00 #8] | 1542.4062 | 234819.4375 | 0 | 0 | 236361.8438
48 | shell | 2007-02-02 08:00 | 2007-04-26 17:00 | 60d |  |  | 472804.4375 |  |  | 542212.4375 | [9 empty] | 0% |  | 0 | 0 | [8 empty] | 0% | 2007-02-02 08:00 | 2007-04-26 17:00 | 60d | 0 | 0 | 472804.4375 | 0 | 0 | 542212.4375
19 | steelframe I | 2007-02-02 08:00 | 2007-03-01 17:00 | 20d | team subcontractor[4,00 #8] | 24678.3984 | 118992.5078 | 0 | 0 | 143670.9062 |  | 0 | 0 | 143670.9062 | 20d | 0 | 0 | 0 | 143670.9062 | 0% | Not Started | 0 | 0 | 0 | 0 | 143670.9062 | 20d | 0 | 0 | 0 | 143670.9062 | 0% | 2007-02-02 08:00 | 2007-03-01 17:00 | 20d | team subcontractor[4,00 #8] | 24678.3984 | 118992.5078 | 0 | 0 | 143670.9062
20 | concrete vaults I | 2007-03-02 08:00 | 2007-03-15 17:00 | 10d | team subcontractor[4,00 #8] | 12339.2031 | 117409.7188 | 0 | 0 | 129748.9219 |  | 0 | 0 | 129748.9219 | 10d | 0 | 0 | 0 | 129748.9219 | 0% | Not Started | 0 | 0 | 0 | 0 | 129748.9219 | 10d | 0 | 0 | 0 | 129748.9219 | 0% | 2007-03-02 08:00 | 2007-03-15 17:00 | 10d | team subcontractor[4,00 #8] | 12339.2031 | 117409.7188 | 0 | 0 | 129748.9219
22 | steelframe II | 2007-03-16 08:00 | 2007-04-05 17:00 | 15d | team subcontractor[3,00 #8] | 13881.6016 | 118992.5078 | 0 | 0 | 132874.1094 |  | 0 | 0 | 132874.1094 | 15d | 0 | 0 | 0 | 132874.1094 | 0% | Not Started | 0 | 0 | 0 | 0 | 132874.1094 | 15d | 0 | 0 | 0 | 132874.1094 | 0% | 2007-03-16 08:00 | 2007-04-05 17:00 | 15d | team subcontractor[3,00 #8] | 13881.6016 | 118992.5078 | 0 | 0 | 132874.1094
24 | concrete vaults II | 2007-04-06 08:00 | 2007-04-26 17:00 | 15d | team subcontractor[4,00 #8] | 18508.7969 | 117409.7188 | 0 | 0 | 135918.5156 |  | 0 | 0 | 135918.5156 | 15d | 0 | 0 | 0 | 135918.5156 | 0% | Not Started | 0 | 0 | 0 | 0 | 135918.5156 | 15d | 0 | 0 | 0 | 135918.5156 | 0% | 2007-04-06 08:00 | 2007-04-26 17:00 | 15d | team subcontractor[4,00 #8] | 18508.7969 | 117409.7188 | 0 | 0 | 135918.5156
50 | wind and water proof | 2007-04-27 08:00 | 2007-06-07 17:00 | 30d |  |  | 560844.1875 |  |  | 597047.375 | [9 empty] | 0% |  | 0 | 0 | [8 empty] | 0% | 2007-04-27 08:00 | 2007-06-07 17:00 | 30d | 0 | 0 | 560844.1875 | 0 | 0 | 597047.375
25 | facades | 2007-04-27 08:00 | 2007-05-24 17:00 | 20d | team subcontractor[2,00 #8] | 12339.1875 | 339314 | 0 | 0 | 351653.1875 |  | 0 | 0 | 351653.1875 | 20d | 0 | 0 | 0 | 351653.1875 | 0% | Not Started | 0 | 0 | 0 | 0 | 351653.1875 | 20d | 0 | 0 | 0 | 351653.1875 | 0% | 2007-04-27 08:00 | 2007-05-24 17:00 | 20d | team subcontractor[2,00 #8] | 12339.1875 | 339314 | 0 | 0 | 351653.1875
26 | outside windows | 2007-05-25 08:00 | 2007-06-07 17:00 | 10d | carpenter[3,00 #3] | 9120 | 150750.5938 | 0 | 0 | 159870.5938 |  | 0 | 0 | 159870.5938 | 10d | 0 | 0 | 0 | 159870.5938 | 0% | Not Started | 0 | 0 | 0 | 0 | 159870.5938 | 10d | 0 | 0 | 0 | 159870.5938 | 0% | 2007-05-25 08:00 | 2007-06-07 17:00 | 10d | carpenter[3,00 #3] | 9120 | 150750.5938 | 0 | 0 | 159870.5938
49 | roof | 2007-04-27 08:00 | 2007-05-10 17:00 | 10d | roofer[4,00 #4] | 11520 | 70779.5703 | 40.3 | 3224 | 85523.5703 |  | 0 | 0 | 85523.5703 | 10d | 0 | 0 | 0 | 85523.5703 | 0% | Not Started | 0 | 0 | 0 | 0 | 85523.5703 | 10d | 0 | 0 | 0 | 85523.5703 | 0% | 2007-04-27 08:00 | 2007-05-10 17:00 | 10d | roofer[4,00 #4] | 11520 | 70779.5703 | 40.3 | 3224 | 85523.5703
62 | warehouse | 2007-06-08 08:00 | 2007-10-31 10:00 | 103d 2h |  |  | 257044.9688 |  |  | 301814.5625 | [9 empty] | 0% |  | 0 | 0 | [8 empty] | 0% | 2007-06-08 08:00 | 2007-10-31 10:00 | 103d 2h | 0 | 0 | 257044.9688 | 0 | 0 | 301814.5625
28 | v0 concrete | 2007-06-08 08:00 | 2007-06-21 17:00 | 10d | team subcontractor[5,00 #8] | 15424 | 134400 | 0 | 0 | 149824 |  | 0 | 0 | 149824 | 10d | 0 | 0 | 0 | 149824 | 0% | Not Started | 0 | 0 | 0 | 0 | 149824 | 10d | 0 | 0 | 0 | 149824 | 0% | 2007-06-08 08:00 | 2007-06-21 17:00 | 10d | team subcontractor[5,00 #8] | 15424 | 134400 | 0 | 0 | 149824
30 | v0 sanitary | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 |  | 0 | 0 | 7673 | 10d | 0 | 0 | 0 | 7673 | 0% | Not Started | 0 | 0 | 0 | 0 | 7673 | 10d | 0 | 0 | 0 | 7673 | 0% | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673
27 | v0 masonry | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 40.65 | 3252 | 37704.9609 |  | 0 | 0 | 37704.9609 | 10d | 0 | 0 | 0 | 37704.9609 | 0% | Not Started | 0 | 0 | 0 | 0 | 37704.9609 | 10d | 0 | 0 | 0 | 37704.9609 | 0% | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 40.65 | 3252 | 37704.9609
59 | v0 heating | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | heating engineer | 6912 | 11651 | 0 | 0 | 18563 |  | 0 | 0 | 18563 | 20d | 0 | 0 | 0 | 18563 | 0% | Not Started | 0 | 0 | 0 | 0 | 18563 | 20d | 0 | 0 | 0 | 18563 | 0% | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | heating engineer | 6912 | 11651 | 0 | 0 | 18563
29 | v0 electricity | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 |  | 0 | 0 | 6400 | 25d | 0 | 0 | 0 | 6400 | 0% | Not Started | 0 | 0 | 0 | 0 | 6400 | 25d | 0 | 0 | 0 | 6400 | 0% | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400
35 | v0 floors | 2007-10-03 10:00 | 2007-10-31 10:00 | 20d | floor layer | 6649.6016 | 75000 | 0 | 0 | 81649.6016 |  | 0 | 0 | 81649.6016 | 20d | 0 | 0 | 0 | 81649.6016 | 0% | Not Started | 0 | 0 | 0 | 0 | 81649.6016 | 20d | 0 | 0 | 0 | 81649.6016 | 0% | 2007-10-03 10:00 | 2007-10-31 10:00 | 20d | floor layer | 6649.6016 | 75000 | 0 | 0 | 81649.6016
66 | construction leave | 2007-08-15 10:00 | 2007-08-29 10:00 | 10d |  |  | 0.01 |  |  | 0.01 | [9 empty] | 0% |  | 0 | 0 | [8 empty] | 0% | 2007-08-15 10:00 | 2007-08-29 10:00 | 10d | 0 | 0 | 0.01 | 0 | 0 | 0.01
31 | construction leave | 2007-08-15 10:00 | 2007-08-29 10:00 | 10d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 10d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 0 | 0 | 0.01 | 10d | 0 | 0 | 0 | 0.01 | 0% | 2007-08-15 10:00 | 2007-08-29 10:00 | 10d | 0 | 0 | 0.01 | 0 | 0 | 0.01
63 | level 1 | 2007-08-29 10:00 | 2007-10-24 10:00 | 40d |  |  | 226284.9844 |  |  | 262542.5938 | [9 empty] | 0% |  | 0 | 0 | [8 empty] | 0% | 2007-08-29 10:00 | 2007-10-24 10:00 | 40d | 0 | 0 | 226284.9844 | 0 | 0 | 262542.5938
52 | v1 sanitary | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 |  | 0 | 0 | 7673 | 10d | 0 | 0 | 0 | 7673 | 0% | Not Started | 0 | 0 | 0 | 0 | 7673 | 10d | 0 | 0 | 0 | 7673 | 0% | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673
45 | v1 masonry | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 40.65 | 3252 | 37704.9609 |  | 0 | 0 | 37704.9609 | 10d | 0 | 0 | 0 | 37704.9609 | 0% | Not Started | 0 | 0 | 0 | 0 | 37704.9609 | 10d | 0 | 0 | 0 | 37704.9609 | 0% | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 40.65 | 3252 | 37704.9609
34 | v1 screed | 2007-08-29 10:00 | 2007-09-19 10:00 | 15d | screed layer[2,00 #3] | 0 | 106140 | 0 | 0 | 106140 |  | 0 | 0 | 106140 | 15d | 0 | 0 | 0 | 106140 | 0% | Not Started | 0 | 0 | 0 | 0 | 106140 | 15d | 0 | 0 | 0 | 106140 | 0% | 2007-08-29 10:00 | 2007-09-19 10:00 | 15d | screed layer[2,00 #3] | 0 | 106140 | 0 | 0 | 106140
60 | v1 heating | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | heating engineer | 6912 | 11651 | 43.2 | 6912 | 25475 |  | 0 | 0 | 25475 | 20d | 0 | 0 | 0 | 25475 | 0% | Not Started | 0 | 0 | 0 | 0 | 25475 | 20d | 0 | 0 | 0 | 25475 | 0% | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | heating engineer | 6912 | 11651 | 43.2 | 6912 | 25475
51 | v1 electricity | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 |  | 0 | 0 | 6400 | 25d | 0 | 0 | 0 | 6400 | 0% | Not Started | 0 | 0 | 0 | 0 | 6400 | 25d | 0 | 0 | 0 | 6400 | 0% | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400
67 | v1 drying screed | 2007-09-19 10:00 | 2007-09-26 10:00 | 5d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 5d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 0 | 0 | 0.01 | 5d | 0 | 0 | 0 | 0.01 | 0% | 2007-09-19 10:00 | 2007-09-26 10:00 | 5d | 0 | 0 | 0.01 | 0 | 0 | 0.01
57 | v1 flooring | 2007-09-26 10:00 | 2007-10-24 10:00 | 20d | floor layer | 6649.6016 | 72500 | 0 | 0 | 79149.6016 |  | 0 | 0 | 79149.6016 | 20d | 0 | 0 | 0 | 79149.6016 | 0% | Not Started | 0 | 0 | 0 | 0 | 79149.6016 | 20d | 0 | 0 | 0 | 79149.6016 | 0% | 2007-09-26 10:00 | 2007-10-24 10:00 | 20d | floor layer | 6649.6016 | 72500 | 0 | 0 | 79149.6016
64 | level 2 | 2007-08-29 10:00 | 2007-10-24 10:00 | 40d |  |  | 125260.9688 |  |  | 149562.5625 | [9 empty] | 0% |  | 0 | 0 | [8 empty] | 0% | 2007-08-29 10:00 | 2007-10-24 10:00 | 40d | 0 | 0 | 125260.9688 | 0 | 0 | 149562.5625
53 | v2 sanitary | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 |  | 0 | 0 | 7673 | 10d | 0 | 0 | 0 | 7673 | 0% | Not Started | 0 | 0 | 0 | 0 | 7673 | 10d | 0 | 0 | 0 | 7673 | 0% | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673
55 | v2 masonry | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 0 | 0 | 34452.9609 |  | 0 | 0 | 34452.9609 | 10d | 0 | 0 | 0 | 34452.9609 | 0% | Not Started | 0 | 0 | 0 | 0 | 34452.9609 | 10d | 0 | 0 | 0 | 34452.9609 | 0% | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 0 | 0 | 34452.9609
56 | v2 screed | 2007-08-29 10:00 | 2007-09-19 10:00 | 15d | screed layer | 0 | 46116 | 0 | 0 | 46116 |  | 0 | 0 | 46116 | 15d | 0 | 0 | 0 | 46116 | 0% | Not Started | 0 | 0 | 0 | 0 | 46116 | 15d | 0 | 0 | 0 | 46116 | 0% | 2007-08-29 10:00 | 2007-09-19 10:00 | 15d | screed layer | 0 | 46116 | 0 | 0 | 46116
61 | v2 heating | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | electrician | 5120 | 11651 | 0 | 0 | 16771 |  | 0 | 0 | 16771 | 20d | 0 | 0 | 0 | 16771 | 0% | Not Started | 0 | 0 | 0 | 0 | 16771 | 20d | 0 | 0 | 0 | 16771 | 0% | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | electrician | 5120 | 11651 | 0 | 0 | 16771
54 | v2 electricity | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 |  | 0 | 0 | 6400 | 25d | 0 | 0 | 0 | 6400 | 0% | Not Started | 0 | 0 | 0 | 0 | 6400 | 25d | 0 | 0 | 0 | 6400 | 0% | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400
68 | v2 drying screed | 2007-09-19 10:00 | 2007-09-26 10:00 | 5d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 5d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 0 | 0 | 0.01 | 5d | 0 | 0 | 0 | 0.01 | 0% | 2007-09-19 10:00 | 2007-09-26 10:00 | 5d | 0 | 0 | 0.01 | 0 | 0 | 0.01
58 | v2 flooring | 2007-09-26 10:00 | 2007-10-24 10:00 | 20d | floor layer | 6649.6016 | 31500 | 0 | 0 | 38149.6016 |  | 0 | 0 | 38149.6016 | 20d | 0 | 0 | 0 | 38149.6016 | 0% | Not Started | 0 | 0 | 0 | 0 | 38149.6016 | 20d | 0 | 0 | 0 | 38149.6016 | 0% | 2007-09-26 10:00 | 2007-10-24 10:00 | 20d | floor layer | 6649.6016 | 31500 | 0 | 0 | 38149.6016
65 | completion | 2007-09-26 10:00 | 2007-12-26 10:00 | 65d |  |  | 478615.9062 |  |  | 518712.7188 | [9 empty] | 0% |  | 0 | 0 | [8 empty] | 0% | 2007-09-26 10:00 | 2007-12-26 10:00 | 65d | 0 | 0 | 478615.9062 | 0 | 0 | 518712.7188
32 | stucco | 2007-09-26 10:00 | 2007-10-17 10:00 | 15d | plasterer[3,00 #4] | 14896.8008 | 8642 | 0 | 0 | 23538.8008 |  | 0 | 0 | 23538.8008 | 15d | 0 | 0 | 0 | 23538.8008 | 0% | Not Started | 0 | 0 | 0 | 0 | 23538.8008 | 15d | 0 | 0 | 0 | 23538.8008 | 0% | 2007-09-26 10:00 | 2007-10-17 10:00 | 15d | plasterer[3,00 #4] | 14896.8008 | 8642 | 0 | 0 | 23538.8008
36 | drywall | 2007-10-24 10:00 | 2007-11-28 10:00 | 25d |  | 0 | 48000 | 0 | 0 | 48000 |  | 0 | 0 | 48000 | 25d | 0 | 0 | 0 | 48000 | 0% | Not Started | 0 | 0 | 0 | 0 | 48000 | 25d | 0 | 0 | 0 | 48000 | 0% | 2007-10-24 10:00 | 2007-11-28 10:00 | 25d | 0 | 0 | 48000 | 0 | 0 | 48000
41 | kitchen and bar | 2007-10-31 10:00 | 2007-11-21 10:00 | 15d |  | 0 | 87000 | 0 | 0 | 87000 |  | 0 | 0 | 87000 | 15d | 0 | 0 | 0 | 87000 | 0% | Not Started | 0 | 0 | 0 | 0 | 87000 | 15d | 0 | 0 | 0 | 87000 | 0% | 2007-10-31 10:00 | 2007-11-21 10:00 | 15d | 0 | 0 | 87000 | 0 | 0 | 87000
37 | techniques | 2007-10-31 10:00 | 2007-11-21 10:00 | 15d |  | 0 | 2156.0601 | 0 | 0 | 2156.0601 |  | 0 | 0 | 2156.0601 | 15d | 0 | 0 | 0 | 2156.0601 | 0% | Not Started | 0 | 0 | 0 | 0 | 2156.0601 | 15d | 0 | 0 | 0 | 2156.0601 | 0% | 2007-10-31 10:00 | 2007-11-21 10:00 | 15d | 0 | 0 | 2156.0601 | 0 | 0 | 2156.0601
44 | stairs | 2007-11-21 10:00 | 2007-12-05 10:00 | 10d |  | 0 | 33000 | 0 | 0 | 33000 |  | 0 | 0 | 33000 | 10d | 0 | 0 | 0 | 33000 | 0% | Not Started | 0 | 0 | 0 | 0 | 33000 | 10d | 0 | 0 | 0 | 33000 | 0% | 2007-11-21 10:00 | 2007-12-05 10:00 | 10d | 0 | 0 | 33000 | 0 | 0 | 33000
42 | entrance doors | 2007-11-21 10:00 | 2007-12-05 10:00 | 10d |  | 0 | 16000 | 0 | 0 | 16000 |  | 0 | 0 | 16000 | 10d | 0 | 0 | 0 | 16000 | 0% | Not Started | 0 | 0 | 0 | 0 | 16000 | 10d | 0 | 0 | 0 | 16000 | 0% | 2007-11-21 10:00 | 2007-12-05 10:00 | 10d | 0 | 0 | 16000 | 0 | 0 | 16000
43 | elevator | 2007-11-21 10:00 | 2007-11-28 10:00 | 5d |  | 0 | 38817.8516 | 0 | 0 | 38817.8516 |  | 0 | 0 | 38817.8516 | 5d | 0 | 0 | 0 | 38817.8516 | 0% | Not Started | 0 | 0 | 0 | 0 | 38817.8516 | 5d | 0 | 0 | 0 | 38817.8516 | 0% | 2007-11-21 10:00 | 2007-11-28 10:00 | 5d | 0 | 0 | 38817.8516 | 0 | 0 | 38817.8516
38 | suspended ceiling | 2007-11-21 10:00 | 2007-11-28 10:00 | 5d |  | 0 | 32000 | 0 | 0 | 32000 |  | 0 | 0 | 32000 | 5d | 0 | 0 | 0 | 32000 | 0% | Not Started | 0 | 0 | 0 | 0 | 32000 | 5d | 0 | 0 | 0 | 32000 | 0% | 2007-11-21 10:00 | 2007-11-28 10:00 | 5d | 0 | 0 | 32000 | 0 | 0 | 32000
39 | painting | 2007-11-28 10:00 | 2007-12-19 10:00 | 15d | painter[4,00 #6] | 16800 | 83000 | 0 | 0 | 99800 |  | 0 | 0 | 99800 | 15d | 0 | 0 | 0 | 99800 | 0% | Not Started | 0 | 0 | 0 | 0 | 99800 | 15d | 0 | 0 | 0 | 99800 | 0% | 2007-11-28 10:00 | 2007-12-19 10:00 | 15d | painter[4,00 #6] | 16800 | 83000 | 0 | 0 | 99800
40 | furniture | 2007-12-19 10:00 | 2007-12-26 10:00 | 5d | joiner[5,00 #5] | 8400 | 130000 | 0 | 0 | 138400 |  | 0 | 0 | 138400 | 5d | 0 | 0 | 0 | 138400 | 0% | Not Started | 0 | 0 | 0 | 0 | 138400 | 5d | 0 | 0 | 0 | 138400 | 0% | 2007-12-19 10:00 | 2007-12-26 10:00 | 5d | joiner[5,00 #5] | 8400 | 130000 | 0 | 0 | 138400

## TP2
| TP Status Date | 2007-02-08 08:00 |  | TP Name | Preparation2
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [15 empty] | protrack
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Werkelijke Duurtijd | PAC | PRC | Resterende Duurtijd | PAC Dev | PRC Dev | Werkelijke Kost | Resterende Kost | Percentage Compleet
0 | PROJECT CLAEYS-VERHELST | 2006-04-17 08:00 | 2007-12-26 10:00 | 442d 2h |  |  | 2700210.5 |  |  | 3027133.25 | [9 empty] | 8% |  | 253804.5938 | 779169.1875 | [8 empty] | 8%
46 | preparation | 2006-04-17 08:00 | 2006-12-08 17:00 | 170d |  |  | 216786.9844 |  |  | 253804.5938 | [9 empty] | 100% |  | 253804.5938 | 253804.5938 | [8 empty] | 100%
2 | building permit | 2006-04-17 08:00 | 2006-07-07 17:00 | 60d |  | 0 | 75 | 0 | 0 | 75 | 2006-04-17 08:00 | 100d | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 75 | 75 | 100d | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100%
3 | hire contractor | 2006-07-10 08:00 | 2006-08-04 17:00 | 20d |  | 0 | 210000 | 0 | 0 | 210000 | 2006-09-04 08:00 | 30d | 210000 | 0 | 0 | 0 | 0 | 210000 | 0 | 100% | Finished | 210000 | 210000 | 30d | 210000 | 0 | 0 | 0 | 0 | 210000 | 0 | 100%
4 | temporary offices | 2006-04-17 08:00 | 2006-05-12 17:00 | 20d |  | 0 | 3765.3101 | 0 | 0 | 3765.3101 | 2006-04-17 08:00 | 20d | 3765.3101 | 0 | 0 | 0 | 0 | 3765.3101 | 0 | 100% | Finished | 3765.3101 | 3765.3101 | 20d | 3765.3101 | 0 | 0 | 0 | 0 | 3765.3101 | 0 | 100%
5 | temporary facilities | 2006-04-17 08:00 | 2006-07-07 17:00 | 60d |  | 0 | 1876.54 | 0 | 0 | 1876.54 | 2006-04-17 08:00 | 60d | 1876.54 | 0 | 0 | 0 | 0 | 1876.54 | 0 | 100% | Finished | 1876.54 | 1876.54 | 60d | 1876.54 | 0 | 0 | 0 | 0 | 1876.54 | 0 | 100%
16 | preparation contractor | 2006-08-07 08:00 | 2006-10-27 17:00 | 60d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2006-09-04 08:00 | 60d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 60d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100%
6 | demolition | 2006-10-30 08:00 | 2006-12-08 17:00 | 30d | team subcontractor[4,00 #8] | 37017.6016 | 1070.11 | 0 | 0 | 38087.7109 | 2006-11-27 08:00 | 54d | 67701.7891 | 0 | 0 | 0 | 0 | 67701.7891 | 0 | 100% | Finished | 38087.7109 | 38087.7109 | 54d | 67701.7891 | 0 | 0 | 0 | 0 | 67701.7891 | 0 | 100%
47 | foundation | 2006-12-11 08:00 | 2007-02-01 17:00 | 39d |  |  | 362567.875 |  |  | 401436.375 | [9 empty] | 0% |  | 0 | 401436.375 | [8 empty] | 0%
17 | excavation | 2006-12-11 08:00 | 2006-12-28 17:00 | 14d | team subcontractor | 4318.7207 | 26000 | 0 | 0 | 30318.7207 |  | 0 | 0 | 30318.7207 | 14d | 0 | 0 | 0 | 30318.7207 | 0% | Not Started | 0 | 30318.7207 | 0 | 0 | 30318.7207 | 14d | 0 | 0 | 0 | 30318.7207 | 0%
69 | soil analyses | 2006-12-11 08:00 | 2006-12-12 17:00 | 2d | team subcontractor | 616.96 | 2000 | 0 | 0 | 2616.96 |  | 0 | 0 | 2616.96 | 2d | 0 | 0 | 0 | 2616.96 | 0% | Not Started | 0 | 2616.96 | 0 | 0 | 2616.96 | 2d | 0 | 0 | 0 | 2616.96 | 0%
18 | foundation beam | 2006-12-29 08:00 | 2007-02-01 17:00 | 25d | team subcontractor[3,00 #8] | 23136 | 98523.7266 | 0 | 0 | 121659.7266 |  | 0 | 0 | 121659.7266 | 25d | 0 | 0 | 0 | 121659.7266 | 0% | Not Started | 0 | 121659.7266 | 0 | 0 | 121659.7266 | 25d | 0 | 0 | 0 | 121659.7266 | 0%
21 | placing sewerage | 2006-12-29 08:00 | 2007-01-11 17:00 | 10d | team subcontractor[3,00 #8] | 9254.4004 | 1224.73 | 0 | 0 | 10479.1309 |  | 0 | 0 | 10479.1309 | 10d | 0 | 0 | 0 | 10479.1309 | 0% | Not Started | 0 | 10479.1309 | 0 | 0 | 10479.1309 | 10d | 0 | 0 | 0 | 10479.1309 | 0%
23 | foundation plate | 2007-01-12 08:00 | 2007-01-12 17:00 | 1d | team subcontractor[5,00 #8] | 1542.4062 | 234819.4375 | 0 | 0 | 236361.8438 |  | 0 | 0 | 236361.8438 | 1d | 0 | 0 | 0 | 236361.8438 | 0% | Not Started | 0 | 236361.8438 | 0 | 0 | 236361.8438 | 1d | 0 | 0 | 0 | 236361.8438 | 0%
48 | shell | 2007-02-02 08:00 | 2007-04-26 17:00 | 60d |  |  | 472804.4375 |  |  | 542212.4375 | [9 empty] | 0% |  | 0 | 123928.1875 | [8 empty] | 0%
19 | steelframe I | 2007-02-02 08:00 | 2007-03-01 17:00 | 20d | team subcontractor[4,00 #8] | 24678.3984 | 118992.5078 | 0 | 0 | 143670.9062 |  | 0 | 0 | 143670.9062 | 20d | 0 | 0 | 0 | 143670.9062 | 0% | Not Started | 0 | 123928.1875 | 0 | 0 | 143670.9062 | 20d | 0 | 0 | 0 | 143670.9062 | 0%
20 | concrete vaults I | 2007-03-02 08:00 | 2007-03-15 17:00 | 10d | team subcontractor[4,00 #8] | 12339.2031 | 117409.7188 | 0 | 0 | 129748.9219 |  | 0 | 0 | 129748.9219 | 10d | 0 | 0 | 0 | 129748.9219 | 0% | Not Started | 0 | 0 | 0 | 0 | 129748.9219 | 10d | 0 | 0 | 0 | 129748.9219 | 0%
22 | steelframe II | 2007-03-16 08:00 | 2007-04-05 17:00 | 15d | team subcontractor[3,00 #8] | 13881.6016 | 118992.5078 | 0 | 0 | 132874.1094 |  | 0 | 0 | 132874.1094 | 15d | 0 | 0 | 0 | 132874.1094 | 0% | Not Started | 0 | 0 | 0 | 0 | 132874.1094 | 15d | 0 | 0 | 0 | 132874.1094 | 0%
24 | concrete vaults II | 2007-04-06 08:00 | 2007-04-26 17:00 | 15d | team subcontractor[4,00 #8] | 18508.7969 | 117409.7188 | 0 | 0 | 135918.5156 |  | 0 | 0 | 135918.5156 | 15d | 0 | 0 | 0 | 135918.5156 | 0% | Not Started | 0 | 0 | 0 | 0 | 135918.5156 | 15d | 0 | 0 | 0 | 135918.5156 | 0%
50 | wind and water proof | 2007-04-27 08:00 | 2007-06-07 17:00 | 30d |  |  | 560844.1875 |  |  | 597047.375 | [9 empty] | 0% |  | 0 | 0 | [8 empty] | 0%
25 | facades | 2007-04-27 08:00 | 2007-05-24 17:00 | 20d | team subcontractor[2,00 #8] | 12339.1875 | 339314 | 0 | 0 | 351653.1875 |  | 0 | 0 | 351653.1875 | 20d | 0 | 0 | 0 | 351653.1875 | 0% | Not Started | 0 | 0 | 0 | 0 | 351653.1875 | 20d | 0 | 0 | 0 | 351653.1875 | 0%
26 | outside windows | 2007-05-25 08:00 | 2007-06-07 17:00 | 10d | carpenter[3,00 #3] | 9120 | 150750.5938 | 0 | 0 | 159870.5938 |  | 0 | 0 | 159870.5938 | 10d | 0 | 0 | 0 | 159870.5938 | 0% | Not Started | 0 | 0 | 0 | 0 | 159870.5938 | 10d | 0 | 0 | 0 | 159870.5938 | 0%
49 | roof | 2007-04-27 08:00 | 2007-05-10 17:00 | 10d | roofer[4,00 #4] | 11520 | 70779.5703 | 40.3 | 3224 | 85523.5703 |  | 0 | 0 | 85523.5703 | 10d | 0 | 0 | 0 | 85523.5703 | 0% | Not Started | 0 | 0 | 0 | 0 | 85523.5703 | 10d | 0 | 0 | 0 | 85523.5703 | 0%
62 | warehouse | 2007-06-08 08:00 | 2007-10-31 10:00 | 103d 2h |  |  | 257044.9688 |  |  | 301814.5625 | [9 empty] | 0% |  | 0 | 0 | [8 empty] | 0%
28 | v0 concrete | 2007-06-08 08:00 | 2007-06-21 17:00 | 10d | team subcontractor[5,00 #8] | 15424 | 134400 | 0 | 0 | 149824 |  | 0 | 0 | 149824 | 10d | 0 | 0 | 0 | 149824 | 0% | Not Started | 0 | 0 | 0 | 0 | 149824 | 10d | 0 | 0 | 0 | 149824 | 0%
30 | v0 sanitary | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 |  | 0 | 0 | 7673 | 10d | 0 | 0 | 0 | 7673 | 0% | Not Started | 0 | 0 | 0 | 0 | 7673 | 10d | 0 | 0 | 0 | 7673 | 0%
27 | v0 masonry | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 40.65 | 3252 | 37704.9609 |  | 0 | 0 | 37704.9609 | 10d | 0 | 0 | 0 | 37704.9609 | 0% | Not Started | 0 | 0 | 0 | 0 | 37704.9609 | 10d | 0 | 0 | 0 | 37704.9609 | 0%
59 | v0 heating | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | heating engineer | 6912 | 11651 | 0 | 0 | 18563 |  | 0 | 0 | 18563 | 20d | 0 | 0 | 0 | 18563 | 0% | Not Started | 0 | 0 | 0 | 0 | 18563 | 20d | 0 | 0 | 0 | 18563 | 0%
29 | v0 electricity | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 |  | 0 | 0 | 6400 | 25d | 0 | 0 | 0 | 6400 | 0% | Not Started | 0 | 0 | 0 | 0 | 6400 | 25d | 0 | 0 | 0 | 6400 | 0%
35 | v0 floors | 2007-10-03 10:00 | 2007-10-31 10:00 | 20d | floor layer | 6649.6016 | 75000 | 0 | 0 | 81649.6016 |  | 0 | 0 | 81649.6016 | 20d | 0 | 0 | 0 | 81649.6016 | 0% | Not Started | 0 | 0 | 0 | 0 | 81649.6016 | 20d | 0 | 0 | 0 | 81649.6016 | 0%
66 | construction leave | 2007-08-15 10:00 | 2007-08-29 10:00 | 10d |  |  | 0.01 |  |  | 0.01 | [9 empty] | 0% |  | 0 | 0 | [8 empty] | 0%
31 | construction leave | 2007-08-15 10:00 | 2007-08-29 10:00 | 10d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 10d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 0 | 0 | 0.01 | 10d | 0 | 0 | 0 | 0.01 | 0%
63 | level 1 | 2007-08-29 10:00 | 2007-10-24 10:00 | 40d |  |  | 226284.9844 |  |  | 262542.5938 | [9 empty] | 0% |  | 0 | 0 | [8 empty] | 0%
52 | v1 sanitary | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 |  | 0 | 0 | 7673 | 10d | 0 | 0 | 0 | 7673 | 0% | Not Started | 0 | 0 | 0 | 0 | 7673 | 10d | 0 | 0 | 0 | 7673 | 0%
45 | v1 masonry | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 40.65 | 3252 | 37704.9609 |  | 0 | 0 | 37704.9609 | 10d | 0 | 0 | 0 | 37704.9609 | 0% | Not Started | 0 | 0 | 0 | 0 | 37704.9609 | 10d | 0 | 0 | 0 | 37704.9609 | 0%
34 | v1 screed | 2007-08-29 10:00 | 2007-09-19 10:00 | 15d | screed layer[2,00 #3] | 0 | 106140 | 0 | 0 | 106140 |  | 0 | 0 | 106140 | 15d | 0 | 0 | 0 | 106140 | 0% | Not Started | 0 | 0 | 0 | 0 | 106140 | 15d | 0 | 0 | 0 | 106140 | 0%
60 | v1 heating | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | heating engineer | 6912 | 11651 | 43.2 | 6912 | 25475 |  | 0 | 0 | 25475 | 20d | 0 | 0 | 0 | 25475 | 0% | Not Started | 0 | 0 | 0 | 0 | 25475 | 20d | 0 | 0 | 0 | 25475 | 0%
51 | v1 electricity | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 |  | 0 | 0 | 6400 | 25d | 0 | 0 | 0 | 6400 | 0% | Not Started | 0 | 0 | 0 | 0 | 6400 | 25d | 0 | 0 | 0 | 6400 | 0%
67 | v1 drying screed | 2007-09-19 10:00 | 2007-09-26 10:00 | 5d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 5d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 0 | 0 | 0.01 | 5d | 0 | 0 | 0 | 0.01 | 0%
57 | v1 flooring | 2007-09-26 10:00 | 2007-10-24 10:00 | 20d | floor layer | 6649.6016 | 72500 | 0 | 0 | 79149.6016 |  | 0 | 0 | 79149.6016 | 20d | 0 | 0 | 0 | 79149.6016 | 0% | Not Started | 0 | 0 | 0 | 0 | 79149.6016 | 20d | 0 | 0 | 0 | 79149.6016 | 0%
64 | level 2 | 2007-08-29 10:00 | 2007-10-24 10:00 | 40d |  |  | 125260.9688 |  |  | 149562.5625 | [9 empty] | 0% |  | 0 | 0 | [8 empty] | 0%
53 | v2 sanitary | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 |  | 0 | 0 | 7673 | 10d | 0 | 0 | 0 | 7673 | 0% | Not Started | 0 | 0 | 0 | 0 | 7673 | 10d | 0 | 0 | 0 | 7673 | 0%
55 | v2 masonry | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 0 | 0 | 34452.9609 |  | 0 | 0 | 34452.9609 | 10d | 0 | 0 | 0 | 34452.9609 | 0% | Not Started | 0 | 0 | 0 | 0 | 34452.9609 | 10d | 0 | 0 | 0 | 34452.9609 | 0%
56 | v2 screed | 2007-08-29 10:00 | 2007-09-19 10:00 | 15d | screed layer | 0 | 46116 | 0 | 0 | 46116 |  | 0 | 0 | 46116 | 15d | 0 | 0 | 0 | 46116 | 0% | Not Started | 0 | 0 | 0 | 0 | 46116 | 15d | 0 | 0 | 0 | 46116 | 0%
61 | v2 heating | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | electrician | 5120 | 11651 | 0 | 0 | 16771 |  | 0 | 0 | 16771 | 20d | 0 | 0 | 0 | 16771 | 0% | Not Started | 0 | 0 | 0 | 0 | 16771 | 20d | 0 | 0 | 0 | 16771 | 0%
54 | v2 electricity | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 |  | 0 | 0 | 6400 | 25d | 0 | 0 | 0 | 6400 | 0% | Not Started | 0 | 0 | 0 | 0 | 6400 | 25d | 0 | 0 | 0 | 6400 | 0%
68 | v2 drying screed | 2007-09-19 10:00 | 2007-09-26 10:00 | 5d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 5d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 | 0 | 0 | 0.01 | 5d | 0 | 0 | 0 | 0.01 | 0%
58 | v2 flooring | 2007-09-26 10:00 | 2007-10-24 10:00 | 20d | floor layer | 6649.6016 | 31500 | 0 | 0 | 38149.6016 |  | 0 | 0 | 38149.6016 | 20d | 0 | 0 | 0 | 38149.6016 | 0% | Not Started | 0 | 0 | 0 | 0 | 38149.6016 | 20d | 0 | 0 | 0 | 38149.6016 | 0%
65 | completion | 2007-09-26 10:00 | 2007-12-26 10:00 | 65d |  |  | 478615.9062 |  |  | 518712.7188 | [9 empty] | 0% |  | 0 | 0 | [8 empty] | 0%
32 | stucco | 2007-09-26 10:00 | 2007-10-17 10:00 | 15d | plasterer[3,00 #4] | 14896.8008 | 8642 | 0 | 0 | 23538.8008 |  | 0 | 0 | 23538.8008 | 15d | 0 | 0 | 0 | 23538.8008 | 0% | Not Started | 0 | 0 | 0 | 0 | 23538.8008 | 15d | 0 | 0 | 0 | 23538.8008 | 0%
36 | drywall | 2007-10-24 10:00 | 2007-11-28 10:00 | 25d |  | 0 | 48000 | 0 | 0 | 48000 |  | 0 | 0 | 48000 | 25d | 0 | 0 | 0 | 48000 | 0% | Not Started | 0 | 0 | 0 | 0 | 48000 | 25d | 0 | 0 | 0 | 48000 | 0%
41 | kitchen and bar | 2007-10-31 10:00 | 2007-11-21 10:00 | 15d |  | 0 | 87000 | 0 | 0 | 87000 |  | 0 | 0 | 87000 | 15d | 0 | 0 | 0 | 87000 | 0% | Not Started | 0 | 0 | 0 | 0 | 87000 | 15d | 0 | 0 | 0 | 87000 | 0%
37 | techniques | 2007-10-31 10:00 | 2007-11-21 10:00 | 15d |  | 0 | 2156.0601 | 0 | 0 | 2156.0601 |  | 0 | 0 | 2156.0601 | 15d | 0 | 0 | 0 | 2156.0601 | 0% | Not Started | 0 | 0 | 0 | 0 | 2156.0601 | 15d | 0 | 0 | 0 | 2156.0601 | 0%
44 | stairs | 2007-11-21 10:00 | 2007-12-05 10:00 | 10d |  | 0 | 33000 | 0 | 0 | 33000 |  | 0 | 0 | 33000 | 10d | 0 | 0 | 0 | 33000 | 0% | Not Started | 0 | 0 | 0 | 0 | 33000 | 10d | 0 | 0 | 0 | 33000 | 0%
42 | entrance doors | 2007-11-21 10:00 | 2007-12-05 10:00 | 10d |  | 0 | 16000 | 0 | 0 | 16000 |  | 0 | 0 | 16000 | 10d | 0 | 0 | 0 | 16000 | 0% | Not Started | 0 | 0 | 0 | 0 | 16000 | 10d | 0 | 0 | 0 | 16000 | 0%
43 | elevator | 2007-11-21 10:00 | 2007-11-28 10:00 | 5d |  | 0 | 38817.8516 | 0 | 0 | 38817.8516 |  | 0 | 0 | 38817.8516 | 5d | 0 | 0 | 0 | 38817.8516 | 0% | Not Started | 0 | 0 | 0 | 0 | 38817.8516 | 5d | 0 | 0 | 0 | 38817.8516 | 0%
38 | suspended ceiling | 2007-11-21 10:00 | 2007-11-28 10:00 | 5d |  | 0 | 32000 | 0 | 0 | 32000 |  | 0 | 0 | 32000 | 5d | 0 | 0 | 0 | 32000 | 0% | Not Started | 0 | 0 | 0 | 0 | 32000 | 5d | 0 | 0 | 0 | 32000 | 0%
39 | painting | 2007-11-28 10:00 | 2007-12-19 10:00 | 15d | painter[4,00 #6] | 16800 | 83000 | 0 | 0 | 99800 |  | 0 | 0 | 99800 | 15d | 0 | 0 | 0 | 99800 | 0% | Not Started | 0 | 0 | 0 | 0 | 99800 | 15d | 0 | 0 | 0 | 99800 | 0%
40 | furniture | 2007-12-19 10:00 | 2007-12-26 10:00 | 5d | joiner[5,00 #5] | 8400 | 130000 | 0 | 0 | 138400 |  | 0 | 0 | 138400 | 5d | 0 | 0 | 0 | 138400 | 0% | Not Started | 0 | 0 | 0 | 0 | 138400 | 5d | 0 | 0 | 0 | 138400 | 0%

## TP3
| TP Status Date | 2007-03-17 08:00 |  | TP Name | Foundation
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [16 empty] | protrack
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Werkelijke Start | Werkelijke Duurtijd | PAC | PRC | Resterende Duurtijd | PAC Dev | PRC Dev | Werkelijke Kost | Resterende Kost | Percentage Compleet
0 | PROJECT CLAEYS-VERHELST | 2006-04-17 08:00 | 2007-12-26 10:00 | 442d 2h |  |  | 2700210.5 |  |  | 3027133.25 | [9 empty] | 21% |  | 647075.375 | 1048578.75 | [9 empty] | 21%
46 | preparation | 2006-04-17 08:00 | 2006-12-08 17:00 | 170d |  |  | 216786.9844 |  |  | 253804.5938 | [9 empty] | 100% |  | 253804.5938 | 253804.5938 | [9 empty] | 100%
2 | building permit | 2006-04-17 08:00 | 2006-07-07 17:00 | 60d |  | 0 | 75 | 0 | 0 | 75 | 2006-04-17 08:00 | 100d | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 75 | 75 | 2006-04-17 08:00 | 100d | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100%
3 | hire contractor | 2006-07-10 08:00 | 2006-08-04 17:00 | 20d |  | 0 | 210000 | 0 | 0 | 210000 | 2006-09-04 08:00 | 30d | 210000 | 0 | 0 | 0 | 0 | 210000 | 0 | 100% | Finished | 210000 | 210000 | 2006-09-04 08:00 | 30d | 210000 | 0 | 0 | 0 | 0 | 210000 | 0 | 100%
4 | temporary offices | 2006-04-17 08:00 | 2006-05-12 17:00 | 20d |  | 0 | 3765.3101 | 0 | 0 | 3765.3101 | 2006-04-17 08:00 | 20d | 3765.3101 | 0 | 0 | 0 | 0 | 3765.3101 | 0 | 100% | Finished | 3765.3101 | 3765.3101 | 2006-04-17 08:00 | 20d | 3765.3101 | 0 | 0 | 0 | 0 | 3765.3101 | 0 | 100%
5 | temporary facilities | 2006-04-17 08:00 | 2006-07-07 17:00 | 60d |  | 0 | 1876.54 | 0 | 0 | 1876.54 | 2006-04-17 08:00 | 60d | 1876.54 | 0 | 0 | 0 | 0 | 1876.54 | 0 | 100% | Finished | 1876.54 | 1876.54 | 2006-04-17 08:00 | 60d | 1876.54 | 0 | 0 | 0 | 0 | 1876.54 | 0 | 100%
16 | preparation contractor | 2006-08-07 08:00 | 2006-10-27 17:00 | 60d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2006-09-04 08:00 | 60d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 2006-09-04 08:00 | 60d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100%
6 | demolition | 2006-10-30 08:00 | 2006-12-08 17:00 | 30d | team subcontractor[4,00 #8] | 37017.6016 | 1070.11 | 0 | 0 | 38087.7109 | 2006-11-27 08:00 | 54d | 67701.7891 | 0 | 0 | 0 | 0 | 67701.7891 | 0 | 100% | Finished | 38087.7109 | 38087.7109 | 2006-11-27 08:00 | 54d | 67701.7891 | 0 | 0 | 0 | 0 | 67701.7891 | 0 | 100%
47 | foundation | 2006-12-11 08:00 | 2007-02-01 17:00 | 39d |  |  | 362567.875 |  |  | 401436.375 | [9 empty] | 98% |  | 393270.75 | 401436.375 | [9 empty] | 98%
17 | excavation | 2006-12-11 08:00 | 2006-12-28 17:00 | 14d | team subcontractor | 4318.7207 | 26000 | 0 | 0 | 30318.7207 | 2007-02-08 08:00 | 10d | 29084.8008 | 0 | 0 | 0 | 0 | 29084.8008 | 0 | 100% | Finished | 30318.7207 | 30318.7207 | 2007-02-08 08:00 | 10d | 29084.8008 | 0 | 0 | 0 | 0 | 29084.8008 | 0 | 100%
69 | soil analyses | 2006-12-11 08:00 | 2006-12-12 17:00 | 2d | team subcontractor | 616.96 | 2000 | 0 | 0 | 2616.96 | 2007-02-08 08:00 | 12d | 5701.7603 | 0 | 0 | 0 | 0 | 5701.7603 | 0 | 100% | Finished | 2616.96 | 2616.96 | 2007-02-08 08:00 | 12d | 5701.7603 | 0 | 0 | 0 | 0 | 5701.7603 | 0 | 100%
18 | foundation beam | 2006-12-29 08:00 | 2007-02-01 17:00 | 25d | team subcontractor[3,00 #8] | 23136 | 98523.7266 | 0 | 0 | 121659.7266 | 2007-02-28 08:00 | 22d | 118883.4062 | 11105.2803 | 12d | 0 | 0 | 118883.4062 | 11105.2803 | 65% | Started | 113494.0859 | 121659.7266 | 2007-02-28 08:00 | 22d | 118883.4062 | 11105.2803 | 12d | 0 | 0 | 118883.4062 | 11105.2803 | 65%
21 | placing sewerage | 2006-12-29 08:00 | 2007-01-11 17:00 | 10d | team subcontractor[3,00 #8] | 9254.4004 | 1224.73 | 0 | 0 | 10479.1309 | 2007-02-28 08:00 | 12d | 12330.0098 | 0 | 0 | 0 | 0 | 12330.0098 | 0 | 100% | Finished | 10479.1309 | 10479.1309 | 2007-02-28 08:00 | 12d | 12330.0098 | 0 | 0 | 0 | 0 | 12330.0098 | 0 | 100%
23 | foundation plate | 2007-01-12 08:00 | 2007-01-12 17:00 | 1d | team subcontractor[5,00 #8] | 1542.4062 | 234819.4375 | 0 | 0 | 236361.8438 | 2007-03-16 08:00 | 1d | 236361.8438 | 0 | 0 | 0 | 0 | 236361.8438 | 0 | 100% | Finished | 236361.8438 | 236361.8438 | 2007-03-16 08:00 | 1d | 236361.8438 | 0 | 0 | 0 | 0 | 236361.8438 | 0 | 100%
48 | shell | 2007-02-02 08:00 | 2007-04-26 17:00 | 60d |  |  | 472804.4375 |  |  | 542212.4375 | [9 empty] | 0% |  | 0 | 393337.75 | [9 empty] | 0%
19 | steelframe I | 2007-02-02 08:00 | 2007-03-01 17:00 | 20d | team subcontractor[4,00 #8] | 24678.3984 | 118992.5078 | 0 | 0 | 143670.9062 |  | 0 | 0 | 143670.9062 | 20d | 0 | 0 | 0 | 143670.9062 | 0% | Not Started | 0 | 143670.9062 |  | 0 | 0 | 143670.9062 | 20d | 0 | 0 | 0 | 143670.9062 | 0%
20 | concrete vaults I | 2007-03-02 08:00 | 2007-03-15 17:00 | 10d | team subcontractor[4,00 #8] | 12339.2031 | 117409.7188 | 0 | 0 | 129748.9219 |  | 0 | 0 | 129748.9219 | 10d | 0 | 0 | 0 | 129748.9219 | 0% | Not Started | 0 | 129748.9219 |  | 0 | 0 | 129748.9219 | 10d | 0 | 0 | 0 | 129748.9219 | 0%
22 | steelframe II | 2007-03-16 08:00 | 2007-04-05 17:00 | 15d | team subcontractor[3,00 #8] | 13881.6016 | 118992.5078 | 0 | 0 | 132874.1094 |  | 0 | 0 | 132874.1094 | 15d | 0 | 0 | 0 | 132874.1094 | 0% | Not Started | 0 | 119917.9453 |  | 0 | 0 | 132874.1094 | 15d | 0 | 0 | 0 | 132874.1094 | 0%
24 | concrete vaults II | 2007-04-06 08:00 | 2007-04-26 17:00 | 15d | team subcontractor[4,00 #8] | 18508.7969 | 117409.7188 | 0 | 0 | 135918.5156 |  | 0 | 0 | 135918.5156 | 15d | 0 | 0 | 0 | 135918.5156 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 135918.5156 | 15d | 0 | 0 | 0 | 135918.5156 | 0%
50 | wind and water proof | 2007-04-27 08:00 | 2007-06-07 17:00 | 30d |  |  | 560844.1875 |  |  | 597047.375 | [9 empty] | 0% |  | 0 | 0 | [9 empty] | 0%
25 | facades | 2007-04-27 08:00 | 2007-05-24 17:00 | 20d | team subcontractor[2,00 #8] | 12339.1875 | 339314 | 0 | 0 | 351653.1875 |  | 0 | 0 | 351653.1875 | 20d | 0 | 0 | 0 | 351653.1875 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 351653.1875 | 20d | 0 | 0 | 0 | 351653.1875 | 0%
26 | outside windows | 2007-05-25 08:00 | 2007-06-07 17:00 | 10d | carpenter[3,00 #3] | 9120 | 150750.5938 | 0 | 0 | 159870.5938 |  | 0 | 0 | 159870.5938 | 10d | 0 | 0 | 0 | 159870.5938 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 159870.5938 | 10d | 0 | 0 | 0 | 159870.5938 | 0%
49 | roof | 2007-04-27 08:00 | 2007-05-10 17:00 | 10d | roofer[4,00 #4] | 11520 | 70779.5703 | 40.3 | 3224 | 85523.5703 |  | 0 | 0 | 85523.5703 | 10d | 0 | 0 | 0 | 85523.5703 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 85523.5703 | 10d | 0 | 0 | 0 | 85523.5703 | 0%
62 | warehouse | 2007-06-08 08:00 | 2007-10-31 10:00 | 103d 2h |  |  | 257044.9688 |  |  | 301814.5625 | [9 empty] | 0% |  | 0 | 0 | [9 empty] | 0%
28 | v0 concrete | 2007-06-08 08:00 | 2007-06-21 17:00 | 10d | team subcontractor[5,00 #8] | 15424 | 134400 | 0 | 0 | 149824 |  | 0 | 0 | 149824 | 10d | 0 | 0 | 0 | 149824 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 149824 | 10d | 0 | 0 | 0 | 149824 | 0%
30 | v0 sanitary | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 |  | 0 | 0 | 7673 | 10d | 0 | 0 | 0 | 7673 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 7673 | 10d | 0 | 0 | 0 | 7673 | 0%
27 | v0 masonry | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 40.65 | 3252 | 37704.9609 |  | 0 | 0 | 37704.9609 | 10d | 0 | 0 | 0 | 37704.9609 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 37704.9609 | 10d | 0 | 0 | 0 | 37704.9609 | 0%
59 | v0 heating | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | heating engineer | 6912 | 11651 | 0 | 0 | 18563 |  | 0 | 0 | 18563 | 20d | 0 | 0 | 0 | 18563 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 18563 | 20d | 0 | 0 | 0 | 18563 | 0%
29 | v0 electricity | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 |  | 0 | 0 | 6400 | 25d | 0 | 0 | 0 | 6400 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 6400 | 25d | 0 | 0 | 0 | 6400 | 0%
35 | v0 floors | 2007-10-03 10:00 | 2007-10-31 10:00 | 20d | floor layer | 6649.6016 | 75000 | 0 | 0 | 81649.6016 |  | 0 | 0 | 81649.6016 | 20d | 0 | 0 | 0 | 81649.6016 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 81649.6016 | 20d | 0 | 0 | 0 | 81649.6016 | 0%
66 | construction leave | 2007-08-15 10:00 | 2007-08-29 10:00 | 10d |  |  | 0.01 |  |  | 0.01 | [9 empty] | 0% |  | 0 | 0 | [9 empty] | 0%
31 | construction leave | 2007-08-15 10:00 | 2007-08-29 10:00 | 10d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 10d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 0.01 | 10d | 0 | 0 | 0 | 0.01 | 0%
63 | level 1 | 2007-08-29 10:00 | 2007-10-24 10:00 | 40d |  |  | 226284.9844 |  |  | 262542.5938 | [9 empty] | 0% |  | 0 | 0 | [9 empty] | 0%
52 | v1 sanitary | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 |  | 0 | 0 | 7673 | 10d | 0 | 0 | 0 | 7673 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 7673 | 10d | 0 | 0 | 0 | 7673 | 0%
45 | v1 masonry | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 40.65 | 3252 | 37704.9609 |  | 0 | 0 | 37704.9609 | 10d | 0 | 0 | 0 | 37704.9609 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 37704.9609 | 10d | 0 | 0 | 0 | 37704.9609 | 0%
34 | v1 screed | 2007-08-29 10:00 | 2007-09-19 10:00 | 15d | screed layer[2,00 #3] | 0 | 106140 | 0 | 0 | 106140 |  | 0 | 0 | 106140 | 15d | 0 | 0 | 0 | 106140 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 106140 | 15d | 0 | 0 | 0 | 106140 | 0%
60 | v1 heating | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | heating engineer | 6912 | 11651 | 43.2 | 6912 | 25475 |  | 0 | 0 | 25475 | 20d | 0 | 0 | 0 | 25475 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 25475 | 20d | 0 | 0 | 0 | 25475 | 0%
51 | v1 electricity | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 |  | 0 | 0 | 6400 | 25d | 0 | 0 | 0 | 6400 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 6400 | 25d | 0 | 0 | 0 | 6400 | 0%
67 | v1 drying screed | 2007-09-19 10:00 | 2007-09-26 10:00 | 5d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 5d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 0.01 | 5d | 0 | 0 | 0 | 0.01 | 0%
57 | v1 flooring | 2007-09-26 10:00 | 2007-10-24 10:00 | 20d | floor layer | 6649.6016 | 72500 | 0 | 0 | 79149.6016 |  | 0 | 0 | 79149.6016 | 20d | 0 | 0 | 0 | 79149.6016 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 79149.6016 | 20d | 0 | 0 | 0 | 79149.6016 | 0%
64 | level 2 | 2007-08-29 10:00 | 2007-10-24 10:00 | 40d |  |  | 125260.9688 |  |  | 149562.5625 | [9 empty] | 0% |  | 0 | 0 | [9 empty] | 0%
53 | v2 sanitary | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 |  | 0 | 0 | 7673 | 10d | 0 | 0 | 0 | 7673 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 7673 | 10d | 0 | 0 | 0 | 7673 | 0%
55 | v2 masonry | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 0 | 0 | 34452.9609 |  | 0 | 0 | 34452.9609 | 10d | 0 | 0 | 0 | 34452.9609 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 34452.9609 | 10d | 0 | 0 | 0 | 34452.9609 | 0%
56 | v2 screed | 2007-08-29 10:00 | 2007-09-19 10:00 | 15d | screed layer | 0 | 46116 | 0 | 0 | 46116 |  | 0 | 0 | 46116 | 15d | 0 | 0 | 0 | 46116 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 46116 | 15d | 0 | 0 | 0 | 46116 | 0%
61 | v2 heating | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | electrician | 5120 | 11651 | 0 | 0 | 16771 |  | 0 | 0 | 16771 | 20d | 0 | 0 | 0 | 16771 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 16771 | 20d | 0 | 0 | 0 | 16771 | 0%
54 | v2 electricity | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 |  | 0 | 0 | 6400 | 25d | 0 | 0 | 0 | 6400 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 6400 | 25d | 0 | 0 | 0 | 6400 | 0%
68 | v2 drying screed | 2007-09-19 10:00 | 2007-09-26 10:00 | 5d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 5d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 0.01 | 5d | 0 | 0 | 0 | 0.01 | 0%
58 | v2 flooring | 2007-09-26 10:00 | 2007-10-24 10:00 | 20d | floor layer | 6649.6016 | 31500 | 0 | 0 | 38149.6016 |  | 0 | 0 | 38149.6016 | 20d | 0 | 0 | 0 | 38149.6016 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 38149.6016 | 20d | 0 | 0 | 0 | 38149.6016 | 0%
65 | completion | 2007-09-26 10:00 | 2007-12-26 10:00 | 65d |  |  | 478615.9062 |  |  | 518712.7188 | [9 empty] | 0% |  | 0 | 0 | [9 empty] | 0%
32 | stucco | 2007-09-26 10:00 | 2007-10-17 10:00 | 15d | plasterer[3,00 #4] | 14896.8008 | 8642 | 0 | 0 | 23538.8008 |  | 0 | 0 | 23538.8008 | 15d | 0 | 0 | 0 | 23538.8008 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 23538.8008 | 15d | 0 | 0 | 0 | 23538.8008 | 0%
36 | drywall | 2007-10-24 10:00 | 2007-11-28 10:00 | 25d |  | 0 | 48000 | 0 | 0 | 48000 |  | 0 | 0 | 48000 | 25d | 0 | 0 | 0 | 48000 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 48000 | 25d | 0 | 0 | 0 | 48000 | 0%
41 | kitchen and bar | 2007-10-31 10:00 | 2007-11-21 10:00 | 15d |  | 0 | 87000 | 0 | 0 | 87000 |  | 0 | 0 | 87000 | 15d | 0 | 0 | 0 | 87000 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 87000 | 15d | 0 | 0 | 0 | 87000 | 0%
37 | techniques | 2007-10-31 10:00 | 2007-11-21 10:00 | 15d |  | 0 | 2156.0601 | 0 | 0 | 2156.0601 |  | 0 | 0 | 2156.0601 | 15d | 0 | 0 | 0 | 2156.0601 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 2156.0601 | 15d | 0 | 0 | 0 | 2156.0601 | 0%
44 | stairs | 2007-11-21 10:00 | 2007-12-05 10:00 | 10d |  | 0 | 33000 | 0 | 0 | 33000 |  | 0 | 0 | 33000 | 10d | 0 | 0 | 0 | 33000 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 33000 | 10d | 0 | 0 | 0 | 33000 | 0%
42 | entrance doors | 2007-11-21 10:00 | 2007-12-05 10:00 | 10d |  | 0 | 16000 | 0 | 0 | 16000 |  | 0 | 0 | 16000 | 10d | 0 | 0 | 0 | 16000 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 16000 | 10d | 0 | 0 | 0 | 16000 | 0%
43 | elevator | 2007-11-21 10:00 | 2007-11-28 10:00 | 5d |  | 0 | 38817.8516 | 0 | 0 | 38817.8516 |  | 0 | 0 | 38817.8516 | 5d | 0 | 0 | 0 | 38817.8516 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 38817.8516 | 5d | 0 | 0 | 0 | 38817.8516 | 0%
38 | suspended ceiling | 2007-11-21 10:00 | 2007-11-28 10:00 | 5d |  | 0 | 32000 | 0 | 0 | 32000 |  | 0 | 0 | 32000 | 5d | 0 | 0 | 0 | 32000 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 32000 | 5d | 0 | 0 | 0 | 32000 | 0%
39 | painting | 2007-11-28 10:00 | 2007-12-19 10:00 | 15d | painter[4,00 #6] | 16800 | 83000 | 0 | 0 | 99800 |  | 0 | 0 | 99800 | 15d | 0 | 0 | 0 | 99800 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 99800 | 15d | 0 | 0 | 0 | 99800 | 0%
40 | furniture | 2007-12-19 10:00 | 2007-12-26 10:00 | 5d | joiner[5,00 #5] | 8400 | 130000 | 0 | 0 | 138400 |  | 0 | 0 | 138400 | 5d | 0 | 0 | 0 | 138400 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 138400 | 5d | 0 | 0 | 0 | 138400 | 0%

## TP4
| TP Status Date | 2007-06-04 08:00 |  | TP Name | Shell
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [16 empty] | protrack
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Werkelijke Start | Werkelijke Duurtijd | PAC | PRC | Resterende Duurtijd | PAC Dev | PRC Dev | Werkelijke Kost | Resterende Kost | Percentage Compleet
0 | PROJECT CLAEYS-VERHELST | 2006-04-17 08:00 | 2007-12-26 10:00 | 442d 2h |  |  | 2700210.5 |  |  | 3027133.25 | [9 empty] | 39% |  | 1183389.5 | 1790852.875 | [9 empty] | 39%
46 | preparation | 2006-04-17 08:00 | 2006-12-08 17:00 | 170d |  |  | 216786.9844 |  |  | 253804.5938 | [9 empty] | 100% |  | 253804.5938 | 253804.5938 | [9 empty] | 100%
2 | building permit | 2006-04-17 08:00 | 2006-07-07 17:00 | 60d |  | 0 | 75 | 0 | 0 | 75 | 2006-04-17 08:00 | 100d | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 75 | 75 | 2006-04-17 08:00 | 100d | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100%
3 | hire contractor | 2006-07-10 08:00 | 2006-08-04 17:00 | 20d |  | 0 | 210000 | 0 | 0 | 210000 | 2006-09-04 08:00 | 30d | 210000 | 0 | 0 | 0 | 0 | 210000 | 0 | 100% | Finished | 210000 | 210000 | 2006-09-04 08:00 | 30d | 210000 | 0 | 0 | 0 | 0 | 210000 | 0 | 100%
4 | temporary offices | 2006-04-17 08:00 | 2006-05-12 17:00 | 20d |  | 0 | 3765.3101 | 0 | 0 | 3765.3101 | 2006-04-17 08:00 | 20d | 3765.3101 | 0 | 0 | 0 | 0 | 3765.3101 | 0 | 100% | Finished | 3765.3101 | 3765.3101 | 2006-04-17 08:00 | 20d | 3765.3101 | 0 | 0 | 0 | 0 | 3765.3101 | 0 | 100%
5 | temporary facilities | 2006-04-17 08:00 | 2006-07-07 17:00 | 60d |  | 0 | 1876.54 | 0 | 0 | 1876.54 | 2006-04-17 08:00 | 60d | 1876.54 | 0 | 0 | 0 | 0 | 1876.54 | 0 | 100% | Finished | 1876.54 | 1876.54 | 2006-04-17 08:00 | 60d | 1876.54 | 0 | 0 | 0 | 0 | 1876.54 | 0 | 100%
16 | preparation contractor | 2006-08-07 08:00 | 2006-10-27 17:00 | 60d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2006-09-04 08:00 | 60d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 2006-09-04 08:00 | 60d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100%
6 | demolition | 2006-10-30 08:00 | 2006-12-08 17:00 | 30d | team subcontractor[4,00 #8] | 37017.6016 | 1070.11 | 0 | 0 | 38087.7109 | 2006-11-27 08:00 | 54d | 67701.7891 | 0 | 0 | 0 | 0 | 67701.7891 | 0 | 100% | Finished | 38087.7109 | 38087.7109 | 2006-11-27 08:00 | 54d | 67701.7891 | 0 | 0 | 0 | 0 | 67701.7891 | 0 | 100%
47 | foundation | 2006-12-11 08:00 | 2007-02-01 17:00 | 39d |  |  | 362567.875 |  |  | 401436.375 | [9 empty] | 100% |  | 401436.375 | 401436.375 | [9 empty] | 100%
17 | excavation | 2006-12-11 08:00 | 2006-12-28 17:00 | 14d | team subcontractor | 4318.7207 | 26000 | 0 | 0 | 30318.7207 | 2007-02-08 08:00 | 10d | 29084.8008 | 0 | 0 | 0 | 0 | 29084.8008 | 0 | 100% | Finished | 30318.7207 | 30318.7207 | 2007-02-08 08:00 | 10d | 29084.8008 | 0 | 0 | 0 | 0 | 29084.8008 | 0 | 100%
69 | soil analyses | 2006-12-11 08:00 | 2006-12-12 17:00 | 2d | team subcontractor | 616.96 | 2000 | 0 | 0 | 2616.96 | 2007-02-08 08:00 | 12d | 5701.7603 | 0 | 0 | 0 | 0 | 5701.7603 | 0 | 100% | Finished | 2616.96 | 2616.96 | 2007-02-08 08:00 | 12d | 5701.7603 | 0 | 0 | 0 | 0 | 5701.7603 | 0 | 100%
18 | foundation beam | 2006-12-29 08:00 | 2007-02-01 17:00 | 25d | team subcontractor[3,00 #8] | 23136 | 98523.7266 | 0 | 0 | 121659.7266 | 2007-02-28 08:00 | 22d | 118883.4062 | 0 | 0 | 0 | 0 | 118883.4062 | 0 | 100% | Finished | 121659.7266 | 121659.7266 | 2007-02-28 08:00 | 22d | 118883.4062 | 0 | 0 | 0 | 0 | 118883.4062 | 0 | 100%
21 | placing sewerage | 2006-12-29 08:00 | 2007-01-11 17:00 | 10d | team subcontractor[3,00 #8] | 9254.4004 | 1224.73 | 0 | 0 | 10479.1309 | 2007-02-28 08:00 | 12d | 12330.0098 | 0 | 0 | 0 | 0 | 12330.0098 | 0 | 100% | Finished | 10479.1309 | 10479.1309 | 2007-02-28 08:00 | 12d | 12330.0098 | 0 | 0 | 0 | 0 | 12330.0098 | 0 | 100%
23 | foundation plate | 2007-01-12 08:00 | 2007-01-12 17:00 | 1d | team subcontractor[5,00 #8] | 1542.4062 | 234819.4375 | 0 | 0 | 236361.8438 | 2007-03-16 08:00 | 1d | 236361.8438 | 0 | 0 | 0 | 0 | 236361.8438 | 0 | 100% | Finished | 236361.8438 | 236361.8438 | 2007-03-16 08:00 | 1d | 236361.8438 | 0 | 0 | 0 | 0 | 236361.8438 | 0 | 100%
48 | shell | 2007-02-02 08:00 | 2007-04-26 17:00 | 60d |  |  | 472804.4375 |  |  | 542212.4375 | [9 empty] | 97% |  | 528148.4197 | 542212.4375 | [9 empty] | 97%
19 | steelframe I | 2007-02-02 08:00 | 2007-03-01 17:00 | 20d | team subcontractor[4,00 #8] | 24678.3984 | 118992.5078 | 0 | 0 | 143670.9062 | 2007-04-02 08:00 | 15d | 137501.3125 | 24524.1602 | 19d 7u | 0 | 0 | 137501.3125 | 24524.1602 | 43% | Finished | 129606.8727 | 143670.9062 | 2007-04-02 08:00 | 15d | 137501.3125 | 24524.1602 | 19d 7u | 0 | 0 | 137501.3125 | 24524.1602 | 43%
20 | concrete vaults I | 2007-03-02 08:00 | 2007-03-15 17:00 | 10d | team subcontractor[4,00 #8] | 12339.2031 | 117409.7188 | 0 | 0 | 129748.9219 | 2007-04-23 08:00 | 5d | 123579.3203 | 0 | 0 | 0 | 0 | 123579.3203 | 0 | 100% | Finished | 129748.9219 | 129748.9219 | 2007-04-23 08:00 | 5d | 123579.3203 | 0 | 0 | 0 | 0 | 123579.3203 | 0 | 100%
22 | steelframe II | 2007-03-16 08:00 | 2007-04-05 17:00 | 15d | team subcontractor[3,00 #8] | 13881.6016 | 118992.5078 | 0 | 0 | 132874.1094 | 2007-04-30 08:00 | 15d | 132874.1094 | 0 | 0 | 0 | 0 | 132874.1094 | 0 | 100% | Finished | 132874.1094 | 132874.1094 | 2007-04-30 08:00 | 15d | 132874.1094 | 0 | 0 | 0 | 0 | 132874.1094 | 0 | 100%
24 | concrete vaults II | 2007-04-06 08:00 | 2007-04-26 17:00 | 15d | team subcontractor[4,00 #8] | 18508.7969 | 117409.7188 | 0 | 0 | 135918.5156 | 2007-05-21 08:00 | 10d | 129748.9219 | 0 | 0 | 0 | 0 | 129748.9219 | 0 | 100% | Finished | 135918.5156 | 135918.5156 | 2007-05-21 08:00 | 10d | 129748.9219 | 0 | 0 | 0 | 0 | 129748.9219 | 0 | 100%
50 | wind and water proof | 2007-04-27 08:00 | 2007-06-07 17:00 | 30d |  |  | 560844.1875 |  |  | 597047.375 | [9 empty] | 0% |  | 0 | 593399.375 | [9 empty] | 0%
25 | facades | 2007-04-27 08:00 | 2007-05-24 17:00 | 20d | team subcontractor[2,00 #8] | 12339.1875 | 339314 | 0 | 0 | 351653.1875 |  | 0 | 0 | 351653.1875 | 20d | 0 | 0 | 0 | 351653.1875 | 0% | Not Started | 0 | 351653.1875 |  | 0 | 0 | 351653.1875 | 20d | 0 | 0 | 0 | 351653.1875 | 0%
26 | outside windows | 2007-05-25 08:00 | 2007-06-07 17:00 | 10d | carpenter[3,00 #3] | 9120 | 150750.5938 | 0 | 0 | 159870.5938 |  | 0 | 0 | 159870.5938 | 10d | 0 | 0 | 0 | 159870.5938 | 0% | Not Started | 0 | 156222.5938 |  | 0 | 0 | 159870.5938 | 10d | 0 | 0 | 0 | 159870.5938 | 0%
49 | roof | 2007-04-27 08:00 | 2007-05-10 17:00 | 10d | roofer[4,00 #4] | 11520 | 70779.5703 | 40.3 | 3224 | 85523.5703 |  | 0 | 0 | 85523.5703 | 10d | 0 | 0 | 0 | 85523.5703 | 0% | Not Started | 0 | 85523.5703 |  | 0 | 0 | 85523.5703 | 10d | 0 | 0 | 0 | 85523.5703 | 0%
62 | warehouse | 2007-06-08 08:00 | 2007-10-31 10:00 | 103d 2h |  |  | 257044.9688 |  |  | 301814.5625 | [9 empty] | 0% |  | 0 | 0 | [9 empty] | 0%
28 | v0 concrete | 2007-06-08 08:00 | 2007-06-21 17:00 | 10d | team subcontractor[5,00 #8] | 15424 | 134400 | 0 | 0 | 149824 |  | 0 | 0 | 149824 | 10d | 0 | 0 | 0 | 149824 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 149824 | 10d | 0 | 0 | 0 | 149824 | 0%
30 | v0 sanitary | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 |  | 0 | 0 | 7673 | 10d | 0 | 0 | 0 | 7673 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 7673 | 10d | 0 | 0 | 0 | 7673 | 0%
27 | v0 masonry | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 40.65 | 3252 | 37704.9609 |  | 0 | 0 | 37704.9609 | 10d | 0 | 0 | 0 | 37704.9609 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 37704.9609 | 10d | 0 | 0 | 0 | 37704.9609 | 0%
59 | v0 heating | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | heating engineer | 6912 | 11651 | 0 | 0 | 18563 |  | 0 | 0 | 18563 | 20d | 0 | 0 | 0 | 18563 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 18563 | 20d | 0 | 0 | 0 | 18563 | 0%
29 | v0 electricity | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 |  | 0 | 0 | 6400 | 25d | 0 | 0 | 0 | 6400 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 6400 | 25d | 0 | 0 | 0 | 6400 | 0%
35 | v0 floors | 2007-10-03 10:00 | 2007-10-31 10:00 | 20d | floor layer | 6649.6016 | 75000 | 0 | 0 | 81649.6016 |  | 0 | 0 | 81649.6016 | 20d | 0 | 0 | 0 | 81649.6016 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 81649.6016 | 20d | 0 | 0 | 0 | 81649.6016 | 0%
66 | construction leave | 2007-08-15 10:00 | 2007-08-29 10:00 | 10d |  |  | 0.01 |  |  | 0.01 | [9 empty] | 0% |  | 0 | 0 | [9 empty] | 0%
31 | construction leave | 2007-08-15 10:00 | 2007-08-29 10:00 | 10d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 10d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 0.01 | 10d | 0 | 0 | 0 | 0.01 | 0%
63 | level 1 | 2007-08-29 10:00 | 2007-10-24 10:00 | 40d |  |  | 226284.9844 |  |  | 262542.5938 | [9 empty] | 0% |  | 0 | 0 | [9 empty] | 0%
52 | v1 sanitary | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 |  | 0 | 0 | 7673 | 10d | 0 | 0 | 0 | 7673 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 7673 | 10d | 0 | 0 | 0 | 7673 | 0%
45 | v1 masonry | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 40.65 | 3252 | 37704.9609 |  | 0 | 0 | 37704.9609 | 10d | 0 | 0 | 0 | 37704.9609 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 37704.9609 | 10d | 0 | 0 | 0 | 37704.9609 | 0%
34 | v1 screed | 2007-08-29 10:00 | 2007-09-19 10:00 | 15d | screed layer[2,00 #3] | 0 | 106140 | 0 | 0 | 106140 |  | 0 | 0 | 106140 | 15d | 0 | 0 | 0 | 106140 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 106140 | 15d | 0 | 0 | 0 | 106140 | 0%
60 | v1 heating | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | heating engineer | 6912 | 11651 | 43.2 | 6912 | 25475 |  | 0 | 0 | 25475 | 20d | 0 | 0 | 0 | 25475 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 25475 | 20d | 0 | 0 | 0 | 25475 | 0%
51 | v1 electricity | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 |  | 0 | 0 | 6400 | 25d | 0 | 0 | 0 | 6400 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 6400 | 25d | 0 | 0 | 0 | 6400 | 0%
67 | v1 drying screed | 2007-09-19 10:00 | 2007-09-26 10:00 | 5d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 5d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 0.01 | 5d | 0 | 0 | 0 | 0.01 | 0%
57 | v1 flooring | 2007-09-26 10:00 | 2007-10-24 10:00 | 20d | floor layer | 6649.6016 | 72500 | 0 | 0 | 79149.6016 |  | 0 | 0 | 79149.6016 | 20d | 0 | 0 | 0 | 79149.6016 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 79149.6016 | 20d | 0 | 0 | 0 | 79149.6016 | 0%
64 | level 2 | 2007-08-29 10:00 | 2007-10-24 10:00 | 40d |  |  | 125260.9688 |  |  | 149562.5625 | [9 empty] | 0% |  | 0 | 0 | [9 empty] | 0%
53 | v2 sanitary | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 |  | 0 | 0 | 7673 | 10d | 0 | 0 | 0 | 7673 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 7673 | 10d | 0 | 0 | 0 | 7673 | 0%
55 | v2 masonry | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 0 | 0 | 34452.9609 |  | 0 | 0 | 34452.9609 | 10d | 0 | 0 | 0 | 34452.9609 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 34452.9609 | 10d | 0 | 0 | 0 | 34452.9609 | 0%
56 | v2 screed | 2007-08-29 10:00 | 2007-09-19 10:00 | 15d | screed layer | 0 | 46116 | 0 | 0 | 46116 |  | 0 | 0 | 46116 | 15d | 0 | 0 | 0 | 46116 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 46116 | 15d | 0 | 0 | 0 | 46116 | 0%
61 | v2 heating | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | electrician | 5120 | 11651 | 0 | 0 | 16771 |  | 0 | 0 | 16771 | 20d | 0 | 0 | 0 | 16771 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 16771 | 20d | 0 | 0 | 0 | 16771 | 0%
54 | v2 electricity | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 |  | 0 | 0 | 6400 | 25d | 0 | 0 | 0 | 6400 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 6400 | 25d | 0 | 0 | 0 | 6400 | 0%
68 | v2 drying screed | 2007-09-19 10:00 | 2007-09-26 10:00 | 5d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 5d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 0.01 | 5d | 0 | 0 | 0 | 0.01 | 0%
58 | v2 flooring | 2007-09-26 10:00 | 2007-10-24 10:00 | 20d | floor layer | 6649.6016 | 31500 | 0 | 0 | 38149.6016 |  | 0 | 0 | 38149.6016 | 20d | 0 | 0 | 0 | 38149.6016 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 38149.6016 | 20d | 0 | 0 | 0 | 38149.6016 | 0%
65 | completion | 2007-09-26 10:00 | 2007-12-26 10:00 | 65d |  |  | 478615.9062 |  |  | 518712.7188 | [9 empty] | 0% |  | 0 | 0 | [9 empty] | 0%
32 | stucco | 2007-09-26 10:00 | 2007-10-17 10:00 | 15d | plasterer[3,00 #4] | 14896.8008 | 8642 | 0 | 0 | 23538.8008 |  | 0 | 0 | 23538.8008 | 15d | 0 | 0 | 0 | 23538.8008 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 23538.8008 | 15d | 0 | 0 | 0 | 23538.8008 | 0%
36 | drywall | 2007-10-24 10:00 | 2007-11-28 10:00 | 25d |  | 0 | 48000 | 0 | 0 | 48000 |  | 0 | 0 | 48000 | 25d | 0 | 0 | 0 | 48000 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 48000 | 25d | 0 | 0 | 0 | 48000 | 0%
41 | kitchen and bar | 2007-10-31 10:00 | 2007-11-21 10:00 | 15d |  | 0 | 87000 | 0 | 0 | 87000 |  | 0 | 0 | 87000 | 15d | 0 | 0 | 0 | 87000 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 87000 | 15d | 0 | 0 | 0 | 87000 | 0%
37 | techniques | 2007-10-31 10:00 | 2007-11-21 10:00 | 15d |  | 0 | 2156.0601 | 0 | 0 | 2156.0601 |  | 0 | 0 | 2156.0601 | 15d | 0 | 0 | 0 | 2156.0601 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 2156.0601 | 15d | 0 | 0 | 0 | 2156.0601 | 0%
44 | stairs | 2007-11-21 10:00 | 2007-12-05 10:00 | 10d |  | 0 | 33000 | 0 | 0 | 33000 |  | 0 | 0 | 33000 | 10d | 0 | 0 | 0 | 33000 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 33000 | 10d | 0 | 0 | 0 | 33000 | 0%
42 | entrance doors | 2007-11-21 10:00 | 2007-12-05 10:00 | 10d |  | 0 | 16000 | 0 | 0 | 16000 |  | 0 | 0 | 16000 | 10d | 0 | 0 | 0 | 16000 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 16000 | 10d | 0 | 0 | 0 | 16000 | 0%
43 | elevator | 2007-11-21 10:00 | 2007-11-28 10:00 | 5d |  | 0 | 38817.8516 | 0 | 0 | 38817.8516 |  | 0 | 0 | 38817.8516 | 5d | 0 | 0 | 0 | 38817.8516 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 38817.8516 | 5d | 0 | 0 | 0 | 38817.8516 | 0%
38 | suspended ceiling | 2007-11-21 10:00 | 2007-11-28 10:00 | 5d |  | 0 | 32000 | 0 | 0 | 32000 |  | 0 | 0 | 32000 | 5d | 0 | 0 | 0 | 32000 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 32000 | 5d | 0 | 0 | 0 | 32000 | 0%
39 | painting | 2007-11-28 10:00 | 2007-12-19 10:00 | 15d | painter[4,00 #6] | 16800 | 83000 | 0 | 0 | 99800 |  | 0 | 0 | 99800 | 15d | 0 | 0 | 0 | 99800 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 99800 | 15d | 0 | 0 | 0 | 99800 | 0%
40 | furniture | 2007-12-19 10:00 | 2007-12-26 10:00 | 5d | joiner[5,00 #5] | 8400 | 130000 | 0 | 0 | 138400 |  | 0 | 0 | 138400 | 5d | 0 | 0 | 0 | 138400 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 138400 | 5d | 0 | 0 | 0 | 138400 | 0%

## TP5
| TP Status Date | 2007-07-02 08:00 |  | TP Name | Wind & waterproof
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [16 empty] | protrack
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Werkelijke Start | Werkelijke Duurtijd | PAC | PRC | Resterende Duurtijd | PAC Dev | PRC Dev | Werkelijke Kost | Resterende Kost | Percentage Compleet
0 | PROJECT CLAEYS-VERHELST | 2006-04-17 08:00 | 2007-12-26 10:00 | 442d 2h |  |  | 2700210.5 |  |  | 3027133.25 | [9 empty] | 59% |  | 1790091.375 | 1944324.875 | [9 empty] | 59%
46 | preparation | 2006-04-17 08:00 | 2006-12-08 17:00 | 170d |  |  | 216786.9844 |  |  | 253804.5938 | [9 empty] | 100% |  | 253804.5938 | 253804.5938 | [9 empty] | 100%
2 | building permit | 2006-04-17 08:00 | 2006-07-07 17:00 | 60d |  | 0 | 75 | 0 | 0 | 75 | 2006-04-17 08:00 | 100d | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 75 | 75 | 2006-04-17 08:00 | 100d | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100%
3 | hire contractor | 2006-07-10 08:00 | 2006-08-04 17:00 | 20d |  | 0 | 210000 | 0 | 0 | 210000 | 2006-09-04 08:00 | 30d | 210000 | 0 | 0 | 0 | 0 | 210000 | 0 | 100% | Finished | 210000 | 210000 | 2006-09-04 08:00 | 30d | 210000 | 0 | 0 | 0 | 0 | 210000 | 0 | 100%
4 | temporary offices | 2006-04-17 08:00 | 2006-05-12 17:00 | 20d |  | 0 | 3765.3101 | 0 | 0 | 3765.3101 | 2006-04-17 08:00 | 20d | 3765.3101 | 0 | 0 | 0 | 0 | 3765.3101 | 0 | 100% | Finished | 3765.3101 | 3765.3101 | 2006-04-17 08:00 | 20d | 3765.3101 | 0 | 0 | 0 | 0 | 3765.3101 | 0 | 100%
5 | temporary facilities | 2006-04-17 08:00 | 2006-07-07 17:00 | 60d |  | 0 | 1876.54 | 0 | 0 | 1876.54 | 2006-04-17 08:00 | 60d | 1876.54 | 0 | 0 | 0 | 0 | 1876.54 | 0 | 100% | Finished | 1876.54 | 1876.54 | 2006-04-17 08:00 | 60d | 1876.54 | 0 | 0 | 0 | 0 | 1876.54 | 0 | 100%
16 | preparation contractor | 2006-08-07 08:00 | 2006-10-27 17:00 | 60d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2006-09-04 08:00 | 60d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 2006-09-04 08:00 | 60d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100%
6 | demolition | 2006-10-30 08:00 | 2006-12-08 17:00 | 30d | team subcontractor[4,00 #8] | 37017.6016 | 1070.11 | 0 | 0 | 38087.7109 | 2006-11-27 08:00 | 54d | 67701.7891 | 0 | 0 | 0 | 0 | 67701.7891 | 0 | 100% | Finished | 38087.7109 | 38087.7109 | 2006-11-27 08:00 | 54d | 67701.7891 | 0 | 0 | 0 | 0 | 67701.7891 | 0 | 100%
47 | foundation | 2006-12-11 08:00 | 2007-02-01 17:00 | 39d |  |  | 362567.875 |  |  | 401436.375 | [9 empty] | 100% |  | 401436.375 | 401436.375 | [9 empty] | 100%
17 | excavation | 2006-12-11 08:00 | 2006-12-28 17:00 | 14d | team subcontractor | 4318.7207 | 26000 | 0 | 0 | 30318.7207 | 2007-02-08 08:00 | 10d | 29084.8008 | 0 | 0 | 0 | 0 | 29084.8008 | 0 | 100% | Finished | 30318.7207 | 30318.7207 | 2007-02-08 08:00 | 10d | 29084.8008 | 0 | 0 | 0 | 0 | 29084.8008 | 0 | 100%
69 | soil analyses | 2006-12-11 08:00 | 2006-12-12 17:00 | 2d | team subcontractor | 616.96 | 2000 | 0 | 0 | 2616.96 | 2007-02-08 08:00 | 12d | 5701.7603 | 0 | 0 | 0 | 0 | 5701.7603 | 0 | 100% | Finished | 2616.96 | 2616.96 | 2007-02-08 08:00 | 12d | 5701.7603 | 0 | 0 | 0 | 0 | 5701.7603 | 0 | 100%
18 | foundation beam | 2006-12-29 08:00 | 2007-02-01 17:00 | 25d | team subcontractor[3,00 #8] | 23136 | 98523.7266 | 0 | 0 | 121659.7266 | 2007-02-28 08:00 | 22d | 118883.4062 | 0 | 0 | 0 | 0 | 118883.4062 | 0 | 100% | Finished | 121659.7266 | 121659.7266 | 2007-02-28 08:00 | 22d | 118883.4062 | 0 | 0 | 0 | 0 | 118883.4062 | 0 | 100%
21 | placing sewerage | 2006-12-29 08:00 | 2007-01-11 17:00 | 10d | team subcontractor[3,00 #8] | 9254.4004 | 1224.73 | 0 | 0 | 10479.1309 | 2007-02-28 08:00 | 12d | 12330.0098 | 0 | 0 | 0 | 0 | 12330.0098 | 0 | 100% | Finished | 10479.1309 | 10479.1309 | 2007-02-28 08:00 | 12d | 12330.0098 | 0 | 0 | 0 | 0 | 12330.0098 | 0 | 100%
23 | foundation plate | 2007-01-12 08:00 | 2007-01-12 17:00 | 1d | team subcontractor[5,00 #8] | 1542.4062 | 234819.4375 | 0 | 0 | 236361.8438 | 2007-03-16 08:00 | 1d | 236361.8438 | 0 | 0 | 0 | 0 | 236361.8438 | 0 | 100% | Finished | 236361.8438 | 236361.8438 | 2007-03-16 08:00 | 1d | 236361.8438 | 0 | 0 | 0 | 0 | 236361.8438 | 0 | 100%
48 | shell | 2007-02-02 08:00 | 2007-04-26 17:00 | 60d |  |  | 472804.4375 |  |  | 542212.4375 | [9 empty] | 100% |  | 542212.4375 | 542212.4375 | [9 empty] | 100%
19 | steelframe I | 2007-02-02 08:00 | 2007-03-01 17:00 | 20d | team subcontractor[4,00 #8] | 24678.3984 | 118992.5078 | 0 | 0 | 143670.9062 | 2007-04-02 08:00 | 15d | 137501.3125 | 0 | 0 | 0 | 0 | 137501.3125 | 0 | 100% | Finished | 143670.9062 | 143670.9062 | 2007-04-02 08:00 | 15d | 137501.3125 | 0 | 0 | 0 | 0 | 137501.3125 | 0 | 100%
20 | concrete vaults I | 2007-03-02 08:00 | 2007-03-15 17:00 | 10d | team subcontractor[4,00 #8] | 12339.2031 | 117409.7188 | 0 | 0 | 129748.9219 | 2007-04-23 08:00 | 5d | 123579.3203 | 0 | 0 | 0 | 0 | 123579.3203 | 0 | 100% | Finished | 129748.9219 | 129748.9219 | 2007-04-23 08:00 | 5d | 123579.3203 | 0 | 0 | 0 | 0 | 123579.3203 | 0 | 100%
22 | steelframe II | 2007-03-16 08:00 | 2007-04-05 17:00 | 15d | team subcontractor[3,00 #8] | 13881.6016 | 118992.5078 | 0 | 0 | 132874.1094 | 2007-04-30 08:00 | 15d | 132874.1094 | 0 | 0 | 0 | 0 | 132874.1094 | 0 | 100% | Finished | 132874.1094 | 132874.1094 | 2007-04-30 08:00 | 15d | 132874.1094 | 0 | 0 | 0 | 0 | 132874.1094 | 0 | 100%
24 | concrete vaults II | 2007-04-06 08:00 | 2007-04-26 17:00 | 15d | team subcontractor[4,00 #8] | 18508.7969 | 117409.7188 | 0 | 0 | 135918.5156 | 2007-05-21 08:00 | 10d | 129748.9219 | 0 | 0 | 0 | 0 | 129748.9219 | 0 | 100% | Finished | 135918.5156 | 135918.5156 | 2007-05-21 08:00 | 10d | 129748.9219 | 0 | 0 | 0 | 0 | 129748.9219 | 0 | 100%
50 | wind and water proof | 2007-04-27 08:00 | 2007-06-07 17:00 | 30d |  |  | 560844.1875 |  |  | 597047.375 | [9 empty] | 99% |  | 592637.8449 | 597047.375 | [9 empty] | 99%
25 | facades | 2007-04-27 08:00 | 2007-05-24 17:00 | 20d | team subcontractor[2,00 #8] | 12339.1875 | 339314 | 0 | 0 | 351653.1875 | 2007-06-04 08:00 | 20d | 351653.1875 | 4935.6802 | 8d | 0 | 0 | 351653.1875 | 4935.6802 | 71% | Finished | 348127.7054 | 351653.1875 | 2007-06-04 08:00 | 20d | 351653.1875 | 4935.6802 | 8d | 0 | 0 | 351653.1875 | 4935.6802 | 71%
26 | outside windows | 2007-05-25 08:00 | 2007-06-07 17:00 | 10d | carpenter[3,00 #3] | 9120 | 150750.5938 | 0 | 0 | 159870.5938 | 2007-07-02 08:00 | 92d | 234654.5938 | 9006 | 9d 7u | 0 | 0 | 234654.5938 | 9006 | 90% | Not Started | 158986.5693 | 159870.5938 | 2007-07-02 08:00 | 92d | 234654.5938 | 9006 | 9d 7u | 0 | 0 | 234654.5938 | 9006 | 90%
49 | roof | 2007-04-27 08:00 | 2007-05-10 17:00 | 10d | roofer[4,00 #4] | 11520 | 70779.5703 | 40.3 | 3224 | 85523.5703 | 2007-06-04 08:00 | 10d | 85523.5703 | 0 | 0 | 0 | 0 | 85523.5703 | 0 | 100% | Finished | 85523.5703 | 85523.5703 | 2007-06-04 08:00 | 10d | 85523.5703 | 0 | 0 | 0 | 0 | 85523.5703 | 0 | 100%
62 | warehouse | 2007-06-08 08:00 | 2007-10-31 10:00 | 103d 2h |  |  | 257044.9688 |  |  | 301814.5625 | [9 empty] | 0% |  | 0 | 149824 | [9 empty] | 0%
28 | v0 concrete | 2007-06-08 08:00 | 2007-06-21 17:00 | 10d | team subcontractor[5,00 #8] | 15424 | 134400 | 0 | 0 | 149824 |  | 0 | 0 | 149824 | 10d | 0 | 0 | 0 | 149824 | 0% | Not Started | 0 | 149824 |  | 0 | 0 | 149824 | 10d | 0 | 0 | 0 | 149824 | 0%
30 | v0 sanitary | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 |  | 0 | 0 | 7673 | 10d | 0 | 0 | 0 | 7673 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 7673 | 10d | 0 | 0 | 0 | 7673 | 0%
27 | v0 masonry | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 40.65 | 3252 | 37704.9609 |  | 0 | 0 | 37704.9609 | 10d | 0 | 0 | 0 | 37704.9609 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 37704.9609 | 10d | 0 | 0 | 0 | 37704.9609 | 0%
59 | v0 heating | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | heating engineer | 6912 | 11651 | 0 | 0 | 18563 |  | 0 | 0 | 18563 | 20d | 0 | 0 | 0 | 18563 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 18563 | 20d | 0 | 0 | 0 | 18563 | 0%
29 | v0 electricity | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 |  | 0 | 0 | 6400 | 25d | 0 | 0 | 0 | 6400 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 6400 | 25d | 0 | 0 | 0 | 6400 | 0%
35 | v0 floors | 2007-10-03 10:00 | 2007-10-31 10:00 | 20d | floor layer | 6649.6016 | 75000 | 0 | 0 | 81649.6016 |  | 0 | 0 | 81649.6016 | 20d | 0 | 0 | 0 | 81649.6016 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 81649.6016 | 20d | 0 | 0 | 0 | 81649.6016 | 0%
66 | construction leave | 2007-08-15 10:00 | 2007-08-29 10:00 | 10d |  |  | 0.01 |  |  | 0.01 | [9 empty] | 0% |  | 0 | 0 | [9 empty] | 0%
31 | construction leave | 2007-08-15 10:00 | 2007-08-29 10:00 | 10d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 10d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 0.01 | 10d | 0 | 0 | 0 | 0.01 | 0%
63 | level 1 | 2007-08-29 10:00 | 2007-10-24 10:00 | 40d |  |  | 226284.9844 |  |  | 262542.5938 | [9 empty] | 0% |  | 0 | 0 | [9 empty] | 0%
52 | v1 sanitary | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 |  | 0 | 0 | 7673 | 10d | 0 | 0 | 0 | 7673 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 7673 | 10d | 0 | 0 | 0 | 7673 | 0%
45 | v1 masonry | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 40.65 | 3252 | 37704.9609 |  | 0 | 0 | 37704.9609 | 10d | 0 | 0 | 0 | 37704.9609 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 37704.9609 | 10d | 0 | 0 | 0 | 37704.9609 | 0%
34 | v1 screed | 2007-08-29 10:00 | 2007-09-19 10:00 | 15d | screed layer[2,00 #3] | 0 | 106140 | 0 | 0 | 106140 |  | 0 | 0 | 106140 | 15d | 0 | 0 | 0 | 106140 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 106140 | 15d | 0 | 0 | 0 | 106140 | 0%
60 | v1 heating | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | heating engineer | 6912 | 11651 | 43.2 | 6912 | 25475 |  | 0 | 0 | 25475 | 20d | 0 | 0 | 0 | 25475 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 25475 | 20d | 0 | 0 | 0 | 25475 | 0%
51 | v1 electricity | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 |  | 0 | 0 | 6400 | 25d | 0 | 0 | 0 | 6400 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 6400 | 25d | 0 | 0 | 0 | 6400 | 0%
67 | v1 drying screed | 2007-09-19 10:00 | 2007-09-26 10:00 | 5d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 5d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 0.01 | 5d | 0 | 0 | 0 | 0.01 | 0%
57 | v1 flooring | 2007-09-26 10:00 | 2007-10-24 10:00 | 20d | floor layer | 6649.6016 | 72500 | 0 | 0 | 79149.6016 |  | 0 | 0 | 79149.6016 | 20d | 0 | 0 | 0 | 79149.6016 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 79149.6016 | 20d | 0 | 0 | 0 | 79149.6016 | 0%
64 | level 2 | 2007-08-29 10:00 | 2007-10-24 10:00 | 40d |  |  | 125260.9688 |  |  | 149562.5625 | [9 empty] | 0% |  | 0 | 0 | [9 empty] | 0%
53 | v2 sanitary | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 |  | 0 | 0 | 7673 | 10d | 0 | 0 | 0 | 7673 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 7673 | 10d | 0 | 0 | 0 | 7673 | 0%
55 | v2 masonry | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 0 | 0 | 34452.9609 |  | 0 | 0 | 34452.9609 | 10d | 0 | 0 | 0 | 34452.9609 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 34452.9609 | 10d | 0 | 0 | 0 | 34452.9609 | 0%
56 | v2 screed | 2007-08-29 10:00 | 2007-09-19 10:00 | 15d | screed layer | 0 | 46116 | 0 | 0 | 46116 |  | 0 | 0 | 46116 | 15d | 0 | 0 | 0 | 46116 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 46116 | 15d | 0 | 0 | 0 | 46116 | 0%
61 | v2 heating | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | electrician | 5120 | 11651 | 0 | 0 | 16771 |  | 0 | 0 | 16771 | 20d | 0 | 0 | 0 | 16771 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 16771 | 20d | 0 | 0 | 0 | 16771 | 0%
54 | v2 electricity | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 |  | 0 | 0 | 6400 | 25d | 0 | 0 | 0 | 6400 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 6400 | 25d | 0 | 0 | 0 | 6400 | 0%
68 | v2 drying screed | 2007-09-19 10:00 | 2007-09-26 10:00 | 5d |  | 0 | 0.01 | 0 | 0 | 0.01 |  | 0 | 0 | 0.01 | 5d | 0 | 0 | 0 | 0.01 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 0.01 | 5d | 0 | 0 | 0 | 0.01 | 0%
58 | v2 flooring | 2007-09-26 10:00 | 2007-10-24 10:00 | 20d | floor layer | 6649.6016 | 31500 | 0 | 0 | 38149.6016 |  | 0 | 0 | 38149.6016 | 20d | 0 | 0 | 0 | 38149.6016 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 38149.6016 | 20d | 0 | 0 | 0 | 38149.6016 | 0%
65 | completion | 2007-09-26 10:00 | 2007-12-26 10:00 | 65d |  |  | 478615.9062 |  |  | 518712.7188 | [9 empty] | 0% |  | 0 | 0 | [9 empty] | 0%
32 | stucco | 2007-09-26 10:00 | 2007-10-17 10:00 | 15d | plasterer[3,00 #4] | 14896.8008 | 8642 | 0 | 0 | 23538.8008 |  | 0 | 0 | 23538.8008 | 15d | 0 | 0 | 0 | 23538.8008 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 23538.8008 | 15d | 0 | 0 | 0 | 23538.8008 | 0%
36 | drywall | 2007-10-24 10:00 | 2007-11-28 10:00 | 25d |  | 0 | 48000 | 0 | 0 | 48000 |  | 0 | 0 | 48000 | 25d | 0 | 0 | 0 | 48000 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 48000 | 25d | 0 | 0 | 0 | 48000 | 0%
41 | kitchen and bar | 2007-10-31 10:00 | 2007-11-21 10:00 | 15d |  | 0 | 87000 | 0 | 0 | 87000 |  | 0 | 0 | 87000 | 15d | 0 | 0 | 0 | 87000 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 87000 | 15d | 0 | 0 | 0 | 87000 | 0%
37 | techniques | 2007-10-31 10:00 | 2007-11-21 10:00 | 15d |  | 0 | 2156.0601 | 0 | 0 | 2156.0601 |  | 0 | 0 | 2156.0601 | 15d | 0 | 0 | 0 | 2156.0601 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 2156.0601 | 15d | 0 | 0 | 0 | 2156.0601 | 0%
44 | stairs | 2007-11-21 10:00 | 2007-12-05 10:00 | 10d |  | 0 | 33000 | 0 | 0 | 33000 |  | 0 | 0 | 33000 | 10d | 0 | 0 | 0 | 33000 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 33000 | 10d | 0 | 0 | 0 | 33000 | 0%
42 | entrance doors | 2007-11-21 10:00 | 2007-12-05 10:00 | 10d |  | 0 | 16000 | 0 | 0 | 16000 |  | 0 | 0 | 16000 | 10d | 0 | 0 | 0 | 16000 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 16000 | 10d | 0 | 0 | 0 | 16000 | 0%
43 | elevator | 2007-11-21 10:00 | 2007-11-28 10:00 | 5d |  | 0 | 38817.8516 | 0 | 0 | 38817.8516 |  | 0 | 0 | 38817.8516 | 5d | 0 | 0 | 0 | 38817.8516 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 38817.8516 | 5d | 0 | 0 | 0 | 38817.8516 | 0%
38 | suspended ceiling | 2007-11-21 10:00 | 2007-11-28 10:00 | 5d |  | 0 | 32000 | 0 | 0 | 32000 |  | 0 | 0 | 32000 | 5d | 0 | 0 | 0 | 32000 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 32000 | 5d | 0 | 0 | 0 | 32000 | 0%
39 | painting | 2007-11-28 10:00 | 2007-12-19 10:00 | 15d | painter[4,00 #6] | 16800 | 83000 | 0 | 0 | 99800 |  | 0 | 0 | 99800 | 15d | 0 | 0 | 0 | 99800 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 99800 | 15d | 0 | 0 | 0 | 99800 | 0%
40 | furniture | 2007-12-19 10:00 | 2007-12-26 10:00 | 5d | joiner[5,00 #5] | 8400 | 130000 | 0 | 0 | 138400 |  | 0 | 0 | 138400 | 5d | 0 | 0 | 0 | 138400 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 138400 | 5d | 0 | 0 | 0 | 138400 | 0%

## TP6
| TP Status Date | 2007-10-24 08:00 |  | TP Name | WH, L1, L2
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [16 empty] | protrack
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Werkelijke Start | Werkelijke Duurtijd | PAC | PRC | Resterende Duurtijd | PAC Dev | PRC Dev | Werkelijke Kost | Resterende Kost | Percentage Compleet
0 | PROJECT CLAEYS-VERHELST | 2006-04-17 08:00 | 2007-12-26 10:00 | 442d 2h |  |  | 2700210.5 |  |  | 3027133.25 | [9 empty] | 83% |  | 2506206.5 | 2530047.75 | [9 empty] | 83%
46 | preparation | 2006-04-17 08:00 | 2006-12-08 17:00 | 170d |  |  | 216786.9844 |  |  | 253804.5938 | [9 empty] | 100% |  | 253804.5938 | 253804.5938 | [9 empty] | 100%
2 | building permit | 2006-04-17 08:00 | 2006-07-07 17:00 | 60d |  | 0 | 75 | 0 | 0 | 75 | 2006-04-17 08:00 | 100d | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 75 | 75 | 2006-04-17 08:00 | 100d | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100%
3 | hire contractor | 2006-07-10 08:00 | 2006-08-04 17:00 | 20d |  | 0 | 210000 | 0 | 0 | 210000 | 2006-09-04 08:00 | 30d | 210000 | 0 | 0 | 0 | 0 | 210000 | 0 | 100% | Finished | 210000 | 210000 | 2006-09-04 08:00 | 30d | 210000 | 0 | 0 | 0 | 0 | 210000 | 0 | 100%
4 | temporary offices | 2006-04-17 08:00 | 2006-05-12 17:00 | 20d |  | 0 | 3765.3101 | 0 | 0 | 3765.3101 | 2006-04-17 08:00 | 20d | 3765.3101 | 0 | 0 | 0 | 0 | 3765.3101 | 0 | 100% | Finished | 3765.3101 | 3765.3101 | 2006-04-17 08:00 | 20d | 3765.3101 | 0 | 0 | 0 | 0 | 3765.3101 | 0 | 100%
5 | temporary facilities | 2006-04-17 08:00 | 2006-07-07 17:00 | 60d |  | 0 | 1876.54 | 0 | 0 | 1876.54 | 2006-04-17 08:00 | 60d | 1876.54 | 0 | 0 | 0 | 0 | 1876.54 | 0 | 100% | Finished | 1876.54 | 1876.54 | 2006-04-17 08:00 | 60d | 1876.54 | 0 | 0 | 0 | 0 | 1876.54 | 0 | 100%
16 | preparation contractor | 2006-08-07 08:00 | 2006-10-27 17:00 | 60d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2006-09-04 08:00 | 60d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 2006-09-04 08:00 | 60d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100%
6 | demolition | 2006-10-30 08:00 | 2006-12-08 17:00 | 30d | team subcontractor[4,00 #8] | 37017.6016 | 1070.11 | 0 | 0 | 38087.7109 | 2006-11-27 08:00 | 54d | 67701.7891 | 0 | 0 | 0 | 0 | 67701.7891 | 0 | 100% | Finished | 38087.7109 | 38087.7109 | 2006-11-27 08:00 | 54d | 67701.7891 | 0 | 0 | 0 | 0 | 67701.7891 | 0 | 100%
47 | foundation | 2006-12-11 08:00 | 2007-02-01 17:00 | 39d |  |  | 362567.875 |  |  | 401436.375 | [9 empty] | 100% |  | 401436.375 | 401436.375 | [9 empty] | 100%
17 | excavation | 2006-12-11 08:00 | 2006-12-28 17:00 | 14d | team subcontractor | 4318.7207 | 26000 | 0 | 0 | 30318.7207 | 2007-02-08 08:00 | 10d | 29084.8008 | 0 | 0 | 0 | 0 | 29084.8008 | 0 | 100% | Finished | 30318.7207 | 30318.7207 | 2007-02-08 08:00 | 10d | 29084.8008 | 0 | 0 | 0 | 0 | 29084.8008 | 0 | 100%
69 | soil analyses | 2006-12-11 08:00 | 2006-12-12 17:00 | 2d | team subcontractor | 616.96 | 2000 | 0 | 0 | 2616.96 | 2007-02-08 08:00 | 12d | 5701.7603 | 0 | 0 | 0 | 0 | 5701.7603 | 0 | 100% | Finished | 2616.96 | 2616.96 | 2007-02-08 08:00 | 12d | 5701.7603 | 0 | 0 | 0 | 0 | 5701.7603 | 0 | 100%
18 | foundation beam | 2006-12-29 08:00 | 2007-02-01 17:00 | 25d | team subcontractor[3,00 #8] | 23136 | 98523.7266 | 0 | 0 | 121659.7266 | 2007-02-28 08:00 | 22d | 118883.4062 | 0 | 0 | 0 | 0 | 118883.4062 | 0 | 100% | Finished | 121659.7266 | 121659.7266 | 2007-02-28 08:00 | 22d | 118883.4062 | 0 | 0 | 0 | 0 | 118883.4062 | 0 | 100%
21 | placing sewerage | 2006-12-29 08:00 | 2007-01-11 17:00 | 10d | team subcontractor[3,00 #8] | 9254.4004 | 1224.73 | 0 | 0 | 10479.1309 | 2007-02-28 08:00 | 12d | 12330.0098 | 0 | 0 | 0 | 0 | 12330.0098 | 0 | 100% | Finished | 10479.1309 | 10479.1309 | 2007-02-28 08:00 | 12d | 12330.0098 | 0 | 0 | 0 | 0 | 12330.0098 | 0 | 100%
23 | foundation plate | 2007-01-12 08:00 | 2007-01-12 17:00 | 1d | team subcontractor[5,00 #8] | 1542.4062 | 234819.4375 | 0 | 0 | 236361.8438 | 2007-03-16 08:00 | 1d | 236361.8438 | 0 | 0 | 0 | 0 | 236361.8438 | 0 | 100% | Finished | 236361.8438 | 236361.8438 | 2007-03-16 08:00 | 1d | 236361.8438 | 0 | 0 | 0 | 0 | 236361.8438 | 0 | 100%
48 | shell | 2007-02-02 08:00 | 2007-04-26 17:00 | 60d |  |  | 472804.4375 |  |  | 542212.4375 | [9 empty] | 100% |  | 542212.4375 | 542212.4375 | [9 empty] | 100%
19 | steelframe I | 2007-02-02 08:00 | 2007-03-01 17:00 | 20d | team subcontractor[4,00 #8] | 24678.3984 | 118992.5078 | 0 | 0 | 143670.9062 | 2007-04-02 08:00 | 15d | 137501.3125 | 0 | 0 | 0 | 0 | 137501.3125 | 0 | 100% | Finished | 143670.9062 | 143670.9062 | 2007-04-02 08:00 | 15d | 137501.3125 | 0 | 0 | 0 | 0 | 137501.3125 | 0 | 100%
20 | concrete vaults I | 2007-03-02 08:00 | 2007-03-15 17:00 | 10d | team subcontractor[4,00 #8] | 12339.2031 | 117409.7188 | 0 | 0 | 129748.9219 | 2007-04-23 08:00 | 5d | 123579.3203 | 0 | 0 | 0 | 0 | 123579.3203 | 0 | 100% | Finished | 129748.9219 | 129748.9219 | 2007-04-23 08:00 | 5d | 123579.3203 | 0 | 0 | 0 | 0 | 123579.3203 | 0 | 100%
22 | steelframe II | 2007-03-16 08:00 | 2007-04-05 17:00 | 15d | team subcontractor[3,00 #8] | 13881.6016 | 118992.5078 | 0 | 0 | 132874.1094 | 2007-04-30 08:00 | 15d | 132874.1094 | 0 | 0 | 0 | 0 | 132874.1094 | 0 | 100% | Finished | 132874.1094 | 132874.1094 | 2007-04-30 08:00 | 15d | 132874.1094 | 0 | 0 | 0 | 0 | 132874.1094 | 0 | 100%
24 | concrete vaults II | 2007-04-06 08:00 | 2007-04-26 17:00 | 15d | team subcontractor[4,00 #8] | 18508.7969 | 117409.7188 | 0 | 0 | 135918.5156 | 2007-05-21 08:00 | 10d | 129748.9219 | 0 | 0 | 0 | 0 | 129748.9219 | 0 | 100% | Finished | 135918.5156 | 135918.5156 | 2007-05-21 08:00 | 10d | 129748.9219 | 0 | 0 | 0 | 0 | 129748.9219 | 0 | 100%
50 | wind and water proof | 2007-04-27 08:00 | 2007-06-07 17:00 | 30d |  |  | 560844.1875 |  |  | 597047.375 | [9 empty] | 100% |  | 596163.3125 | 597047.375 | [9 empty] | 100%
25 | facades | 2007-04-27 08:00 | 2007-05-24 17:00 | 20d | team subcontractor[2,00 #8] | 12339.1875 | 339314 | 0 | 0 | 351653.1875 | 2007-06-04 08:00 | 20d | 351653.1875 | 0 | 0 | 0 | 0 | 351653.1875 | 0 | 100% | Finished | 351653.1875 | 351653.1875 | 2007-06-04 08:00 | 20d | 351653.1875 | 0 | 0 | 0 | 0 | 351653.1875 | 0 | 100%
26 | outside windows | 2007-05-25 08:00 | 2007-06-07 17:00 | 10d | carpenter[3,00 #3] | 9120 | 150750.5938 | 0 | 0 | 159870.5938 | 2007-07-02 08:00 | 92d | 234654.5938 | 9006 | 9d 7u | 0 | 0 | 234654.5938 | 9006 | 90% | Started | 158986.5625 | 159870.5938 | 2007-07-02 08:00 | 92d | 234654.5938 | 9006 | 9d 7u | 0 | 0 | 234654.5938 | 9006 | 90%
49 | roof | 2007-04-27 08:00 | 2007-05-10 17:00 | 10d | roofer[4,00 #4] | 11520 | 70779.5703 | 40.3 | 3224 | 85523.5703 | 2007-06-04 08:00 | 10d | 85523.5703 | 0 | 0 | 0 | 0 | 85523.5703 | 0 | 100% | Finished | 85523.5703 | 85523.5703 | 2007-06-04 08:00 | 10d | 85523.5703 | 0 | 0 | 0 | 0 | 85523.5703 | 0 | 100%
62 | warehouse | 2007-06-08 08:00 | 2007-10-31 10:00 | 103d 2h |  |  | 257044.9688 |  |  | 301814.5625 | [9 empty] | 100% |  | 301814.5625 | 300069.0625 | [9 empty] | 100%
28 | v0 concrete | 2007-06-08 08:00 | 2007-06-21 17:00 | 10d | team subcontractor[5,00 #8] | 15424 | 134400 | 0 | 0 | 149824 | 2007-07-25 08:00 | 5d | 142112 | 0 | 0 | 0 | 0 | 142112 | 0 | 100% | Finished | 149824 | 149824 | 2007-07-25 08:00 | 5d | 142112 | 0 | 0 | 0 | 0 | 142112 | 0 | 100%
30 | v0 sanitary | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 | 2007-08-29 08:00 | 10d | 7673 | 0 | 0 | 0 | 0 | 7673 | 0 | 100% | Finished | 7673 | 7673 | 2007-08-29 08:00 | 10d | 7673 | 0 | 0 | 0 | 0 | 7673 | 0 | 100%
27 | v0 masonry | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 40.65 | 3252 | 37704.9609 | 2007-08-29 08:00 | 10d | 37704.9609 | 0 | 0 | 0 | 0 | 37704.9609 | 0 | 100% | Finished | 37704.9609 | 37704.9609 | 2007-08-29 08:00 | 10d | 37704.9609 | 0 | 0 | 0 | 0 | 37704.9609 | 0 | 100%
59 | v0 heating | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | heating engineer | 6912 | 11651 | 0 | 0 | 18563 | 2007-08-29 08:00 | 20d | 18563 | 0 | 0 | 0 | 0 | 18563 | 0 | 100% | Finished | 18563 | 18563 | 2007-08-29 08:00 | 20d | 18563 | 0 | 0 | 0 | 0 | 18563 | 0 | 100%
29 | v0 electricity | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 | 2007-08-02 08:00 | 15d | 3840 | 0 | 0 | 0 | 0 | 3840 | 0 | 100% | Finished | 6400 | 6400 | 2007-08-02 08:00 | 15d | 3840 | 0 | 0 | 0 | 0 | 3840 | 0 | 100%
35 | v0 floors | 2007-10-03 10:00 | 2007-10-31 10:00 | 20d | floor layer | 6649.6016 | 75000 | 0 | 0 | 81649.6016 | 2007-09-26 08:00 | 20d | 81649.6016 | 0 | 0 | 0 | 0 | 81649.6016 | 0 | 100% | Finished | 81649.6016 | 79904.0781 | 2007-09-26 08:00 | 20d | 81649.6016 | 0 | 0 | 0 | 0 | 81649.6016 | 0 | 100%
66 | construction leave | 2007-08-15 10:00 | 2007-08-29 10:00 | 10d |  |  | 0.01 |  |  | 0.01 | [9 empty] | 100% |  | 0.01 | 0.01 | [9 empty] | 100%
31 | construction leave | 2007-08-15 10:00 | 2007-08-29 10:00 | 10d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2007-08-08 08:00 | 10d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Started | 0.01 | 0.01 | 2007-08-08 08:00 | 10d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100%
63 | level 1 | 2007-08-29 10:00 | 2007-10-24 10:00 | 40d |  |  | 226284.9844 |  |  | 262542.5938 | [9 empty] | 99% |  | 261212.6562 | 262459.4688 | [9 empty] | 99%
52 | v1 sanitary | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 | 2007-08-29 08:00 | 10d | 7673 | 0 | 0 | 0 | 0 | 7673 | 0 | 100% | Finished | 7673 | 7673 | 2007-08-29 08:00 | 10d | 7673 | 0 | 0 | 0 | 0 | 7673 | 0 | 100%
45 | v1 masonry | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 40.65 | 3252 | 37704.9609 | 2007-08-29 08:00 | 10d | 37704.9609 | 0 | 0 | 0 | 0 | 37704.9609 | 0 | 100% | Finished | 37704.9609 | 37704.9609 | 2007-08-29 08:00 | 10d | 37704.9609 | 0 | 0 | 0 | 0 | 37704.9609 | 0 | 100%
34 | v1 screed | 2007-08-29 10:00 | 2007-09-19 10:00 | 15d | screed layer[2,00 #3] | 0 | 106140 | 0 | 0 | 106140 | 2007-08-29 08:00 | 15d | 106140 | 0 | 0 | 0 | 0 | 106140 | 0 | 100% | Finished | 106140 | 106140 | 2007-08-29 08:00 | 15d | 106140 | 0 | 0 | 0 | 0 | 106140 | 0 | 100%
60 | v1 heating | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | heating engineer | 6912 | 11651 | 43.2 | 6912 | 25475 | 2007-08-29 08:00 | 20d | 25475 | 0 | 0 | 0 | 0 | 25475 | 0 | 100% | Finished | 25475 | 25475 | 2007-08-29 08:00 | 20d | 25475 | 0 | 0 | 0 | 0 | 25475 | 0 | 100%
51 | v1 electricity | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 | 2007-08-29 08:00 | 25d | 6400 | 0 | 0 | 0 | 0 | 6400 | 0 | 100% | Finished | 6400 | 6400 | 2007-08-29 08:00 | 25d | 6400 | 0 | 0 | 0 | 0 | 6400 | 0 | 100%
67 | v1 drying screed | 2007-09-19 10:00 | 2007-09-26 10:00 | 5d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2007-09-19 08:00 | 5d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 2007-09-19 08:00 | 5d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100%
57 | v1 flooring | 2007-09-26 10:00 | 2007-10-24 10:00 | 20d | floor layer | 6649.6016 | 72500 | 0 | 0 | 79149.6016 | 2007-10-03 08:00 | 20d | 79149.6016 | 1662.4 | 5d | 0 | 0 | 79149.6016 | 1662.4 | 80% | Started | 77819.6797 | 79066.4766 | 2007-10-03 08:00 | 20d | 79149.6016 | 1662.4 | 5d | 0 | 0 | 79149.6016 | 1662.4 | 80%
64 | level 2 | 2007-08-29 10:00 | 2007-10-24 10:00 | 40d |  |  | 125260.9688 |  |  | 149562.5625 | [9 empty] | 100% |  | 149562.5625 | 149479.4531 | [9 empty] | 100%
53 | v2 sanitary | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 | 2007-08-29 08:00 | 10d | 7673 | 0 | 0 | 0 | 0 | 7673 | 0 | 100% | Finished | 7673 | 7673 | 2007-08-29 08:00 | 10d | 7673 | 0 | 0 | 0 | 0 | 7673 | 0 | 100%
55 | v2 masonry | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 0 | 0 | 34452.9609 | 2007-08-29 08:00 | 10d | 34452.9609 | 0 | 0 | 0 | 0 | 34452.9609 | 0 | 100% | Finished | 34452.9609 | 34452.9609 | 2007-08-29 08:00 | 10d | 34452.9609 | 0 | 0 | 0 | 0 | 34452.9609 | 0 | 100%
56 | v2 screed | 2007-08-29 10:00 | 2007-09-19 10:00 | 15d | screed layer | 0 | 46116 | 0 | 0 | 46116 | 2007-08-29 08:00 | 15d | 46116 | 0 | 0 | 0 | 0 | 46116 | 0 | 100% | Finished | 46116 | 46116 | 2007-08-29 08:00 | 15d | 46116 | 0 | 0 | 0 | 0 | 46116 | 0 | 100%
61 | v2 heating | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | electrician | 5120 | 11651 | 0 | 0 | 16771 | 2007-08-29 08:00 | 20d | 16771 | 0 | 0 | 0 | 0 | 16771 | 0 | 100% | Finished | 16771 | 16771 | 2007-08-29 08:00 | 20d | 16771 | 0 | 0 | 0 | 0 | 16771 | 0 | 100%
54 | v2 electricity | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 | 2007-08-29 08:00 | 20d | 5120 | 0 | 0 | 0 | 0 | 5120 | 0 | 100% | Finished | 6400 | 6400 | 2007-08-29 08:00 | 20d | 5120 | 0 | 0 | 0 | 0 | 5120 | 0 | 100%
68 | v2 drying screed | 2007-09-19 10:00 | 2007-09-26 10:00 | 5d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2007-09-19 08:00 | 5d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 2007-09-19 08:00 | 5d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100%
58 | v2 flooring | 2007-09-26 10:00 | 2007-10-24 10:00 | 20d | floor layer | 6649.6016 | 31500 | 0 | 0 | 38149.6016 | 2007-09-26 08:00 | 20d | 38149.6016 | 0 | 0 | 0 | 0 | 38149.6016 | 0 | 100% | Finished | 38149.6016 | 38066.4805 | 2007-09-26 08:00 | 20d | 38149.6016 | 0 | 0 | 0 | 0 | 38149.6016 | 0 | 100%
65 | completion | 2007-09-26 10:00 | 2007-12-26 10:00 | 65d |  |  | 478615.9062 |  |  | 518712.7188 | [9 empty] | 0% |  | 0 | 23538.8008 | [9 empty] | 0%
32 | stucco | 2007-09-26 10:00 | 2007-10-17 10:00 | 15d | plasterer[3,00 #4] | 14896.8008 | 8642 | 0 | 0 | 23538.8008 |  | 0 | 0 | 23538.8008 | 15d | 0 | 0 | 0 | 23538.8008 | 0% | Not Started | 0 | 23538.8008 |  | 0 | 0 | 23538.8008 | 15d | 0 | 0 | 0 | 23538.8008 | 0%
36 | drywall | 2007-10-24 10:00 | 2007-11-28 10:00 | 25d |  | 0 | 48000 | 0 | 0 | 48000 |  | 0 | 0 | 48000 | 25d | 0 | 0 | 0 | 48000 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 48000 | 25d | 0 | 0 | 0 | 48000 | 0%
41 | kitchen and bar | 2007-10-31 10:00 | 2007-11-21 10:00 | 15d |  | 0 | 87000 | 0 | 0 | 87000 |  | 0 | 0 | 87000 | 15d | 0 | 0 | 0 | 87000 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 87000 | 15d | 0 | 0 | 0 | 87000 | 0%
37 | techniques | 2007-10-31 10:00 | 2007-11-21 10:00 | 15d |  | 0 | 2156.0601 | 0 | 0 | 2156.0601 |  | 0 | 0 | 2156.0601 | 15d | 0 | 0 | 0 | 2156.0601 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 2156.0601 | 15d | 0 | 0 | 0 | 2156.0601 | 0%
44 | stairs | 2007-11-21 10:00 | 2007-12-05 10:00 | 10d |  | 0 | 33000 | 0 | 0 | 33000 |  | 0 | 0 | 33000 | 10d | 0 | 0 | 0 | 33000 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 33000 | 10d | 0 | 0 | 0 | 33000 | 0%
42 | entrance doors | 2007-11-21 10:00 | 2007-12-05 10:00 | 10d |  | 0 | 16000 | 0 | 0 | 16000 |  | 0 | 0 | 16000 | 10d | 0 | 0 | 0 | 16000 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 16000 | 10d | 0 | 0 | 0 | 16000 | 0%
43 | elevator | 2007-11-21 10:00 | 2007-11-28 10:00 | 5d |  | 0 | 38817.8516 | 0 | 0 | 38817.8516 |  | 0 | 0 | 38817.8516 | 5d | 0 | 0 | 0 | 38817.8516 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 38817.8516 | 5d | 0 | 0 | 0 | 38817.8516 | 0%
38 | suspended ceiling | 2007-11-21 10:00 | 2007-11-28 10:00 | 5d |  | 0 | 32000 | 0 | 0 | 32000 |  | 0 | 0 | 32000 | 5d | 0 | 0 | 0 | 32000 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 32000 | 5d | 0 | 0 | 0 | 32000 | 0%
39 | painting | 2007-11-28 10:00 | 2007-12-19 10:00 | 15d | painter[4,00 #6] | 16800 | 83000 | 0 | 0 | 99800 |  | 0 | 0 | 99800 | 15d | 0 | 0 | 0 | 99800 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 99800 | 15d | 0 | 0 | 0 | 99800 | 0%
40 | furniture | 2007-12-19 10:00 | 2007-12-26 10:00 | 5d | joiner[5,00 #5] | 8400 | 130000 | 0 | 0 | 138400 |  | 0 | 0 | 138400 | 5d | 0 | 0 | 0 | 138400 | 0% | Not Started | 0 | 0 |  | 0 | 0 | 138400 | 5d | 0 | 0 | 0 | 138400 | 0%

## TP7
| TP Status Date | 2008-01-10 08:00 |  | TP Name | Completion
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [16 empty] | protrack
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Werkelijke Start | Werkelijke Duurtijd | PAC | PRC | Resterende Duurtijd | PAC Dev | PRC Dev | Werkelijke Kost | Resterende Kost | Percentage Compleet
0 | PROJECT CLAEYS-VERHELST | 2006-04-17 08:00 | 2007-12-26 10:00 | 442d 2h |  |  | 2700210.5 |  |  | 3027133.25 | [9 empty] | 100% |  | 3027133.25 | 3027133.25 | [9 empty] | 100%
46 | preparation | 2006-04-17 08:00 | 2006-12-08 17:00 | 170d |  |  | 216786.9844 |  |  | 253804.5938 | [9 empty] | 100% |  | 253804.5938 | 253804.5938 | [9 empty] | 100%
2 | building permit | 2006-04-17 08:00 | 2006-07-07 17:00 | 60d |  | 0 | 75 | 0 | 0 | 75 | 2006-04-17 08:00 | 100d | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100% | Finished | 75 | 75 | 2006-04-17 08:00 | 100d | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100%
3 | hire contractor | 2006-07-10 08:00 | 2006-08-04 17:00 | 20d |  | 0 | 210000 | 0 | 0 | 210000 | 2006-09-04 08:00 | 30d | 210000 | 0 | 0 | 0 | 0 | 210000 | 0 | 100% | Finished | 210000 | 210000 | 2006-09-04 08:00 | 30d | 210000 | 0 | 0 | 0 | 0 | 210000 | 0 | 100%
4 | temporary offices | 2006-04-17 08:00 | 2006-05-12 17:00 | 20d |  | 0 | 3765.3101 | 0 | 0 | 3765.3101 | 2006-04-17 08:00 | 20d | 3765.3101 | 0 | 0 | 0 | 0 | 3765.3101 | 0 | 100% | Finished | 3765.3101 | 3765.3101 | 2006-04-17 08:00 | 20d | 3765.3101 | 0 | 0 | 0 | 0 | 3765.3101 | 0 | 100%
5 | temporary facilities | 2006-04-17 08:00 | 2006-07-07 17:00 | 60d |  | 0 | 1876.54 | 0 | 0 | 1876.54 | 2006-04-17 08:00 | 60d | 1876.54 | 0 | 0 | 0 | 0 | 1876.54 | 0 | 100% | Finished | 1876.54 | 1876.54 | 2006-04-17 08:00 | 60d | 1876.54 | 0 | 0 | 0 | 0 | 1876.54 | 0 | 100%
16 | preparation contractor | 2006-08-07 08:00 | 2006-10-27 17:00 | 60d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2006-09-04 08:00 | 60d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 2006-09-04 08:00 | 60d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100%
6 | demolition | 2006-10-30 08:00 | 2006-12-08 17:00 | 30d | team subcontractor[4,00 #8] | 37017.6016 | 1070.11 | 0 | 0 | 38087.7109 | 2006-11-27 08:00 | 54d | 67701.7891 | 0 | 0 | 0 | 0 | 67701.7891 | 0 | 100% | Finished | 38087.7109 | 38087.7109 | 2006-11-27 08:00 | 54d | 67701.7891 | 0 | 0 | 0 | 0 | 67701.7891 | 0 | 100%
47 | foundation | 2006-12-11 08:00 | 2007-02-01 17:00 | 39d |  |  | 362567.875 |  |  | 401436.375 | [9 empty] | 100% |  | 401436.375 | 401436.375 | [9 empty] | 100%
17 | excavation | 2006-12-11 08:00 | 2006-12-28 17:00 | 14d | team subcontractor | 4318.7207 | 26000 | 0 | 0 | 30318.7207 | 2007-02-08 08:00 | 10d | 29084.8008 | 0 | 0 | 0 | 0 | 29084.8008 | 0 | 100% | Finished | 30318.7207 | 30318.7207 | 2007-02-08 08:00 | 10d | 29084.8008 | 0 | 0 | 0 | 0 | 29084.8008 | 0 | 100%
69 | soil analyses | 2006-12-11 08:00 | 2006-12-12 17:00 | 2d | team subcontractor | 616.96 | 2000 | 0 | 0 | 2616.96 | 2007-02-08 08:00 | 12d | 5701.7603 | 0 | 0 | 0 | 0 | 5701.7603 | 0 | 100% | Finished | 2616.96 | 2616.96 | 2007-02-08 08:00 | 12d | 5701.7603 | 0 | 0 | 0 | 0 | 5701.7603 | 0 | 100%
18 | foundation beam | 2006-12-29 08:00 | 2007-02-01 17:00 | 25d | team subcontractor[3,00 #8] | 23136 | 98523.7266 | 0 | 0 | 121659.7266 | 2007-02-28 08:00 | 22d | 118883.4062 | 0 | 0 | 0 | 0 | 118883.4062 | 0 | 100% | Finished | 121659.7266 | 121659.7266 | 2007-02-28 08:00 | 22d | 118883.4062 | 0 | 0 | 0 | 0 | 118883.4062 | 0 | 100%
21 | placing sewerage | 2006-12-29 08:00 | 2007-01-11 17:00 | 10d | team subcontractor[3,00 #8] | 9254.4004 | 1224.73 | 0 | 0 | 10479.1309 | 2007-02-28 08:00 | 12d | 12330.0098 | 0 | 0 | 0 | 0 | 12330.0098 | 0 | 100% | Finished | 10479.1309 | 10479.1309 | 2007-02-28 08:00 | 12d | 12330.0098 | 0 | 0 | 0 | 0 | 12330.0098 | 0 | 100%
23 | foundation plate | 2007-01-12 08:00 | 2007-01-12 17:00 | 1d | team subcontractor[5,00 #8] | 1542.4062 | 234819.4375 | 0 | 0 | 236361.8438 | 2007-03-16 08:00 | 1d | 236361.8438 | 0 | 0 | 0 | 0 | 236361.8438 | 0 | 100% | Finished | 236361.8438 | 236361.8438 | 2007-03-16 08:00 | 1d | 236361.8438 | 0 | 0 | 0 | 0 | 236361.8438 | 0 | 100%
48 | shell | 2007-02-02 08:00 | 2007-04-26 17:00 | 60d |  |  | 472804.4375 |  |  | 542212.4375 | [9 empty] | 100% |  | 542212.4375 | 542212.4375 | [9 empty] | 100%
19 | steelframe I | 2007-02-02 08:00 | 2007-03-01 17:00 | 20d | team subcontractor[4,00 #8] | 24678.3984 | 118992.5078 | 0 | 0 | 143670.9062 | 2007-04-02 08:00 | 15d | 137501.3125 | 0 | 0 | 0 | 0 | 137501.3125 | 0 | 100% | Finished | 143670.9062 | 143670.9062 | 2007-04-02 08:00 | 15d | 137501.3125 | 0 | 0 | 0 | 0 | 137501.3125 | 0 | 100%
20 | concrete vaults I | 2007-03-02 08:00 | 2007-03-15 17:00 | 10d | team subcontractor[4,00 #8] | 12339.2031 | 117409.7188 | 0 | 0 | 129748.9219 | 2007-04-23 08:00 | 5d | 123579.3203 | 0 | 0 | 0 | 0 | 123579.3203 | 0 | 100% | Finished | 129748.9219 | 129748.9219 | 2007-04-23 08:00 | 5d | 123579.3203 | 0 | 0 | 0 | 0 | 123579.3203 | 0 | 100%
22 | steelframe II | 2007-03-16 08:00 | 2007-04-05 17:00 | 15d | team subcontractor[3,00 #8] | 13881.6016 | 118992.5078 | 0 | 0 | 132874.1094 | 2007-04-30 08:00 | 15d | 132874.1094 | 0 | 0 | 0 | 0 | 132874.1094 | 0 | 100% | Finished | 132874.1094 | 132874.1094 | 2007-04-30 08:00 | 15d | 132874.1094 | 0 | 0 | 0 | 0 | 132874.1094 | 0 | 100%
24 | concrete vaults II | 2007-04-06 08:00 | 2007-04-26 17:00 | 15d | team subcontractor[4,00 #8] | 18508.7969 | 117409.7188 | 0 | 0 | 135918.5156 | 2007-05-21 08:00 | 10d | 129748.9219 | 0 | 0 | 0 | 0 | 129748.9219 | 0 | 100% | Finished | 135918.5156 | 135918.5156 | 2007-05-21 08:00 | 10d | 129748.9219 | 0 | 0 | 0 | 0 | 129748.9219 | 0 | 100%
50 | wind and water proof | 2007-04-27 08:00 | 2007-06-07 17:00 | 30d |  |  | 560844.1875 |  |  | 597047.375 | [9 empty] | 100% |  | 597047.375 | 597047.375 | [9 empty] | 100%
25 | facades | 2007-04-27 08:00 | 2007-05-24 17:00 | 20d | team subcontractor[2,00 #8] | 12339.1875 | 339314 | 0 | 0 | 351653.1875 | 2007-06-04 08:00 | 20d | 351653.1875 | 0 | 0 | 0 | 0 | 351653.1875 | 0 | 100% | Finished | 351653.1875 | 351653.1875 | 2007-06-04 08:00 | 20d | 351653.1875 | 0 | 0 | 0 | 0 | 351653.1875 | 0 | 100%
26 | outside windows | 2007-05-25 08:00 | 2007-06-07 17:00 | 10d | carpenter[3,00 #3] | 9120 | 150750.5938 | 0 | 0 | 159870.5938 | 2007-07-02 08:00 | 92d | 234654.5938 | 0 | 0 | 0 | 0 | 234654.5938 | 0 | 100% | Finished | 159870.5938 | 159870.5938 | 2007-07-02 08:00 | 92d | 234654.5938 | 0 | 0 | 0 | 0 | 234654.5938 | 0 | 100%
49 | roof | 2007-04-27 08:00 | 2007-05-10 17:00 | 10d | roofer[4,00 #4] | 11520 | 70779.5703 | 40.3 | 3224 | 85523.5703 | 2007-06-04 08:00 | 10d | 85523.5703 | 0 | 0 | 0 | 0 | 85523.5703 | 0 | 100% | Finished | 85523.5703 | 85523.5703 | 2007-06-04 08:00 | 10d | 85523.5703 | 0 | 0 | 0 | 0 | 85523.5703 | 0 | 100%
62 | warehouse | 2007-06-08 08:00 | 2007-10-31 10:00 | 103d 2h |  |  | 257044.9688 |  |  | 301814.5625 | [9 empty] | 100% |  | 301814.5625 | 301814.5625 | [9 empty] | 100%
28 | v0 concrete | 2007-06-08 08:00 | 2007-06-21 17:00 | 10d | team subcontractor[5,00 #8] | 15424 | 134400 | 0 | 0 | 149824 | 2007-07-25 08:00 | 5d | 142112 | 0 | 0 | 0 | 0 | 142112 | 0 | 100% | Finished | 149824 | 149824 | 2007-07-25 08:00 | 5d | 142112 | 0 | 0 | 0 | 0 | 142112 | 0 | 100%
30 | v0 sanitary | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 | 2007-08-29 08:00 | 10d | 7673 | 0 | 0 | 0 | 0 | 7673 | 0 | 100% | Finished | 7673 | 7673 | 2007-08-29 08:00 | 10d | 7673 | 0 | 0 | 0 | 0 | 7673 | 0 | 100%
27 | v0 masonry | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 40.65 | 3252 | 37704.9609 | 2007-08-29 08:00 | 10d | 37704.9609 | 0 | 0 | 0 | 0 | 37704.9609 | 0 | 100% | Finished | 37704.9609 | 37704.9609 | 2007-08-29 08:00 | 10d | 37704.9609 | 0 | 0 | 0 | 0 | 37704.9609 | 0 | 100%
59 | v0 heating | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | heating engineer | 6912 | 11651 | 0 | 0 | 18563 | 2007-08-29 08:00 | 20d | 18563 | 0 | 0 | 0 | 0 | 18563 | 0 | 100% | Finished | 18563 | 18563 | 2007-08-29 08:00 | 20d | 18563 | 0 | 0 | 0 | 0 | 18563 | 0 | 100%
29 | v0 electricity | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 | 2007-08-02 08:00 | 15d | 3840 | 0 | 0 | 0 | 0 | 3840 | 0 | 100% | Finished | 6400 | 6400 | 2007-08-02 08:00 | 15d | 3840 | 0 | 0 | 0 | 0 | 3840 | 0 | 100%
35 | v0 floors | 2007-10-03 10:00 | 2007-10-31 10:00 | 20d | floor layer | 6649.6016 | 75000 | 0 | 0 | 81649.6016 | 2007-09-26 08:00 | 20d | 81649.6016 | 0 | 0 | 0 | 0 | 81649.6016 | 0 | 100% | Finished | 81649.6016 | 81649.6016 | 2007-09-26 08:00 | 20d | 81649.6016 | 0 | 0 | 0 | 0 | 81649.6016 | 0 | 100%
66 | construction leave | 2007-08-15 10:00 | 2007-08-29 10:00 | 10d |  |  | 0.01 |  |  | 0.01 | [9 empty] | 100% |  | 0.01 | 0.01 | [9 empty] | 100%
31 | construction leave | 2007-08-15 10:00 | 2007-08-29 10:00 | 10d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2007-08-08 08:00 | 10d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Started | 0.01 | 0.01 | 2007-08-08 08:00 | 10d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100%
63 | level 1 | 2007-08-29 10:00 | 2007-10-24 10:00 | 40d |  |  | 226284.9844 |  |  | 262542.5938 | [9 empty] | 100% |  | 262542.5938 | 262542.5938 | [9 empty] | 100%
52 | v1 sanitary | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 | 2007-08-29 08:00 | 10d | 7673 | 0 | 0 | 0 | 0 | 7673 | 0 | 100% | Finished | 7673 | 7673 | 2007-08-29 08:00 | 10d | 7673 | 0 | 0 | 0 | 0 | 7673 | 0 | 100%
45 | v1 masonry | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 40.65 | 3252 | 37704.9609 | 2007-08-29 08:00 | 10d | 37704.9609 | 0 | 0 | 0 | 0 | 37704.9609 | 0 | 100% | Finished | 37704.9609 | 37704.9609 | 2007-08-29 08:00 | 10d | 37704.9609 | 0 | 0 | 0 | 0 | 37704.9609 | 0 | 100%
34 | v1 screed | 2007-08-29 10:00 | 2007-09-19 10:00 | 15d | screed layer[2,00 #3] | 0 | 106140 | 0 | 0 | 106140 | 2007-08-29 08:00 | 15d | 106140 | 0 | 0 | 0 | 0 | 106140 | 0 | 100% | Finished | 106140 | 106140 | 2007-08-29 08:00 | 15d | 106140 | 0 | 0 | 0 | 0 | 106140 | 0 | 100%
60 | v1 heating | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | heating engineer | 6912 | 11651 | 43.2 | 6912 | 25475 | 2007-08-29 08:00 | 20d | 25475 | 0 | 0 | 0 | 0 | 25475 | 0 | 100% | Finished | 25475 | 25475 | 2007-08-29 08:00 | 20d | 25475 | 0 | 0 | 0 | 0 | 25475 | 0 | 100%
51 | v1 electricity | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 | 2007-08-29 08:00 | 25d | 6400 | 0 | 0 | 0 | 0 | 6400 | 0 | 100% | Finished | 6400 | 6400 | 2007-08-29 08:00 | 25d | 6400 | 0 | 0 | 0 | 0 | 6400 | 0 | 100%
67 | v1 drying screed | 2007-09-19 10:00 | 2007-09-26 10:00 | 5d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2007-09-19 08:00 | 5d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 2007-09-19 08:00 | 5d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100%
57 | v1 flooring | 2007-09-26 10:00 | 2007-10-24 10:00 | 20d | floor layer | 6649.6016 | 72500 | 0 | 0 | 79149.6016 | 2007-10-03 08:00 | 20d | 79149.6016 | 0 | 0 | 0 | 0 | 79149.6016 | 0 | 100% | Finished | 79149.6016 | 79149.6016 | 2007-10-03 08:00 | 20d | 79149.6016 | 0 | 0 | 0 | 0 | 79149.6016 | 0 | 100%
64 | level 2 | 2007-08-29 10:00 | 2007-10-24 10:00 | 40d |  |  | 125260.9688 |  |  | 149562.5625 | [9 empty] | 100% |  | 149562.5625 | 149562.5625 | [9 empty] | 100%
53 | v2 sanitary | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 | 2007-08-29 08:00 | 10d | 7673 | 0 | 0 | 0 | 0 | 7673 | 0 | 100% | Finished | 7673 | 7673 | 2007-08-29 08:00 | 10d | 7673 | 0 | 0 | 0 | 0 | 7673 | 0 | 100%
55 | v2 masonry | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 0 | 0 | 34452.9609 | 2007-08-29 08:00 | 10d | 34452.9609 | 0 | 0 | 0 | 0 | 34452.9609 | 0 | 100% | Finished | 34452.9609 | 34452.9609 | 2007-08-29 08:00 | 10d | 34452.9609 | 0 | 0 | 0 | 0 | 34452.9609 | 0 | 100%
56 | v2 screed | 2007-08-29 10:00 | 2007-09-19 10:00 | 15d | screed layer | 0 | 46116 | 0 | 0 | 46116 | 2007-08-29 08:00 | 15d | 46116 | 0 | 0 | 0 | 0 | 46116 | 0 | 100% | Finished | 46116 | 46116 | 2007-08-29 08:00 | 15d | 46116 | 0 | 0 | 0 | 0 | 46116 | 0 | 100%
61 | v2 heating | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | electrician | 5120 | 11651 | 0 | 0 | 16771 | 2007-08-29 08:00 | 20d | 16771 | 0 | 0 | 0 | 0 | 16771 | 0 | 100% | Finished | 16771 | 16771 | 2007-08-29 08:00 | 20d | 16771 | 0 | 0 | 0 | 0 | 16771 | 0 | 100%
54 | v2 electricity | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 | 2007-08-29 08:00 | 20d | 5120 | 0 | 0 | 0 | 0 | 5120 | 0 | 100% | Finished | 6400 | 6400 | 2007-08-29 08:00 | 20d | 5120 | 0 | 0 | 0 | 0 | 5120 | 0 | 100%
68 | v2 drying screed | 2007-09-19 10:00 | 2007-09-26 10:00 | 5d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2007-09-19 08:00 | 5d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100% | Finished | 0.01 | 0.01 | 2007-09-19 08:00 | 5d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100%
58 | v2 flooring | 2007-09-26 10:00 | 2007-10-24 10:00 | 20d | floor layer | 6649.6016 | 31500 | 0 | 0 | 38149.6016 | 2007-09-26 08:00 | 20d | 38149.6016 | 0 | 0 | 0 | 0 | 38149.6016 | 0 | 100% | Finished | 38149.6016 | 38149.6016 | 2007-09-26 08:00 | 20d | 38149.6016 | 0 | 0 | 0 | 0 | 38149.6016 | 0 | 100%
65 | completion | 2007-09-26 10:00 | 2007-12-26 10:00 | 65d |  |  | 478615.9062 |  |  | 518712.7188 | [9 empty] | 100% |  | 518712.7188 | 518712.7188 | [9 empty] | 100%
32 | stucco | 2007-09-26 10:00 | 2007-10-17 10:00 | 15d | plasterer[3,00 #4] | 14896.8008 | 8642 | 0 | 0 | 23538.8008 | 2007-11-05 08:00 | 15d | 23538.8008 | 0 | 0 | 0 | 0 | 23538.8008 | 0 | 100% | Finished | 23538.8008 | 23538.8008 | 2007-11-05 08:00 | 15d | 23538.8008 | 0 | 0 | 0 | 0 | 23538.8008 | 0 | 100%
36 | drywall | 2007-10-24 10:00 | 2007-11-28 10:00 | 25d |  | 0 | 48000 | 0 | 0 | 48000 | 2007-11-05 08:00 | 25d | 48000 | 0 | 0 | 0 | 0 | 48000 | 0 | 100% | Finished | 48000 | 48000 | 2007-11-05 08:00 | 25d | 48000 | 0 | 0 | 0 | 0 | 48000 | 0 | 100%
41 | kitchen and bar | 2007-10-31 10:00 | 2007-11-21 10:00 | 15d |  | 0 | 87000 | 0 | 0 | 87000 | 2007-11-26 08:00 | 20d | 87000 | 0 | 0 | 0 | 0 | 87000 | 0 | 100% | Finished | 87000 | 87000 | 2007-11-26 08:00 | 20d | 87000 | 0 | 0 | 0 | 0 | 87000 | 0 | 100%
37 | techniques | 2007-10-31 10:00 | 2007-11-21 10:00 | 15d |  | 0 | 2156.0601 | 0 | 0 | 2156.0601 | 2007-11-26 08:00 | 15d | 2156.0601 | 0 | 0 | 0 | 0 | 2156.0601 | 0 | 100% | Finished | 2156.0601 | 2156.0601 | 2007-11-26 08:00 | 15d | 2156.0601 | 0 | 0 | 0 | 0 | 2156.0601 | 0 | 100%
44 | stairs | 2007-11-21 10:00 | 2007-12-05 10:00 | 10d |  | 0 | 33000 | 0 | 0 | 33000 | 2007-12-10 08:00 | 10d | 33000 | 0 | 0 | 0 | 0 | 33000 | 0 | 100% | Finished | 33000 | 33000 | 2007-12-10 08:00 | 10d | 33000 | 0 | 0 | 0 | 0 | 33000 | 0 | 100%
42 | entrance doors | 2007-11-21 10:00 | 2007-12-05 10:00 | 10d |  | 0 | 16000 | 0 | 0 | 16000 | 2007-12-10 08:00 | 10d | 16000 | 0 | 0 | 0 | 0 | 16000 | 0 | 100% | Finished | 16000 | 16000 | 2007-12-10 08:00 | 10d | 16000 | 0 | 0 | 0 | 0 | 16000 | 0 | 100%
43 | elevator | 2007-11-21 10:00 | 2007-11-28 10:00 | 5d |  | 0 | 38817.8516 | 0 | 0 | 38817.8516 | 2007-12-10 08:00 | 5d | 38817.8516 | 0 | 0 | 0 | 0 | 38817.8516 | 0 | 100% | Finished | 38817.8516 | 38817.8516 | 2007-12-10 08:00 | 5d | 38817.8516 | 0 | 0 | 0 | 0 | 38817.8516 | 0 | 100%
38 | suspended ceiling | 2007-11-21 10:00 | 2007-11-28 10:00 | 5d |  | 0 | 32000 | 0 | 0 | 32000 | 2007-12-10 08:00 | 5d | 32000 | 0 | 0 | 0 | 0 | 32000 | 0 | 100% | Finished | 32000 | 32000 | 2007-12-10 08:00 | 5d | 32000 | 0 | 0 | 0 | 0 | 32000 | 0 | 100%
39 | painting | 2007-11-28 10:00 | 2007-12-19 10:00 | 15d | painter[4,00 #6] | 16800 | 83000 | 0 | 0 | 99800 | 2007-12-17 08:00 | 15d | 99800 | 0 | 0 | 0 | 0 | 99800 | 0 | 100% | Finished | 99800 | 99800 | 2007-12-17 08:00 | 15d | 99800 | 0 | 0 | 0 | 0 | 99800 | 0 | 100%
40 | furniture | 2007-12-19 10:00 | 2007-12-26 10:00 | 5d | joiner[5,00 #5] | 8400 | 130000 | 0 | 0 | 138400 | 2008-01-03 08:00 | 5d | 138400 | 0 | 0 | 0 | 0 | 138400 | 0 | 100% | Finished | 138400 | 138400 | 2008-01-03 08:00 | 5d | 138400 | 0 | 0 | 0 | 0 | 138400 | 0 | 100%