## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost
0 | Claeys-Verhelst Premises | 1 |  |  | 2006-04-17 08:00 | 2007-12-25 17:00 | 10d |  | 0 | 2700210.3057 | 0 | 0 | 3027133.1861
46 | preparation | 1.1 |  |  | 2006-04-17 08:00 | 2006-12-08 17:00 | 10d |  | 0 | 216786.9701 | 0 | 0 | 253804.5701
2 | building permit | 1.1.1 |  | FS3+0 | 2006-04-17 08:00 | 2006-07-07 17:00 | 60d |  | 0 | 75 | 0 | 0 | 75
3 | hire contractor | 1.1.2 | 2FS+0 | FS16+0 | 2006-07-10 08:00 | 2006-08-04 17:00 | 20d |  | 0 | 210000 | 0 | 0 | 210000
4 | temporary offices | 1.1.3 |  |  | 2006-04-17 08:00 | 2006-05-12 17:00 | 20d |  | 0 | 3765.3101 | 0 | 0 | 3765.3101
5 | temporary facilities | 1.1.4 |  |  | 2006-04-17 08:00 | 2006-07-07 17:00 | 60d |  | 0 | 1876.54 | 0 | 0 | 1876.54
16 | preparation contractor | 1.1.5 | 3FS+0 | FS6+0 | 2006-08-07 08:00 | 2006-10-27 17:00 | 60d |  | 0 | 0.01 | 0 | 0 | 0.01
6 | demolition | 1.1.6 | 16FS+0 | FS17+0;FS69+0 | 2006-10-30 08:00 | 2006-12-08 17:00 | 30d | team VDW[4.0 #8] | 37017.6 | 1070.11 | 0 | 0 | 38087.71
47 | foundation | 1.2 |  |  | 2006-12-11 08:00 | 2007-02-01 17:00 | 10d |  | 0 | 362567.894 | 0 | 0 | 401436.374
17 | excavation | 1.2.1 | 6FS+0 | FS18+0;FS21+0 | 2006-12-11 08:00 | 2006-12-28 17:00 | 14d | team VDW | 4318.72 | 26000 | 0 | 0 | 30318.72
69 | soil analyses | 1.2.2 | 6FS+0 | FS18+0 | 2006-12-11 08:00 | 2006-12-12 17:00 | 2d | team VDW | 616.96 | 2000 | 0 | 0 | 2616.96
18 | foundation beam | 1.2.3 | 17FS+0;69FS+0 | FS19+0 | 2006-12-29 08:00 | 2007-02-01 17:00 | 25d | team VDW[3.0 #8] | 23136 | 98523.7266 | 0 | 0 | 121659.7266
21 | placing sewerage | 1.2.4 | 17FS+0 | FS23+0 | 2006-12-29 08:00 | 2007-01-11 17:00 | 10d | team VDW[3.0 #8] | 9254.4 | 1224.73 | 0 | 0 | 10479.13
23 | foundation plate | 1.2.5 | 21FS+0 | FS19+0 | 2007-01-12 08:00 | 2007-01-12 17:00 | 1d | team VDW[5.0 #8] | 1542.4 | 234819.4375 | 0 | 0 | 236361.8375
48 | shell | 1.3 |  |  | 2007-02-02 08:00 | 2007-04-26 17:00 | 10d |  | 0 | 472804.4531 | 0 | 0 | 542212.4531
19 | steelframe I | 1.3.1 | 18FS+0;23FS+0 | FS20+0 | 2007-02-02 08:00 | 2007-03-01 17:00 | 20d | team VDW[4.0 #8] | 24678.4 | 118992.5078 | 0 | 0 | 143670.9078
20 | concrete vaults I | 1.3.2 | 19FS+0 | FS22+0 | 2007-03-02 08:00 | 2007-03-15 17:00 | 10d | team VDW[4.0 #8] | 12339.2 | 117409.7188 | 0 | 0 | 129748.9187
22 | steelframe II | 1.3.3 | 20FS+0 | FS24+0 | 2007-03-16 08:00 | 2007-04-05 17:00 | 15d | team VDW[3.0 #8] | 13881.6 | 118992.5078 | 0 | 0 | 132874.1078
24 | concrete volt II | 1.3.4 | 22FS+0 | FS25+0;FS49+0 | 2007-04-06 08:00 | 2007-04-26 17:00 | 15d | team VDW[4.0 #8] | 18508.8 | 117409.7188 | 0 | 0 | 135918.5187
50 | wind and water proof | 1.4 |  |  | 2007-04-27 08:00 | 2007-06-07 17:00 | 10d |  | 0 | 560844.1641 | 0 | 0 | 597047.364
25 | facades | 1.4.1 | 24FS+0 | FS26+0 | 2007-04-27 08:00 | 2007-05-24 17:00 | 20d | team VDW[2.0 #8] | 12339.2 | 339314 | 0 | 0 | 351653.2
26 | outside windows | 1.4.2 | 25FS+0 | FS28+0;FS29+0 | 2007-05-25 08:00 | 2007-06-07 17:00 | 10d | windows[3.0 #3] | 9120 | 150750.5938 | 0 | 0 | 159870.5938
49 | roof | 1.4.3 | 24FS+0 |  | 2007-04-27 08:00 | 2007-05-10 17:00 | 10d | roofing[4.0 #4] | 11520 | 70779.5703 | 40.3 | 3223.9999 | 85523.5703
62 | warehouse | 1.5 |  |  | 2007-06-08 08:00 | 2007-10-30 17:00 | 10d |  | 0 | 257044.9609 | 0 | 0 | 301814.5611
28 | v0 polierbeton | 1.5.1 | 26FS+0 | FS30+0;FS27+0;FS59+0;FS52+0;FS45+0;FS34+0;FS60+0;FS51+0 | 2007-06-08 08:00 | 2007-06-21 17:00 | 10d | team VDW[5.0 #8] | 15424 | 134400 | 0 | 0 | 149824
30 | v0 sanitary | 1.5.2 | 31FS+0;28FS+0 | FS35+0 | 2007-08-29 10:00 | 2007-09-11 17:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673
27 | v0 -masonry | 1.5.3 | 31FS+0;28FS+0 |  | 2007-08-29 10:00 | 2007-09-11 17:00 | 10d | mason | 3252 | 31200.9609 | 40.65 | 3252.0001 | 37704.9611
59 | v0 heating | 1.5.4 | 31FS+0;28FS+0 | FS35+0 | 2007-08-29 10:00 | 2007-09-25 17:00 | 20d | heating | 6912 | 11651 | 0 | 0 | 18563
29 | v0 electricity | 1.5.5 | 26FS+0;31FS+0 | FS35+0 | 2007-08-29 10:00 | 2007-10-02 17:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400
35 | v0 floors | 1.5.6 | 59FS+0;29FS+0;30FS+0 | FS41+0;FS37+0 | 2007-10-03 10:00 | 2007-10-30 17:00 | 20d | flooring | 6649.6 | 75000 | 0 | 0 | 81649.6
66 | construction leave | 1.6 |  |  | 2007-08-15 10:00 | 2007-08-28 17:00 | 10d |  | 0 | 0.01 | 0 | 0 | 0.01
31 | construction leave | 1.6.1 |  | FS53+0;FS55+0;FS56+0;FS61+0;FS54+0;FS30+0;FS27+0;FS59+0;FS52+0;FS45+0;FS34+0;FS60+0;FS51+0;FS29+0 | 2007-08-15 10:00 | 2007-08-28 17:00 | 10d |  | 0 | 0.01 | 0 | 0 | 0.01
63 | level 1 | 1.7 |  |  | 2007-08-29 10:00 | 2007-10-23 17:00 | 10d |  | 0 | 226284.9709 | 0 | 0 | 262542.5712
52 | vI sanitary | 1.7.1 | 31FS+0;28FS+0 |  | 2007-08-29 10:00 | 2007-09-11 17:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673
45 | vI masonry | 1.7.2 | 31FS+0;28FS+0 |  | 2007-08-29 10:00 | 2007-09-11 17:00 | 10d | mason | 3252 | 31200.9609 | 40.65 | 3252.0001 | 37704.9611
34 | v1screed | 1.7.3 | 31FS+0;28FS+0 | FS67+0 | 2007-08-29 10:00 | 2007-09-18 17:00 | 15d | chapen[2.0 #3] | 0 | 106140 | 0 | 0 | 106140
60 | v1 heating | 1.7.4 | 31FS+0;28FS+0 |  | 2007-08-29 10:00 | 2007-09-25 17:00 | 20d | heating | 6912 | 11651 | 43.2 | 6912.0001 | 25475.0001
51 | vI electricity | 1.7.5 | 31FS+0;28FS+0 |  | 2007-08-29 10:00 | 2007-10-02 17:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400
67 | v1 drying screed | 1.7.6 | 34FS+0 | FS57+0;FS32+0 | 2007-09-19 10:00 | 2007-09-25 17:00 | 5d |  | 0 | 0.01 | 0 | 0 | 0.01
57 | v1flooring | 1.7.7 | 67FS+0 | FS41+0;FS37+0;FS36+0 | 2007-09-26 10:00 | 2007-10-23 17:00 | 20d | flooring | 6649.6 | 72500 | 0 | 0 | 79149.6
64 | level 2 | 1.8 |  |  | 2007-08-29 10:00 | 2007-10-23 17:00 | 10d |  | 0 | 125260.9709 | 0 | 0 | 149562.5709
53 | v2 sanitary | 1.8.1 | 31FS+0 |  | 2007-08-29 10:00 | 2007-09-11 17:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673
55 | v2 masonry | 1.8.2 | 31FS+0 |  | 2007-08-29 10:00 | 2007-09-11 17:00 | 10d | mason | 3252 | 31200.9609 | 0 | 0 | 34452.9609
56 | v2 screed | 1.8.3 | 31FS+0 | FS68+0;FS36+0 | 2007-08-29 10:00 | 2007-09-18 17:00 | 15d | chapen | 0 | 46116 | 0 | 0 | 46116
61 | v2 heating | 1.8.4 | 31FS+0 |  | 2007-08-29 10:00 | 2007-09-25 17:00 | 20d | electrician | 5120 | 11651 | 0 | 0 | 16771
54 | v2 electricity | 1.8.5 | 31FS+0 |  | 2007-08-29 10:00 | 2007-10-02 17:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400
68 | v2 drying screed | 1.8.6 | 56FS+0 | FS58+0;FS32+0 | 2007-09-19 10:00 | 2007-09-25 17:00 | 5d |  | 0 | 0.01 | 0 | 0 | 0.01
58 | v2 flooring | 1.8.7 | 68FS+0 | FS41+0;FS37+0;FS36+0 | 2007-09-26 10:00 | 2007-10-23 17:00 | 20d | flooring | 6649.6 | 31500 | 0 | 0 | 38149.6
65 | completion | 1.9 |  |  | 2007-09-26 10:00 | 2007-12-25 17:00 | 10d |  | 0 | 478615.9116 | 0 | 0 | 518712.7116
32 | stucco | 1.9.1 | 68FS+0;67FS+0 | FS41+0;FS37+0 | 2007-09-26 10:00 | 2007-10-16 17:00 | 15d | stucco[3.0 #4] | 14896.8 | 8642 | 0 | 0 | 23538.8
36 | drywall | 1.9.2 | 58FS+0;57FS+0;56FS+0 |  | 2007-10-24 10:00 | 2007-11-27 17:00 | 25d |  | 0 | 48000 | 0 | 0 | 48000
41 | kitchen and bar | 1.9.3 | 32FS+0;58FS+0;57FS+0;35FS+0 |  | 2007-10-31 10:00 | 2007-11-20 17:00 | 15d |  | 0 | 87000 | 0 | 0 | 87000
37 | techniques | 1.9.4 | 32FS+0;58FS+0;57FS+0;35FS+0 | FS38+0;FS42+0;FS43+0;FS44+0 | 2007-10-31 10:00 | 2007-11-20 17:00 | 15d |  | 0 | 2156.0601 | 0 | 0 | 2156.0601
44 | stairs | 1.9.5 | 37FS+0 |  | 2007-11-21 10:00 | 2007-12-04 17:00 | 10d |  | 0 | 33000 | 0 | 0 | 33000
42 | entrance doors | 1.9.6 | 37FS+0 |  | 2007-11-21 10:00 | 2007-12-04 17:00 | 10d |  | 0 | 16000 | 0 | 0 | 16000
43 | elevator | 1.9.7 | 37FS+0 |  | 2007-11-21 10:00 | 2007-11-27 17:00 | 5d |  | 0 | 38817.8516 | 0 | 0 | 38817.8516
38 | suspended ceiling | 1.9.8 | 37FS+0 | FS39+0 | 2007-11-21 10:00 | 2007-11-27 17:00 | 5d |  | 0 | 32000 | 0 | 0 | 32000
39 | painting | 1.9.9 | 38FS+0 | FS40+0 | 2007-11-28 10:00 | 2007-12-18 17:00 | 15d | painter[4.0 #6] | 16800 | 83000 | 0 | 0 | 99800
40 | furniture | 1.9.10 | 39FS+0 |  | 2007-12-19 10:00 | 2007-12-25 17:00 | 5d | furniture[5.0 #5] | 8400 | 130000 | 0 | 0 | 138400

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost
1 | plumber | Renewable | 4 #4 | 0 | 36 | 30;52;53; | 8640
2 | electrician | Renewable | 4 #4 | 0 | 32 | 29;51;61;54; | 24320
3 | team VDW | Renewable | 8 #8 | 0 | 38.56 | 6[4 #8];17;69;18[3 #8];21[3 #8];23[5 #8];19[4 #8];20[4 #8];22[3 #8];24[4 #8];25[2 #8];28[5 #8]; | 173057.28
4 | mason | Renewable | 4 #4 | 0 | 40.65 | 27;45;55; | 9756
5 | heating | Renewable | 2 #2 | 0 | 43.2 | 59;60; | 13824
6 | roofing | Renewable | 4 #4 | 0 | 36 | 49[4 #4]; | 11520
7 | windows | Renewable | 3 #3 | 0 | 38 | 26[3 #3]; | 9120
8 | flooring | Renewable | 4 #4 | 0 | 41.56 | 35;57;58; | 19948.8
9 | chapen | Renewable | 3 #3 | 0 | 0 | 34[2 #3];56; | 0
10 | stucco | Renewable | 4 #4 | 0 | 41.38 | 32[3 #4]; | 14896.8
11 | painter | Renewable | 6 #6 | 0 | 35 | 39[4 #6]; | 16800
12 | furniture | Renewable | 5 #5 | 0 | 42 | 40[5 #5]; | 8400

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic
0 | Claeys-Verhelst Premises | 10d | manual - absolute | 0 | 0 | 0
46 | preparation | 10d | manual - absolute | 0 | 0 | 0
2 | building permit | 60d | manual - absolute | 402 | 480 | 812
3 | hire contractor | 20d | manual - absolute | 127 | 160 | 326
4 | temporary offices | 20d | standard - symmetric | 80 | 100 | 120
5 | temporary facilities | 60d | standard - symmetric | 80 | 100 | 120
16 | preparation contractor | 60d | standard - no risk | 99 | 100 | 101
6 | demolition | 30d | manual - absolute | 219 | 240 | 302
47 | foundation | 10d | manual - absolute | 0 | 0 | 0
17 | excavation | 14d | standard - symmetric | 80 | 100 | 120
69 | soil analyses | 2d | standard - symmetric | 80 | 100 | 120
18 | foundation beam | 25d | manual - absolute | 159 | 200 | 363
21 | placing sewerage | 10d | manual - absolute | 63 | 80 | 98
23 | foundation plate | 1d | manual - absolute | 6 | 8 | 10
48 | shell | 10d | manual - absolute | 0 | 0 | 0
19 | steelframe I | 20d | manual - absolute | 104 | 120 | 166
20 | concrete vaults I | 10d | manual - absolute | 32 | 40 | 48
22 | steelframe II | 15d | manual - absolute | 64 | 80 | 113
24 | concrete volt II | 15d | manual - absolute | 66 | 80 | 121
50 | wind and water proof | 10d | manual - absolute | 0 | 0 | 0
25 | facades | 20d | manual - absolute | 128 | 160 | 463
26 | outside windows | 10d | manual - absolute | 64 | 80 | 175
49 | roof | 10d | standard - symmetric | 80 | 100 | 120
62 | warehouse | 10d | manual - absolute | 0 | 0 | 0
28 | v0 polierbeton | 10d | standard - symmetric | 80 | 100 | 120
30 | v0 sanitary | 10d | standard - no risk | 99 | 100 | 101
27 | v0 -masonry | 10d | standard - no risk | 99 | 100 | 101
59 | v0 heating | 20d | standard - no risk | 99 | 100 | 101
29 | v0 electricity | 25d | standard - no risk | 99 | 100 | 101
35 | v0 floors | 20d | manual - absolute | 128 | 163 | 543
66 | construction leave | 10d | manual - absolute | 0 | 0 | 0
31 | construction leave | 10d | standard - no risk | 99 | 100 | 101
63 | level 1 | 10d | manual - absolute | 0 | 0 | 0
52 | vI sanitary | 10d | standard - no risk | 99 | 100 | 101
45 | vI masonry | 10d | standard - no risk | 99 | 100 | 101
34 | v1screed | 15d | standard - no risk | 99 | 100 | 101
60 | v1 heating | 20d | standard - no risk | 99 | 100 | 101
51 | vI electricity | 25d | standard - no risk | 99 | 100 | 101
67 | v1 drying screed | 5d | standard - skewed left | 80 | 110 | 120
57 | v1flooring | 20d | manual - absolute | 128 | 160 | 577
64 | level 2 | 10d | manual - absolute | 0 | 0 | 0
53 | v2 sanitary | 10d | manual - absolute | 99 | 100 | 101
55 | v2 masonry | 10d | manual - absolute | 99 | 100 | 101
56 | v2 screed | 15d | manual - absolute | 80 | 110 | 120
61 | v2 heating | 20d | manual - absolute | 80 | 110 | 120
54 | v2 electricity | 25d | manual - absolute | 99 | 100 | 101
68 | v2 drying screed | 5d | manual - absolute | 80 | 110 | 120
58 | v2 flooring | 20d | manual - absolute | 128 | 160 | 556
65 | completion | 10d | manual - absolute | 0 | 0 | 0
32 | stucco | 15d | manual - absolute | 96 | 120 | 451
36 | drywall | 25d | manual - absolute | 160 | 200 | 528
41 | kitchen and bar | 15d | standard - symmetric | 80 | 100 | 120
37 | techniques | 15d | standard - symmetric | 80 | 100 | 120
44 | stairs | 10d | standard - symmetric | 80 | 100 | 120
42 | entrance doors | 10d | standard - symmetric | 80 | 100 | 120
43 | elevator | 5d | standard - symmetric | 80 | 100 | 120
38 | suspended ceiling | 5d | standard - symmetric | 80 | 100 | 120
39 | painting | 15d | standard - symmetric | 80 | 100 | 120
40 | furniture | 5d | standard - symmetric | 80 | 100 | 120

## Project Control - TP1
| TP Status Date | 2006-07-07 08:00 |  | TP Name | Preparation1
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
2 | building permit | 2006-04-17 08:00 | 2006-07-07 17:00 | 60d |  | 0 | 75 | 0 | 0 | 75 | 2006-04-17 08:00 | 100d | 0 | 0 | 1d | 0 | 0 | 0 | -1 | 99.0099012851715% | Started | 0 | 0
3 | hire contractor | 2006-07-10 08:00 | 2006-08-04 17:00 | 20d |  | 0 | 210000 | 0 | 0 | 210000 | 2958466 | 0 | 0 | 0 | 20d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
4 | temporary offices | 2006-04-17 08:00 | 2006-05-12 17:00 | 20d |  | 0 | 3765.3101 | 0 | 0 | 3765.3101 | 2006-04-17 08:00 | 20d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
5 | temporary facilities | 2006-04-17 08:00 | 2006-07-07 17:00 | 60d |  | 0 | 1876.54 | 0 | 0 | 1876.54 | 2006-04-17 08:00 | 60d | 0 | 0 | 1d | 0 | 0 | 0 | -1 | 98.3606994152069% | Started | 0 | 0
6 | demolition | 2006-10-30 08:00 | 2006-12-08 17:00 | 30d | team VDW[4.0 #8] | 37017.6 | 1070.11 | 0 | 0 | 38087.71 | 2958466 | 0 | 0 | 0 | 30d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
16 | preparation contractor | 2006-08-07 08:00 | 2006-10-27 17:00 | 60d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2958466 | 0 | 0 | 0 | 60d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
17 | excavation | 2006-12-11 08:00 | 2006-12-28 17:00 | 14d | team VDW | 4318.72 | 26000 | 0 | 0 | 30318.72 | 2958466 | 0 | 0 | 0 | 14d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
18 | foundation beam | 2006-12-29 08:00 | 2007-02-01 17:00 | 25d | team VDW[3.0 #8] | 23136 | 98523.7266 | 0 | 0 | 121659.7266 | 2958466 | 0 | 0 | 0 | 25d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
19 | steelframe I | 2007-02-02 08:00 | 2007-03-01 17:00 | 20d | team VDW[4.0 #8] | 24678.4 | 118992.5078 | 0 | 0 | 143670.9078 | 2958466 | 0 | 0 | 0 | 20d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
20 | concrete vaults I | 2007-03-02 08:00 | 2007-03-15 17:00 | 10d | team VDW[4.0 #8] | 12339.2 | 117409.7188 | 0 | 0 | 129748.9187 | 2958466 | 0 | 0 | 0 | 10d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
21 | placing sewerage | 2006-12-29 08:00 | 2007-01-11 17:00 | 10d | team VDW[3.0 #8] | 9254.4 | 1224.73 | 0 | 0 | 10479.13 | 2958466 | 0 | 0 | 0 | 10d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
22 | steelframe II | 2007-03-16 08:00 | 2007-04-05 17:00 | 15d | team VDW[3.0 #8] | 13881.6 | 118992.5078 | 0 | 0 | 132874.1078 | 2958466 | 0 | 0 | 0 | 15d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
23 | foundation plate | 2007-01-12 08:00 | 2007-01-12 17:00 | 1d | team VDW[5.0 #8] | 1542.4 | 234819.4375 | 0 | 0 | 236361.8375 | 2958466 | 0 | 0 | 0 | 1d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
24 | concrete volt II | 2007-04-06 08:00 | 2007-04-26 17:00 | 15d | team VDW[4.0 #8] | 18508.8 | 117409.7188 | 0 | 0 | 135918.5187 | 2958466 | 0 | 0 | 0 | 15d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
25 | facades | 2007-04-27 08:00 | 2007-05-24 17:00 | 20d | team VDW[2.0 #8] | 12339.2 | 339314 | 0 | 0 | 351653.2 | 2958466 | 0 | 0 | 0 | 20d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
26 | outside windows | 2007-05-25 08:00 | 2007-06-07 17:00 | 10d | windows[3.0 #3] | 9120 | 150750.5938 | 0 | 0 | 159870.5938 | 2958466 | 0 | 0 | 0 | 10d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
27 | v0 -masonry | 2007-08-29 10:00 | 2007-09-11 17:00 | 10d | mason | 3252 | 31200.9609 | 40.65 | 3252.0001 | 37704.9611 | 2958466 | 0 | 0 | 0 | 10d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
28 | v0 polierbeton | 2007-06-08 08:00 | 2007-06-21 17:00 | 10d | team VDW[5.0 #8] | 15424 | 134400 | 0 | 0 | 149824 | 2958466 | 0 | 0 | 0 | 10d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
29 | v0 electricity | 2007-08-29 10:00 | 2007-10-02 17:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 | 2958466 | 0 | 0 | 0 | 25d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
30 | v0 sanitary | 2007-08-29 10:00 | 2007-09-11 17:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 | 2958466 | 0 | 0 | 0 | 10d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
31 | construction leave | 2007-08-15 10:00 | 2007-08-28 17:00 | 10d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2958466 | 0 | 0 | 0 | 10d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
32 | stucco | 2007-09-26 10:00 | 2007-10-16 17:00 | 15d | stucco[3.0 #4] | 14896.8 | 8642 | 0 | 0 | 23538.8 | 2958466 | 0 | 0 | 0 | 15d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
34 | v1screed | 2007-08-29 10:00 | 2007-09-18 17:00 | 15d | chapen[2.0 #3] | 0 | 106140 | 0 | 0 | 106140 | 2958466 | 0 | 0 | 0 | 15d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
35 | v0 floors | 2007-10-03 10:00 | 2007-10-30 17:00 | 20d | flooring | 6649.6 | 75000 | 0 | 0 | 81649.6 | 2958466 | 0 | 0 | 0 | 20d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
36 | drywall | 2007-10-24 10:00 | 2007-11-27 17:00 | 25d |  | 0 | 48000 | 0 | 0 | 48000 | 2958466 | 0 | 0 | 0 | 25d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
37 | techniques | 2007-10-31 10:00 | 2007-11-20 17:00 | 15d |  | 0 | 2156.0601 | 0 | 0 | 2156.0601 | 2958466 | 0 | 0 | 0 | 15d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
38 | suspended ceiling | 2007-11-21 10:00 | 2007-11-27 17:00 | 5d |  | 0 | 32000 | 0 | 0 | 32000 | 2958466 | 0 | 0 | 0 | 5d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
39 | painting | 2007-11-28 10:00 | 2007-12-18 17:00 | 15d | painter[4.0 #6] | 16800 | 83000 | 0 | 0 | 99800 | 2958466 | 0 | 0 | 0 | 15d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
40 | furniture | 2007-12-19 10:00 | 2007-12-25 17:00 | 5d | furniture[5.0 #5] | 8400 | 130000 | 0 | 0 | 138400 | 2958466 | 0 | 0 | 0 | 5d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
41 | kitchen and bar | 2007-10-31 10:00 | 2007-11-20 17:00 | 15d |  | 0 | 87000 | 0 | 0 | 87000 | 2958466 | 0 | 0 | 0 | 15d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
42 | entrance doors | 2007-11-21 10:00 | 2007-12-04 17:00 | 10d |  | 0 | 16000 | 0 | 0 | 16000 | 2958466 | 0 | 0 | 0 | 10d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
43 | elevator | 2007-11-21 10:00 | 2007-11-27 17:00 | 5d |  | 0 | 38817.8516 | 0 | 0 | 38817.8516 | 2958466 | 0 | 0 | 0 | 5d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
44 | stairs | 2007-11-21 10:00 | 2007-12-04 17:00 | 10d |  | 0 | 33000 | 0 | 0 | 33000 | 2958466 | 0 | 0 | 0 | 10d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
45 | vI masonry | 2007-08-29 10:00 | 2007-09-11 17:00 | 10d | mason | 3252 | 31200.9609 | 40.65 | 3252.0001 | 37704.9611 | 2958466 | 0 | 0 | 0 | 10d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
49 | roof | 2007-04-27 08:00 | 2007-05-10 17:00 | 10d | roofing[4.0 #4] | 11520 | 70779.5703 | 40.3 | 3223.9999 | 85523.5703 | 2958466 | 0 | 0 | 0 | 10d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
51 | vI electricity | 2007-08-29 10:00 | 2007-10-02 17:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 | 2958466 | 0 | 0 | 0 | 25d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
52 | vI sanitary | 2007-08-29 10:00 | 2007-09-11 17:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 | 2958466 | 0 | 0 | 0 | 10d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
53 | v2 sanitary | 2007-08-29 10:00 | 2007-09-11 17:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 | 2958466 | 0 | 0 | 0 | 10d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
54 | v2 electricity | 2007-08-29 10:00 | 2007-10-02 17:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 | 2958466 | 0 | 0 | 0 | 25d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
55 | v2 masonry | 2007-08-29 10:00 | 2007-09-11 17:00 | 10d | mason | 3252 | 31200.9609 | 0 | 0 | 34452.9609 | 2958466 | 0 | 0 | 0 | 10d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
56 | v2 screed | 2007-08-29 10:00 | 2007-09-18 17:00 | 15d | chapen | 0 | 46116 | 0 | 0 | 46116 | 2958466 | 0 | 0 | 0 | 15d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
57 | v1flooring | 2007-09-26 10:00 | 2007-10-23 17:00 | 20d | flooring | 6649.6 | 72500 | 0 | 0 | 79149.6 | 2958466 | 0 | 0 | 0 | 20d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
58 | v2 flooring | 2007-09-26 10:00 | 2007-10-23 17:00 | 20d | flooring | 6649.6 | 31500 | 0 | 0 | 38149.6 | 2958466 | 0 | 0 | 0 | 20d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
59 | v0 heating | 2007-08-29 10:00 | 2007-09-25 17:00 | 20d | heating | 6912 | 11651 | 0 | 0 | 18563 | 2958466 | 0 | 0 | 0 | 20d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
60 | v1 heating | 2007-08-29 10:00 | 2007-09-25 17:00 | 20d | heating | 6912 | 11651 | 43.2 | 6912.0001 | 25475.0001 | 2958466 | 0 | 0 | 0 | 20d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
61 | v2 heating | 2007-08-29 10:00 | 2007-09-25 17:00 | 20d | electrician | 5120 | 11651 | 0 | 0 | 16771 | 2958466 | 0 | 0 | 0 | 20d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
67 | v1 drying screed | 2007-09-19 10:00 | 2007-09-25 17:00 | 5d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2958466 | 0 | 0 | 0 | 5d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
68 | v2 drying screed | 2007-09-19 10:00 | 2007-09-25 17:00 | 5d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2958466 | 0 | 0 | 0 | 5d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
69 | soil analyses | 2006-12-11 08:00 | 2006-12-12 17:00 | 2d | team VDW | 616.96 | 2000 | 0 | 0 | 2616.96 | 2958466 | 0 | 0 | 0 | 2d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0

## TP2
| TP Status Date | 2007-02-08 08:00 |  | TP Name | Preparation2
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
2 | building permit | 2006-04-17 08:00 | 2006-07-07 17:00 | 60d |  | 0 | 75 | 0 | 0 | 75 | 2006-04-17 08:00 | 100d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
3 | hire contractor | 2006-07-10 08:00 | 2006-08-04 17:00 | 20d |  | 0 | 210000 | 0 | 0 | 210000 | 2006-09-04 08:00 | 30d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
4 | temporary offices | 2006-04-17 08:00 | 2006-05-12 17:00 | 20d |  | 0 | 3765.3101 | 0 | 0 | 3765.3101 | 2006-04-17 08:00 | 20d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
5 | temporary facilities | 2006-04-17 08:00 | 2006-07-07 17:00 | 60d |  | 0 | 1876.54 | 0 | 0 | 1876.54 | 2006-04-17 08:00 | 60d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
6 | demolition | 2006-10-30 08:00 | 2006-12-08 17:00 | 30d | team VDW[4.0 #8] | 37017.6 | 1070.11 | 0 | 0 | 38087.71 | 2006-11-27 08:00 | 54d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
16 | preparation contractor | 2006-08-07 08:00 | 2006-10-27 17:00 | 60d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2006-09-04 08:00 | 60d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
17 | excavation | 2006-12-11 08:00 | 2006-12-28 17:00 | 14d | team VDW | 4318.72 | 26000 | 0 | 0 | 30318.72 | 2958466 | 0 | 0 | 0 | 14d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
18 | foundation beam | 2006-12-29 08:00 | 2007-02-01 17:00 | 25d | team VDW[3.0 #8] | 23136 | 98523.7266 | 0 | 0 | 121659.7266 | 2958466 | 0 | 0 | 0 | 25d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
19 | steelframe I | 2007-02-02 08:00 | 2007-03-01 17:00 | 20d | team VDW[4.0 #8] | 24678.4 | 118992.5078 | 0 | 0 | 143670.9078 | 2958466 | 0 | 0 | 0 | 20d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
20 | concrete vaults I | 2007-03-02 08:00 | 2007-03-15 17:00 | 10d | team VDW[4.0 #8] | 12339.2 | 117409.7188 | 0 | 0 | 129748.9187 | 2958466 | 0 | 0 | 0 | 10d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
21 | placing sewerage | 2006-12-29 08:00 | 2007-01-11 17:00 | 10d | team VDW[3.0 #8] | 9254.4 | 1224.73 | 0 | 0 | 10479.13 | 2958466 | 0 | 0 | 0 | 10d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
22 | steelframe II | 2007-03-16 08:00 | 2007-04-05 17:00 | 15d | team VDW[3.0 #8] | 13881.6 | 118992.5078 | 0 | 0 | 132874.1078 | 2958466 | 0 | 0 | 0 | 15d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
23 | foundation plate | 2007-01-12 08:00 | 2007-01-12 17:00 | 1d | team VDW[5.0 #8] | 1542.4 | 234819.4375 | 0 | 0 | 236361.8375 | 2958466 | 0 | 0 | 0 | 1d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
24 | concrete volt II | 2007-04-06 08:00 | 2007-04-26 17:00 | 15d | team VDW[4.0 #8] | 18508.8 | 117409.7188 | 0 | 0 | 135918.5187 | 2958466 | 0 | 0 | 0 | 15d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
25 | facades | 2007-04-27 08:00 | 2007-05-24 17:00 | 20d | team VDW[2.0 #8] | 12339.2 | 339314 | 0 | 0 | 351653.2 | 2958466 | 0 | 0 | 0 | 20d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
26 | outside windows | 2007-05-25 08:00 | 2007-06-07 17:00 | 10d | windows[3.0 #3] | 9120 | 150750.5938 | 0 | 0 | 159870.5938 | 2958466 | 0 | 0 | 0 | 10d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
27 | v0 -masonry | 2007-08-29 10:00 | 2007-09-11 17:00 | 10d | mason | 3252 | 31200.9609 | 40.65 | 3252.0001 | 37704.9611 | 2958466 | 0 | 0 | 0 | 10d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
28 | v0 polierbeton | 2007-06-08 08:00 | 2007-06-21 17:00 | 10d | team VDW[5.0 #8] | 15424 | 134400 | 0 | 0 | 149824 | 2958466 | 0 | 0 | 0 | 10d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
29 | v0 electricity | 2007-08-29 10:00 | 2007-10-02 17:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 | 2958466 | 0 | 0 | 0 | 25d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
30 | v0 sanitary | 2007-08-29 10:00 | 2007-09-11 17:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 | 2958466 | 0 | 0 | 0 | 10d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
31 | construction leave | 2007-08-15 10:00 | 2007-08-28 17:00 | 10d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2958466 | 0 | 0 | 0 | 10d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
32 | stucco | 2007-09-26 10:00 | 2007-10-16 17:00 | 15d | stucco[3.0 #4] | 14896.8 | 8642 | 0 | 0 | 23538.8 | 2958466 | 0 | 0 | 0 | 15d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
34 | v1screed | 2007-08-29 10:00 | 2007-09-18 17:00 | 15d | chapen[2.0 #3] | 0 | 106140 | 0 | 0 | 106140 | 2958466 | 0 | 0 | 0 | 15d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
35 | v0 floors | 2007-10-03 10:00 | 2007-10-30 17:00 | 20d | flooring | 6649.6 | 75000 | 0 | 0 | 81649.6 | 2958466 | 0 | 0 | 0 | 20d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
36 | drywall | 2007-10-24 10:00 | 2007-11-27 17:00 | 25d |  | 0 | 48000 | 0 | 0 | 48000 | 2958466 | 0 | 0 | 0 | 25d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
37 | techniques | 2007-10-31 10:00 | 2007-11-20 17:00 | 15d |  | 0 | 2156.0601 | 0 | 0 | 2156.0601 | 2958466 | 0 | 0 | 0 | 15d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
38 | suspended ceiling | 2007-11-21 10:00 | 2007-11-27 17:00 | 5d |  | 0 | 32000 | 0 | 0 | 32000 | 2958466 | 0 | 0 | 0 | 5d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
39 | painting | 2007-11-28 10:00 | 2007-12-18 17:00 | 15d | painter[4.0 #6] | 16800 | 83000 | 0 | 0 | 99800 | 2958466 | 0 | 0 | 0 | 15d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
40 | furniture | 2007-12-19 10:00 | 2007-12-25 17:00 | 5d | furniture[5.0 #5] | 8400 | 130000 | 0 | 0 | 138400 | 2958466 | 0 | 0 | 0 | 5d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
41 | kitchen and bar | 2007-10-31 10:00 | 2007-11-20 17:00 | 15d |  | 0 | 87000 | 0 | 0 | 87000 | 2958466 | 0 | 0 | 0 | 15d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
42 | entrance doors | 2007-11-21 10:00 | 2007-12-04 17:00 | 10d |  | 0 | 16000 | 0 | 0 | 16000 | 2958466 | 0 | 0 | 0 | 10d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
43 | elevator | 2007-11-21 10:00 | 2007-11-27 17:00 | 5d |  | 0 | 38817.8516 | 0 | 0 | 38817.8516 | 2958466 | 0 | 0 | 0 | 5d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
44 | stairs | 2007-11-21 10:00 | 2007-12-04 17:00 | 10d |  | 0 | 33000 | 0 | 0 | 33000 | 2958466 | 0 | 0 | 0 | 10d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
45 | vI masonry | 2007-08-29 10:00 | 2007-09-11 17:00 | 10d | mason | 3252 | 31200.9609 | 40.65 | 3252.0001 | 37704.9611 | 2958466 | 0 | 0 | 0 | 10d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
49 | roof | 2007-04-27 08:00 | 2007-05-10 17:00 | 10d | roofing[4.0 #4] | 11520 | 70779.5703 | 40.3 | 3223.9999 | 85523.5703 | 2958466 | 0 | 0 | 0 | 10d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
51 | vI electricity | 2007-08-29 10:00 | 2007-10-02 17:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 | 2958466 | 0 | 0 | 0 | 25d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
52 | vI sanitary | 2007-08-29 10:00 | 2007-09-11 17:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 | 2958466 | 0 | 0 | 0 | 10d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
53 | v2 sanitary | 2007-08-29 10:00 | 2007-09-11 17:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 | 2958466 | 0 | 0 | 0 | 10d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
54 | v2 electricity | 2007-08-29 10:00 | 2007-10-02 17:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 | 2958466 | 0 | 0 | 0 | 25d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
55 | v2 masonry | 2007-08-29 10:00 | 2007-09-11 17:00 | 10d | mason | 3252 | 31200.9609 | 0 | 0 | 34452.9609 | 2958466 | 0 | 0 | 0 | 10d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
56 | v2 screed | 2007-08-29 10:00 | 2007-09-18 17:00 | 15d | chapen | 0 | 46116 | 0 | 0 | 46116 | 2958466 | 0 | 0 | 0 | 15d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
57 | v1flooring | 2007-09-26 10:00 | 2007-10-23 17:00 | 20d | flooring | 6649.6 | 72500 | 0 | 0 | 79149.6 | 2958466 | 0 | 0 | 0 | 20d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
58 | v2 flooring | 2007-09-26 10:00 | 2007-10-23 17:00 | 20d | flooring | 6649.6 | 31500 | 0 | 0 | 38149.6 | 2958466 | 0 | 0 | 0 | 20d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
59 | v0 heating | 2007-08-29 10:00 | 2007-09-25 17:00 | 20d | heating | 6912 | 11651 | 0 | 0 | 18563 | 2958466 | 0 | 0 | 0 | 20d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
60 | v1 heating | 2007-08-29 10:00 | 2007-09-25 17:00 | 20d | heating | 6912 | 11651 | 43.2 | 6912.0001 | 25475.0001 | 2958466 | 0 | 0 | 0 | 20d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
61 | v2 heating | 2007-08-29 10:00 | 2007-09-25 17:00 | 20d | electrician | 5120 | 11651 | 0 | 0 | 16771 | 2958466 | 0 | 0 | 0 | 20d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
67 | v1 drying screed | 2007-09-19 10:00 | 2007-09-25 17:00 | 5d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2958466 | 0 | 0 | 0 | 5d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
68 | v2 drying screed | 2007-09-19 10:00 | 2007-09-25 17:00 | 5d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2958466 | 0 | 0 | 0 | 5d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
69 | soil analyses | 2006-12-11 08:00 | 2006-12-12 17:00 | 2d | team VDW | 616.96 | 2000 | 0 | 0 | 2616.96 | 2958466 | 0 | 0 | 0 | 2d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0

## TP3
| TP Status Date | 2007-03-17 08:00 |  | TP Name | Foundation
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
2 | building permit | 2006-04-17 08:00 | 2006-07-07 17:00 | 60d |  | 0 | 75 | 0 | 0 | 75 | 2006-04-17 08:00 | 100d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
3 | hire contractor | 2006-07-10 08:00 | 2006-08-04 17:00 | 20d |  | 0 | 210000 | 0 | 0 | 210000 | 2006-09-04 08:00 | 30d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
4 | temporary offices | 2006-04-17 08:00 | 2006-05-12 17:00 | 20d |  | 0 | 3765.3101 | 0 | 0 | 3765.3101 | 2006-04-17 08:00 | 20d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
5 | temporary facilities | 2006-04-17 08:00 | 2006-07-07 17:00 | 60d |  | 0 | 1876.54 | 0 | 0 | 1876.54 | 2006-04-17 08:00 | 60d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
6 | demolition | 2006-10-30 08:00 | 2006-12-08 17:00 | 30d | team VDW[4.0 #8] | 37017.6 | 1070.11 | 0 | 0 | 38087.71 | 2006-11-27 08:00 | 54d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
16 | preparation contractor | 2006-08-07 08:00 | 2006-10-27 17:00 | 60d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2006-09-04 08:00 | 60d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
17 | excavation | 2006-12-11 08:00 | 2006-12-28 17:00 | 14d | team VDW | 4318.72 | 26000 | 0 | 0 | 30318.72 | 2007-02-08 08:00 | 10d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
18 | foundation beam | 2006-12-29 08:00 | 2007-02-01 17:00 | 25d | team VDW[3.0 #8] | 23136 | 98523.7266 | 0 | 0 | 121659.7266 | 2007-02-28 08:00 | 22d | 0 | 0 | 12d | 0 | 0 | 0 | -1 | 64.705902338028% | Started | 0 | 0
19 | steelframe I | 2007-02-02 08:00 | 2007-03-01 17:00 | 20d | team VDW[4.0 #8] | 24678.4 | 118992.5078 | 0 | 0 | 143670.9078 | 2958466 | 0 | 0 | 0 | 20d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
20 | concrete vaults I | 2007-03-02 08:00 | 2007-03-15 17:00 | 10d | team VDW[4.0 #8] | 12339.2 | 117409.7188 | 0 | 0 | 129748.9187 | 2958466 | 0 | 0 | 0 | 10d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
21 | placing sewerage | 2006-12-29 08:00 | 2007-01-11 17:00 | 10d | team VDW[3.0 #8] | 9254.4 | 1224.73 | 0 | 0 | 10479.13 | 2007-02-28 08:00 | 12d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
22 | steelframe II | 2007-03-16 08:00 | 2007-04-05 17:00 | 15d | team VDW[3.0 #8] | 13881.6 | 118992.5078 | 0 | 0 | 132874.1078 | 2958466 | 0 | 0 | 0 | 15d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
23 | foundation plate | 2007-01-12 08:00 | 2007-01-12 17:00 | 1d | team VDW[5.0 #8] | 1542.4 | 234819.4375 | 0 | 0 | 236361.8375 | 2007-03-16 08:00 | 1d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
24 | concrete volt II | 2007-04-06 08:00 | 2007-04-26 17:00 | 15d | team VDW[4.0 #8] | 18508.8 | 117409.7188 | 0 | 0 | 135918.5187 | 2958466 | 0 | 0 | 0 | 15d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
25 | facades | 2007-04-27 08:00 | 2007-05-24 17:00 | 20d | team VDW[2.0 #8] | 12339.2 | 339314 | 0 | 0 | 351653.2 | 2958466 | 0 | 0 | 0 | 20d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
26 | outside windows | 2007-05-25 08:00 | 2007-06-07 17:00 | 10d | windows[3.0 #3] | 9120 | 150750.5938 | 0 | 0 | 159870.5938 | 2958466 | 0 | 0 | 0 | 10d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
27 | v0 -masonry | 2007-08-29 10:00 | 2007-09-11 17:00 | 10d | mason | 3252 | 31200.9609 | 40.65 | 3252.0001 | 37704.9611 | 2958466 | 0 | 0 | 0 | 10d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
28 | v0 polierbeton | 2007-06-08 08:00 | 2007-06-21 17:00 | 10d | team VDW[5.0 #8] | 15424 | 134400 | 0 | 0 | 149824 | 2958466 | 0 | 0 | 0 | 10d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
29 | v0 electricity | 2007-08-29 10:00 | 2007-10-02 17:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 | 2958466 | 0 | 0 | 0 | 25d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
30 | v0 sanitary | 2007-08-29 10:00 | 2007-09-11 17:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 | 2958466 | 0 | 0 | 0 | 10d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
31 | construction leave | 2007-08-15 10:00 | 2007-08-28 17:00 | 10d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2958466 | 0 | 0 | 0 | 10d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
32 | stucco | 2007-09-26 10:00 | 2007-10-16 17:00 | 15d | stucco[3.0 #4] | 14896.8 | 8642 | 0 | 0 | 23538.8 | 2958466 | 0 | 0 | 0 | 15d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
34 | v1screed | 2007-08-29 10:00 | 2007-09-18 17:00 | 15d | chapen[2.0 #3] | 0 | 106140 | 0 | 0 | 106140 | 2958466 | 0 | 0 | 0 | 15d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
35 | v0 floors | 2007-10-03 10:00 | 2007-10-30 17:00 | 20d | flooring | 6649.6 | 75000 | 0 | 0 | 81649.6 | 2958466 | 0 | 0 | 0 | 20d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
36 | drywall | 2007-10-24 10:00 | 2007-11-27 17:00 | 25d |  | 0 | 48000 | 0 | 0 | 48000 | 2958466 | 0 | 0 | 0 | 25d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
37 | techniques | 2007-10-31 10:00 | 2007-11-20 17:00 | 15d |  | 0 | 2156.0601 | 0 | 0 | 2156.0601 | 2958466 | 0 | 0 | 0 | 15d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
38 | suspended ceiling | 2007-11-21 10:00 | 2007-11-27 17:00 | 5d |  | 0 | 32000 | 0 | 0 | 32000 | 2958466 | 0 | 0 | 0 | 5d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
39 | painting | 2007-11-28 10:00 | 2007-12-18 17:00 | 15d | painter[4.0 #6] | 16800 | 83000 | 0 | 0 | 99800 | 2958466 | 0 | 0 | 0 | 15d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
40 | furniture | 2007-12-19 10:00 | 2007-12-25 17:00 | 5d | furniture[5.0 #5] | 8400 | 130000 | 0 | 0 | 138400 | 2958466 | 0 | 0 | 0 | 5d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
41 | kitchen and bar | 2007-10-31 10:00 | 2007-11-20 17:00 | 15d |  | 0 | 87000 | 0 | 0 | 87000 | 2958466 | 0 | 0 | 0 | 15d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
42 | entrance doors | 2007-11-21 10:00 | 2007-12-04 17:00 | 10d |  | 0 | 16000 | 0 | 0 | 16000 | 2958466 | 0 | 0 | 0 | 10d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
43 | elevator | 2007-11-21 10:00 | 2007-11-27 17:00 | 5d |  | 0 | 38817.8516 | 0 | 0 | 38817.8516 | 2958466 | 0 | 0 | 0 | 5d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
44 | stairs | 2007-11-21 10:00 | 2007-12-04 17:00 | 10d |  | 0 | 33000 | 0 | 0 | 33000 | 2958466 | 0 | 0 | 0 | 10d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
45 | vI masonry | 2007-08-29 10:00 | 2007-09-11 17:00 | 10d | mason | 3252 | 31200.9609 | 40.65 | 3252.0001 | 37704.9611 | 2958466 | 0 | 0 | 0 | 10d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
49 | roof | 2007-04-27 08:00 | 2007-05-10 17:00 | 10d | roofing[4.0 #4] | 11520 | 70779.5703 | 40.3 | 3223.9999 | 85523.5703 | 2958466 | 0 | 0 | 0 | 10d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
51 | vI electricity | 2007-08-29 10:00 | 2007-10-02 17:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 | 2958466 | 0 | 0 | 0 | 25d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
52 | vI sanitary | 2007-08-29 10:00 | 2007-09-11 17:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 | 2958466 | 0 | 0 | 0 | 10d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
53 | v2 sanitary | 2007-08-29 10:00 | 2007-09-11 17:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 | 2958466 | 0 | 0 | 0 | 10d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
54 | v2 electricity | 2007-08-29 10:00 | 2007-10-02 17:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 | 2958466 | 0 | 0 | 0 | 25d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
55 | v2 masonry | 2007-08-29 10:00 | 2007-09-11 17:00 | 10d | mason | 3252 | 31200.9609 | 0 | 0 | 34452.9609 | 2958466 | 0 | 0 | 0 | 10d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
56 | v2 screed | 2007-08-29 10:00 | 2007-09-18 17:00 | 15d | chapen | 0 | 46116 | 0 | 0 | 46116 | 2958466 | 0 | 0 | 0 | 15d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
57 | v1flooring | 2007-09-26 10:00 | 2007-10-23 17:00 | 20d | flooring | 6649.6 | 72500 | 0 | 0 | 79149.6 | 2958466 | 0 | 0 | 0 | 20d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
58 | v2 flooring | 2007-09-26 10:00 | 2007-10-23 17:00 | 20d | flooring | 6649.6 | 31500 | 0 | 0 | 38149.6 | 2958466 | 0 | 0 | 0 | 20d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
59 | v0 heating | 2007-08-29 10:00 | 2007-09-25 17:00 | 20d | heating | 6912 | 11651 | 0 | 0 | 18563 | 2958466 | 0 | 0 | 0 | 20d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
60 | v1 heating | 2007-08-29 10:00 | 2007-09-25 17:00 | 20d | heating | 6912 | 11651 | 43.2 | 6912.0001 | 25475.0001 | 2958466 | 0 | 0 | 0 | 20d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
61 | v2 heating | 2007-08-29 10:00 | 2007-09-25 17:00 | 20d | electrician | 5120 | 11651 | 0 | 0 | 16771 | 2958466 | 0 | 0 | 0 | 20d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
67 | v1 drying screed | 2007-09-19 10:00 | 2007-09-25 17:00 | 5d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2958466 | 0 | 0 | 0 | 5d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
68 | v2 drying screed | 2007-09-19 10:00 | 2007-09-25 17:00 | 5d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2958466 | 0 | 0 | 0 | 5d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
69 | soil analyses | 2006-12-11 08:00 | 2006-12-12 17:00 | 2d | team VDW | 616.96 | 2000 | 0 | 0 | 2616.96 | 2007-02-08 08:00 | 12d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0

## TP4
| TP Status Date | 2007-06-04 08:00 |  | TP Name | Shell
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
2 | building permit | 2006-04-17 08:00 | 2006-07-07 17:00 | 60d |  | 0 | 75 | 0 | 0 | 75 | 2006-04-17 08:00 | 100d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
3 | hire contractor | 2006-07-10 08:00 | 2006-08-04 17:00 | 20d |  | 0 | 210000 | 0 | 0 | 210000 | 2006-09-04 08:00 | 30d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
4 | temporary offices | 2006-04-17 08:00 | 2006-05-12 17:00 | 20d |  | 0 | 3765.3101 | 0 | 0 | 3765.3101 | 2006-04-17 08:00 | 20d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
5 | temporary facilities | 2006-04-17 08:00 | 2006-07-07 17:00 | 60d |  | 0 | 1876.54 | 0 | 0 | 1876.54 | 2006-04-17 08:00 | 60d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
6 | demolition | 2006-10-30 08:00 | 2006-12-08 17:00 | 30d | team VDW[4.0 #8] | 37017.6 | 1070.11 | 0 | 0 | 38087.71 | 2006-11-27 08:00 | 54d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
16 | preparation contractor | 2006-08-07 08:00 | 2006-10-27 17:00 | 60d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2006-09-04 08:00 | 60d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
17 | excavation | 2006-12-11 08:00 | 2006-12-28 17:00 | 14d | team VDW | 4318.72 | 26000 | 0 | 0 | 30318.72 | 2007-02-08 08:00 | 10d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
18 | foundation beam | 2006-12-29 08:00 | 2007-02-01 17:00 | 25d | team VDW[3.0 #8] | 23136 | 98523.7266 | 0 | 0 | 121659.7266 | 2007-02-28 08:00 | 22d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
19 | steelframe I | 2007-02-02 08:00 | 2007-03-01 17:00 | 20d | team VDW[4.0 #8] | 24678.4 | 118992.5078 | 0 | 0 | 143670.9078 | 2007-04-02 08:00 | 15d | 0 | 0 | 19d 21h | 0 | 0 | 0 | -1 | 43.010801076889% | Started | 0 | 0
20 | concrete vaults I | 2007-03-02 08:00 | 2007-03-15 17:00 | 10d | team VDW[4.0 #8] | 12339.2 | 117409.7188 | 0 | 0 | 129748.9187 | 2007-04-23 08:00 | 5d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
21 | placing sewerage | 2006-12-29 08:00 | 2007-01-11 17:00 | 10d | team VDW[3.0 #8] | 9254.4 | 1224.73 | 0 | 0 | 10479.13 | 2007-02-28 08:00 | 12d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
22 | steelframe II | 2007-03-16 08:00 | 2007-04-05 17:00 | 15d | team VDW[3.0 #8] | 13881.6 | 118992.5078 | 0 | 0 | 132874.1078 | 2007-04-30 08:00 | 15d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
23 | foundation plate | 2007-01-12 08:00 | 2007-01-12 17:00 | 1d | team VDW[5.0 #8] | 1542.4 | 234819.4375 | 0 | 0 | 236361.8375 | 2007-03-16 08:00 | 1d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
24 | concrete volt II | 2007-04-06 08:00 | 2007-04-26 17:00 | 15d | team VDW[4.0 #8] | 18508.8 | 117409.7188 | 0 | 0 | 135918.5187 | 2007-05-21 08:00 | 10d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
25 | facades | 2007-04-27 08:00 | 2007-05-24 17:00 | 20d | team VDW[2.0 #8] | 12339.2 | 339314 | 0 | 0 | 351653.2 | 2958466 | 0 | 0 | 0 | 20d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
26 | outside windows | 2007-05-25 08:00 | 2007-06-07 17:00 | 10d | windows[3.0 #3] | 9120 | 150750.5938 | 0 | 0 | 159870.5938 | 2958466 | 0 | 0 | 0 | 10d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
27 | v0 -masonry | 2007-08-29 10:00 | 2007-09-11 17:00 | 10d | mason | 3252 | 31200.9609 | 40.65 | 3252.0001 | 37704.9611 | 2958466 | 0 | 0 | 0 | 10d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
28 | v0 polierbeton | 2007-06-08 08:00 | 2007-06-21 17:00 | 10d | team VDW[5.0 #8] | 15424 | 134400 | 0 | 0 | 149824 | 2958466 | 0 | 0 | 0 | 10d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
29 | v0 electricity | 2007-08-29 10:00 | 2007-10-02 17:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 | 2958466 | 0 | 0 | 0 | 25d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
30 | v0 sanitary | 2007-08-29 10:00 | 2007-09-11 17:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 | 2958466 | 0 | 0 | 0 | 10d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
31 | construction leave | 2007-08-15 10:00 | 2007-08-28 17:00 | 10d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2958466 | 0 | 0 | 0 | 10d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
32 | stucco | 2007-09-26 10:00 | 2007-10-16 17:00 | 15d | stucco[3.0 #4] | 14896.8 | 8642 | 0 | 0 | 23538.8 | 2958466 | 0 | 0 | 0 | 15d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
34 | v1screed | 2007-08-29 10:00 | 2007-09-18 17:00 | 15d | chapen[2.0 #3] | 0 | 106140 | 0 | 0 | 106140 | 2958466 | 0 | 0 | 0 | 15d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
35 | v0 floors | 2007-10-03 10:00 | 2007-10-30 17:00 | 20d | flooring | 6649.6 | 75000 | 0 | 0 | 81649.6 | 2958466 | 0 | 0 | 0 | 20d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
36 | drywall | 2007-10-24 10:00 | 2007-11-27 17:00 | 25d |  | 0 | 48000 | 0 | 0 | 48000 | 2958466 | 0 | 0 | 0 | 25d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
37 | techniques | 2007-10-31 10:00 | 2007-11-20 17:00 | 15d |  | 0 | 2156.0601 | 0 | 0 | 2156.0601 | 2958466 | 0 | 0 | 0 | 15d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
38 | suspended ceiling | 2007-11-21 10:00 | 2007-11-27 17:00 | 5d |  | 0 | 32000 | 0 | 0 | 32000 | 2958466 | 0 | 0 | 0 | 5d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
39 | painting | 2007-11-28 10:00 | 2007-12-18 17:00 | 15d | painter[4.0 #6] | 16800 | 83000 | 0 | 0 | 99800 | 2958466 | 0 | 0 | 0 | 15d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
40 | furniture | 2007-12-19 10:00 | 2007-12-25 17:00 | 5d | furniture[5.0 #5] | 8400 | 130000 | 0 | 0 | 138400 | 2958466 | 0 | 0 | 0 | 5d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
41 | kitchen and bar | 2007-10-31 10:00 | 2007-11-20 17:00 | 15d |  | 0 | 87000 | 0 | 0 | 87000 | 2958466 | 0 | 0 | 0 | 15d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
42 | entrance doors | 2007-11-21 10:00 | 2007-12-04 17:00 | 10d |  | 0 | 16000 | 0 | 0 | 16000 | 2958466 | 0 | 0 | 0 | 10d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
43 | elevator | 2007-11-21 10:00 | 2007-11-27 17:00 | 5d |  | 0 | 38817.8516 | 0 | 0 | 38817.8516 | 2958466 | 0 | 0 | 0 | 5d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
44 | stairs | 2007-11-21 10:00 | 2007-12-04 17:00 | 10d |  | 0 | 33000 | 0 | 0 | 33000 | 2958466 | 0 | 0 | 0 | 10d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
45 | vI masonry | 2007-08-29 10:00 | 2007-09-11 17:00 | 10d | mason | 3252 | 31200.9609 | 40.65 | 3252.0001 | 37704.9611 | 2958466 | 0 | 0 | 0 | 10d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
49 | roof | 2007-04-27 08:00 | 2007-05-10 17:00 | 10d | roofing[4.0 #4] | 11520 | 70779.5703 | 40.3 | 3223.9999 | 85523.5703 | 2958466 | 0 | 0 | 0 | 10d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
51 | vI electricity | 2007-08-29 10:00 | 2007-10-02 17:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 | 2958466 | 0 | 0 | 0 | 25d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
52 | vI sanitary | 2007-08-29 10:00 | 2007-09-11 17:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 | 2958466 | 0 | 0 | 0 | 10d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
53 | v2 sanitary | 2007-08-29 10:00 | 2007-09-11 17:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 | 2958466 | 0 | 0 | 0 | 10d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
54 | v2 electricity | 2007-08-29 10:00 | 2007-10-02 17:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 | 2958466 | 0 | 0 | 0 | 25d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
55 | v2 masonry | 2007-08-29 10:00 | 2007-09-11 17:00 | 10d | mason | 3252 | 31200.9609 | 0 | 0 | 34452.9609 | 2958466 | 0 | 0 | 0 | 10d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
56 | v2 screed | 2007-08-29 10:00 | 2007-09-18 17:00 | 15d | chapen | 0 | 46116 | 0 | 0 | 46116 | 2958466 | 0 | 0 | 0 | 15d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
57 | v1flooring | 2007-09-26 10:00 | 2007-10-23 17:00 | 20d | flooring | 6649.6 | 72500 | 0 | 0 | 79149.6 | 2958466 | 0 | 0 | 0 | 20d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
58 | v2 flooring | 2007-09-26 10:00 | 2007-10-23 17:00 | 20d | flooring | 6649.6 | 31500 | 0 | 0 | 38149.6 | 2958466 | 0 | 0 | 0 | 20d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
59 | v0 heating | 2007-08-29 10:00 | 2007-09-25 17:00 | 20d | heating | 6912 | 11651 | 0 | 0 | 18563 | 2958466 | 0 | 0 | 0 | 20d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
60 | v1 heating | 2007-08-29 10:00 | 2007-09-25 17:00 | 20d | heating | 6912 | 11651 | 43.2 | 6912.0001 | 25475.0001 | 2958466 | 0 | 0 | 0 | 20d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
61 | v2 heating | 2007-08-29 10:00 | 2007-09-25 17:00 | 20d | electrician | 5120 | 11651 | 0 | 0 | 16771 | 2958466 | 0 | 0 | 0 | 20d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
67 | v1 drying screed | 2007-09-19 10:00 | 2007-09-25 17:00 | 5d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2958466 | 0 | 0 | 0 | 5d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
68 | v2 drying screed | 2007-09-19 10:00 | 2007-09-25 17:00 | 5d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2958466 | 0 | 0 | 0 | 5d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
69 | soil analyses | 2006-12-11 08:00 | 2006-12-12 17:00 | 2d | team VDW | 616.96 | 2000 | 0 | 0 | 2616.96 | 2007-02-08 08:00 | 12d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0

## TP5
| TP Status Date | 2007-07-02 08:00 |  | TP Name | Wind&Waterproof
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
2 | building permit | 2006-04-17 08:00 | 2006-07-07 17:00 | 60d |  | 0 | 75 | 0 | 0 | 75 | 2006-04-17 08:00 | 100d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
3 | hire contractor | 2006-07-10 08:00 | 2006-08-04 17:00 | 20d |  | 0 | 210000 | 0 | 0 | 210000 | 2006-09-04 08:00 | 30d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
4 | temporary offices | 2006-04-17 08:00 | 2006-05-12 17:00 | 20d |  | 0 | 3765.3101 | 0 | 0 | 3765.3101 | 2006-04-17 08:00 | 20d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
5 | temporary facilities | 2006-04-17 08:00 | 2006-07-07 17:00 | 60d |  | 0 | 1876.54 | 0 | 0 | 1876.54 | 2006-04-17 08:00 | 60d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
6 | demolition | 2006-10-30 08:00 | 2006-12-08 17:00 | 30d | team VDW[4.0 #8] | 37017.6 | 1070.11 | 0 | 0 | 38087.71 | 2006-11-27 08:00 | 54d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
16 | preparation contractor | 2006-08-07 08:00 | 2006-10-27 17:00 | 60d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2006-09-04 08:00 | 60d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
17 | excavation | 2006-12-11 08:00 | 2006-12-28 17:00 | 14d | team VDW | 4318.72 | 26000 | 0 | 0 | 30318.72 | 2007-02-08 08:00 | 10d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
18 | foundation beam | 2006-12-29 08:00 | 2007-02-01 17:00 | 25d | team VDW[3.0 #8] | 23136 | 98523.7266 | 0 | 0 | 121659.7266 | 2007-02-28 08:00 | 22d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
19 | steelframe I | 2007-02-02 08:00 | 2007-03-01 17:00 | 20d | team VDW[4.0 #8] | 24678.4 | 118992.5078 | 0 | 0 | 143670.9078 | 2007-04-02 08:00 | 15d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
20 | concrete vaults I | 2007-03-02 08:00 | 2007-03-15 17:00 | 10d | team VDW[4.0 #8] | 12339.2 | 117409.7188 | 0 | 0 | 129748.9187 | 2007-04-23 08:00 | 5d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
21 | placing sewerage | 2006-12-29 08:00 | 2007-01-11 17:00 | 10d | team VDW[3.0 #8] | 9254.4 | 1224.73 | 0 | 0 | 10479.13 | 2007-02-28 08:00 | 12d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
22 | steelframe II | 2007-03-16 08:00 | 2007-04-05 17:00 | 15d | team VDW[3.0 #8] | 13881.6 | 118992.5078 | 0 | 0 | 132874.1078 | 2007-04-30 08:00 | 15d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
23 | foundation plate | 2007-01-12 08:00 | 2007-01-12 17:00 | 1d | team VDW[5.0 #8] | 1542.4 | 234819.4375 | 0 | 0 | 236361.8375 | 2007-03-16 08:00 | 1d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
24 | concrete volt II | 2007-04-06 08:00 | 2007-04-26 17:00 | 15d | team VDW[4.0 #8] | 18508.8 | 117409.7188 | 0 | 0 | 135918.5187 | 2007-05-21 08:00 | 10d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
25 | facades | 2007-04-27 08:00 | 2007-05-24 17:00 | 20d | team VDW[2.0 #8] | 12339.2 | 339314 | 0 | 0 | 351653.2 | 2007-06-04 08:00 | 20d | 0 | 0 | 8d | 0 | 0 | 0 | -1 | 71.42857313156131% | Started | 0 | 0
26 | outside windows | 2007-05-25 08:00 | 2007-06-07 17:00 | 10d | windows[3.0 #3] | 9120 | 150750.5938 | 0 | 0 | 159870.5938 | 2007-07-02 08:00 | 92d | 0 | 0 | 9d 21h | 0 | 0 | 0 | -1 | 90.30674695968631% | Started | 0 | 0
27 | v0 -masonry | 2007-08-29 10:00 | 2007-09-11 17:00 | 10d | mason | 3252 | 31200.9609 | 40.65 | 3252.0001 | 37704.9611 | 2958466 | 0 | 0 | 0 | 10d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
28 | v0 polierbeton | 2007-06-08 08:00 | 2007-06-21 17:00 | 10d | team VDW[5.0 #8] | 15424 | 134400 | 0 | 0 | 149824 | 2958466 | 0 | 0 | 0 | 10d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
29 | v0 electricity | 2007-08-29 10:00 | 2007-10-02 17:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 | 2958466 | 0 | 0 | 0 | 25d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
30 | v0 sanitary | 2007-08-29 10:00 | 2007-09-11 17:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 | 2958466 | 0 | 0 | 0 | 10d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
31 | construction leave | 2007-08-15 10:00 | 2007-08-28 17:00 | 10d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2958466 | 0 | 0 | 0 | 10d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
32 | stucco | 2007-09-26 10:00 | 2007-10-16 17:00 | 15d | stucco[3.0 #4] | 14896.8 | 8642 | 0 | 0 | 23538.8 | 2958466 | 0 | 0 | 0 | 15d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
34 | v1screed | 2007-08-29 10:00 | 2007-09-18 17:00 | 15d | chapen[2.0 #3] | 0 | 106140 | 0 | 0 | 106140 | 2958466 | 0 | 0 | 0 | 15d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
35 | v0 floors | 2007-10-03 10:00 | 2007-10-30 17:00 | 20d | flooring | 6649.6 | 75000 | 0 | 0 | 81649.6 | 2958466 | 0 | 0 | 0 | 20d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
36 | drywall | 2007-10-24 10:00 | 2007-11-27 17:00 | 25d |  | 0 | 48000 | 0 | 0 | 48000 | 2958466 | 0 | 0 | 0 | 25d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
37 | techniques | 2007-10-31 10:00 | 2007-11-20 17:00 | 15d |  | 0 | 2156.0601 | 0 | 0 | 2156.0601 | 2958466 | 0 | 0 | 0 | 15d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
38 | suspended ceiling | 2007-11-21 10:00 | 2007-11-27 17:00 | 5d |  | 0 | 32000 | 0 | 0 | 32000 | 2958466 | 0 | 0 | 0 | 5d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
39 | painting | 2007-11-28 10:00 | 2007-12-18 17:00 | 15d | painter[4.0 #6] | 16800 | 83000 | 0 | 0 | 99800 | 2958466 | 0 | 0 | 0 | 15d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
40 | furniture | 2007-12-19 10:00 | 2007-12-25 17:00 | 5d | furniture[5.0 #5] | 8400 | 130000 | 0 | 0 | 138400 | 2958466 | 0 | 0 | 0 | 5d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
41 | kitchen and bar | 2007-10-31 10:00 | 2007-11-20 17:00 | 15d |  | 0 | 87000 | 0 | 0 | 87000 | 2958466 | 0 | 0 | 0 | 15d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
42 | entrance doors | 2007-11-21 10:00 | 2007-12-04 17:00 | 10d |  | 0 | 16000 | 0 | 0 | 16000 | 2958466 | 0 | 0 | 0 | 10d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
43 | elevator | 2007-11-21 10:00 | 2007-11-27 17:00 | 5d |  | 0 | 38817.8516 | 0 | 0 | 38817.8516 | 2958466 | 0 | 0 | 0 | 5d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
44 | stairs | 2007-11-21 10:00 | 2007-12-04 17:00 | 10d |  | 0 | 33000 | 0 | 0 | 33000 | 2958466 | 0 | 0 | 0 | 10d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
45 | vI masonry | 2007-08-29 10:00 | 2007-09-11 17:00 | 10d | mason | 3252 | 31200.9609 | 40.65 | 3252.0001 | 37704.9611 | 2958466 | 0 | 0 | 0 | 10d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
49 | roof | 2007-04-27 08:00 | 2007-05-10 17:00 | 10d | roofing[4.0 #4] | 11520 | 70779.5703 | 40.3 | 3223.9999 | 85523.5703 | 2007-06-04 08:00 | 10d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
51 | vI electricity | 2007-08-29 10:00 | 2007-10-02 17:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 | 2958466 | 0 | 0 | 0 | 25d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
52 | vI sanitary | 2007-08-29 10:00 | 2007-09-11 17:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 | 2958466 | 0 | 0 | 0 | 10d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
53 | v2 sanitary | 2007-08-29 10:00 | 2007-09-11 17:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 | 2958466 | 0 | 0 | 0 | 10d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
54 | v2 electricity | 2007-08-29 10:00 | 2007-10-02 17:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 | 2958466 | 0 | 0 | 0 | 25d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
55 | v2 masonry | 2007-08-29 10:00 | 2007-09-11 17:00 | 10d | mason | 3252 | 31200.9609 | 0 | 0 | 34452.9609 | 2958466 | 0 | 0 | 0 | 10d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
56 | v2 screed | 2007-08-29 10:00 | 2007-09-18 17:00 | 15d | chapen | 0 | 46116 | 0 | 0 | 46116 | 2958466 | 0 | 0 | 0 | 15d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
57 | v1flooring | 2007-09-26 10:00 | 2007-10-23 17:00 | 20d | flooring | 6649.6 | 72500 | 0 | 0 | 79149.6 | 2958466 | 0 | 0 | 0 | 20d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
58 | v2 flooring | 2007-09-26 10:00 | 2007-10-23 17:00 | 20d | flooring | 6649.6 | 31500 | 0 | 0 | 38149.6 | 2958466 | 0 | 0 | 0 | 20d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
59 | v0 heating | 2007-08-29 10:00 | 2007-09-25 17:00 | 20d | heating | 6912 | 11651 | 0 | 0 | 18563 | 2958466 | 0 | 0 | 0 | 20d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
60 | v1 heating | 2007-08-29 10:00 | 2007-09-25 17:00 | 20d | heating | 6912 | 11651 | 43.2 | 6912.0001 | 25475.0001 | 2958466 | 0 | 0 | 0 | 20d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
61 | v2 heating | 2007-08-29 10:00 | 2007-09-25 17:00 | 20d | electrician | 5120 | 11651 | 0 | 0 | 16771 | 2958466 | 0 | 0 | 0 | 20d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
67 | v1 drying screed | 2007-09-19 10:00 | 2007-09-25 17:00 | 5d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2958466 | 0 | 0 | 0 | 5d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
68 | v2 drying screed | 2007-09-19 10:00 | 2007-09-25 17:00 | 5d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2958466 | 0 | 0 | 0 | 5d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
69 | soil analyses | 2006-12-11 08:00 | 2006-12-12 17:00 | 2d | team VDW | 616.96 | 2000 | 0 | 0 | 2616.96 | 2007-02-08 08:00 | 12d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0

## TP6
| TP Status Date | 2007-10-24 08:00 |  | TP Name | WH, L1, L2
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
2 | building permit | 2006-04-17 08:00 | 2006-07-07 17:00 | 60d |  | 0 | 75 | 0 | 0 | 75 | 2006-04-17 08:00 | 100d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
3 | hire contractor | 2006-07-10 08:00 | 2006-08-04 17:00 | 20d |  | 0 | 210000 | 0 | 0 | 210000 | 2006-09-04 08:00 | 30d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
4 | temporary offices | 2006-04-17 08:00 | 2006-05-12 17:00 | 20d |  | 0 | 3765.3101 | 0 | 0 | 3765.3101 | 2006-04-17 08:00 | 20d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
5 | temporary facilities | 2006-04-17 08:00 | 2006-07-07 17:00 | 60d |  | 0 | 1876.54 | 0 | 0 | 1876.54 | 2006-04-17 08:00 | 60d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
6 | demolition | 2006-10-30 08:00 | 2006-12-08 17:00 | 30d | team VDW[4.0 #8] | 37017.6 | 1070.11 | 0 | 0 | 38087.71 | 2006-11-27 08:00 | 54d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
16 | preparation contractor | 2006-08-07 08:00 | 2006-10-27 17:00 | 60d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2006-09-04 08:00 | 60d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
17 | excavation | 2006-12-11 08:00 | 2006-12-28 17:00 | 14d | team VDW | 4318.72 | 26000 | 0 | 0 | 30318.72 | 2007-02-08 08:00 | 10d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
18 | foundation beam | 2006-12-29 08:00 | 2007-02-01 17:00 | 25d | team VDW[3.0 #8] | 23136 | 98523.7266 | 0 | 0 | 121659.7266 | 2007-02-28 08:00 | 22d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
19 | steelframe I | 2007-02-02 08:00 | 2007-03-01 17:00 | 20d | team VDW[4.0 #8] | 24678.4 | 118992.5078 | 0 | 0 | 143670.9078 | 2007-04-02 08:00 | 15d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
20 | concrete vaults I | 2007-03-02 08:00 | 2007-03-15 17:00 | 10d | team VDW[4.0 #8] | 12339.2 | 117409.7188 | 0 | 0 | 129748.9187 | 2007-04-23 08:00 | 5d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
21 | placing sewerage | 2006-12-29 08:00 | 2007-01-11 17:00 | 10d | team VDW[3.0 #8] | 9254.4 | 1224.73 | 0 | 0 | 10479.13 | 2007-02-28 08:00 | 12d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
22 | steelframe II | 2007-03-16 08:00 | 2007-04-05 17:00 | 15d | team VDW[3.0 #8] | 13881.6 | 118992.5078 | 0 | 0 | 132874.1078 | 2007-04-30 08:00 | 15d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
23 | foundation plate | 2007-01-12 08:00 | 2007-01-12 17:00 | 1d | team VDW[5.0 #8] | 1542.4 | 234819.4375 | 0 | 0 | 236361.8375 | 2007-03-16 08:00 | 1d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
24 | concrete volt II | 2007-04-06 08:00 | 2007-04-26 17:00 | 15d | team VDW[4.0 #8] | 18508.8 | 117409.7188 | 0 | 0 | 135918.5187 | 2007-05-21 08:00 | 10d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
25 | facades | 2007-04-27 08:00 | 2007-05-24 17:00 | 20d | team VDW[2.0 #8] | 12339.2 | 339314 | 0 | 0 | 351653.2 | 2007-06-04 08:00 | 20d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
26 | outside windows | 2007-05-25 08:00 | 2007-06-07 17:00 | 10d | windows[3.0 #3] | 9120 | 150750.5938 | 0 | 0 | 159870.5938 | 2007-07-02 08:00 | 92d | 0 | 0 | 9d 21h | 0 | 0 | 0 | -1 | 90.30674695968631% | Started | 0 | 0
27 | v0 -masonry | 2007-08-29 10:00 | 2007-09-11 17:00 | 10d | mason | 3252 | 31200.9609 | 40.65 | 3252.0001 | 37704.9611 | 2007-08-29 08:00 | 10d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
28 | v0 polierbeton | 2007-06-08 08:00 | 2007-06-21 17:00 | 10d | team VDW[5.0 #8] | 15424 | 134400 | 0 | 0 | 149824 | 2007-07-25 08:00 | 5d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
29 | v0 electricity | 2007-08-29 10:00 | 2007-10-02 17:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 | 2007-08-02 08:00 | 15d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
30 | v0 sanitary | 2007-08-29 10:00 | 2007-09-11 17:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 | 2007-08-29 08:00 | 10d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
31 | construction leave | 2007-08-15 10:00 | 2007-08-28 17:00 | 10d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2007-08-08 08:00 | 10d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
32 | stucco | 2007-09-26 10:00 | 2007-10-16 17:00 | 15d | stucco[3.0 #4] | 14896.8 | 8642 | 0 | 0 | 23538.8 | 2958466 | 0 | 0 | 0 | 15d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
34 | v1screed | 2007-08-29 10:00 | 2007-09-18 17:00 | 15d | chapen[2.0 #3] | 0 | 106140 | 0 | 0 | 106140 | 2007-08-29 08:00 | 15d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
35 | v0 floors | 2007-10-03 10:00 | 2007-10-30 17:00 | 20d | flooring | 6649.6 | 75000 | 0 | 0 | 81649.6 | 2007-09-26 08:00 | 20d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
36 | drywall | 2007-10-24 10:00 | 2007-11-27 17:00 | 25d |  | 0 | 48000 | 0 | 0 | 48000 | 2958466 | 0 | 0 | 0 | 25d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
37 | techniques | 2007-10-31 10:00 | 2007-11-20 17:00 | 15d |  | 0 | 2156.0601 | 0 | 0 | 2156.0601 | 2958466 | 0 | 0 | 0 | 15d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
38 | suspended ceiling | 2007-11-21 10:00 | 2007-11-27 17:00 | 5d |  | 0 | 32000 | 0 | 0 | 32000 | 2958466 | 0 | 0 | 0 | 5d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
39 | painting | 2007-11-28 10:00 | 2007-12-18 17:00 | 15d | painter[4.0 #6] | 16800 | 83000 | 0 | 0 | 99800 | 2958466 | 0 | 0 | 0 | 15d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
40 | furniture | 2007-12-19 10:00 | 2007-12-25 17:00 | 5d | furniture[5.0 #5] | 8400 | 130000 | 0 | 0 | 138400 | 2958466 | 0 | 0 | 0 | 5d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
41 | kitchen and bar | 2007-10-31 10:00 | 2007-11-20 17:00 | 15d |  | 0 | 87000 | 0 | 0 | 87000 | 2958466 | 0 | 0 | 0 | 15d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
42 | entrance doors | 2007-11-21 10:00 | 2007-12-04 17:00 | 10d |  | 0 | 16000 | 0 | 0 | 16000 | 2958466 | 0 | 0 | 0 | 10d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
43 | elevator | 2007-11-21 10:00 | 2007-11-27 17:00 | 5d |  | 0 | 38817.8516 | 0 | 0 | 38817.8516 | 2958466 | 0 | 0 | 0 | 5d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
44 | stairs | 2007-11-21 10:00 | 2007-12-04 17:00 | 10d |  | 0 | 33000 | 0 | 0 | 33000 | 2958466 | 0 | 0 | 0 | 10d | 0 | 0 | 0 | -1 | 0.0% | Not Started | 0 | 0
45 | vI masonry | 2007-08-29 10:00 | 2007-09-11 17:00 | 10d | mason | 3252 | 31200.9609 | 40.65 | 3252.0001 | 37704.9611 | 2007-08-29 08:00 | 10d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
49 | roof | 2007-04-27 08:00 | 2007-05-10 17:00 | 10d | roofing[4.0 #4] | 11520 | 70779.5703 | 40.3 | 3223.9999 | 85523.5703 | 2007-06-04 08:00 | 10d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
51 | vI electricity | 2007-08-29 10:00 | 2007-10-02 17:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 | 2007-08-29 08:00 | 25d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
52 | vI sanitary | 2007-08-29 10:00 | 2007-09-11 17:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 | 2007-08-29 08:00 | 10d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
53 | v2 sanitary | 2007-08-29 10:00 | 2007-09-11 17:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 | 2007-08-29 08:00 | 10d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
54 | v2 electricity | 2007-08-29 10:00 | 2007-10-02 17:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 | 2007-08-29 08:00 | 20d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
55 | v2 masonry | 2007-08-29 10:00 | 2007-09-11 17:00 | 10d | mason | 3252 | 31200.9609 | 0 | 0 | 34452.9609 | 2007-08-29 08:00 | 10d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
56 | v2 screed | 2007-08-29 10:00 | 2007-09-18 17:00 | 15d | chapen | 0 | 46116 | 0 | 0 | 46116 | 2007-08-29 08:00 | 15d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
57 | v1flooring | 2007-09-26 10:00 | 2007-10-23 17:00 | 20d | flooring | 6649.6 | 72500 | 0 | 0 | 79149.6 | 2007-10-03 08:00 | 20d | 0 | 0 | 5d | 0 | 0 | 0 | -1 | 80.0000011920929% | Started | 0 | 0
58 | v2 flooring | 2007-09-26 10:00 | 2007-10-23 17:00 | 20d | flooring | 6649.6 | 31500 | 0 | 0 | 38149.6 | 2007-09-26 08:00 | 20d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
59 | v0 heating | 2007-08-29 10:00 | 2007-09-25 17:00 | 20d | heating | 6912 | 11651 | 0 | 0 | 18563 | 2007-08-29 08:00 | 20d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
60 | v1 heating | 2007-08-29 10:00 | 2007-09-25 17:00 | 20d | heating | 6912 | 11651 | 43.2 | 6912.0001 | 25475.0001 | 2007-08-29 08:00 | 20d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
61 | v2 heating | 2007-08-29 10:00 | 2007-09-25 17:00 | 20d | electrician | 5120 | 11651 | 0 | 0 | 16771 | 2007-08-29 08:00 | 20d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
67 | v1 drying screed | 2007-09-19 10:00 | 2007-09-25 17:00 | 5d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2007-09-19 08:00 | 5d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
68 | v2 drying screed | 2007-09-19 10:00 | 2007-09-25 17:00 | 5d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2007-09-19 08:00 | 5d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
69 | soil analyses | 2006-12-11 08:00 | 2006-12-12 17:00 | 2d | team VDW | 616.96 | 2000 | 0 | 0 | 2616.96 | 2007-02-08 08:00 | 12d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0

## TP7
| TP Status Date | 2008-01-10 08:00 |  | TP Name | Completion
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
2 | building permit | 2006-04-17 08:00 | 2006-07-07 17:00 | 60d |  | 0 | 75 | 0 | 0 | 75 | 2006-04-17 08:00 | 100d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
3 | hire contractor | 2006-07-10 08:00 | 2006-08-04 17:00 | 20d |  | 0 | 210000 | 0 | 0 | 210000 | 2006-09-04 08:00 | 30d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
4 | temporary offices | 2006-04-17 08:00 | 2006-05-12 17:00 | 20d |  | 0 | 3765.3101 | 0 | 0 | 3765.3101 | 2006-04-17 08:00 | 20d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
5 | temporary facilities | 2006-04-17 08:00 | 2006-07-07 17:00 | 60d |  | 0 | 1876.54 | 0 | 0 | 1876.54 | 2006-04-17 08:00 | 60d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
6 | demolition | 2006-10-30 08:00 | 2006-12-08 17:00 | 30d | team VDW[4.0 #8] | 37017.6 | 1070.11 | 0 | 0 | 38087.71 | 2006-11-27 08:00 | 54d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
16 | preparation contractor | 2006-08-07 08:00 | 2006-10-27 17:00 | 60d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2006-09-04 08:00 | 60d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
17 | excavation | 2006-12-11 08:00 | 2006-12-28 17:00 | 14d | team VDW | 4318.72 | 26000 | 0 | 0 | 30318.72 | 2007-02-08 08:00 | 10d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
18 | foundation beam | 2006-12-29 08:00 | 2007-02-01 17:00 | 25d | team VDW[3.0 #8] | 23136 | 98523.7266 | 0 | 0 | 121659.7266 | 2007-02-28 08:00 | 22d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
19 | steelframe I | 2007-02-02 08:00 | 2007-03-01 17:00 | 20d | team VDW[4.0 #8] | 24678.4 | 118992.5078 | 0 | 0 | 143670.9078 | 2007-04-02 08:00 | 15d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
20 | concrete vaults I | 2007-03-02 08:00 | 2007-03-15 17:00 | 10d | team VDW[4.0 #8] | 12339.2 | 117409.7188 | 0 | 0 | 129748.9187 | 2007-04-23 08:00 | 5d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
21 | placing sewerage | 2006-12-29 08:00 | 2007-01-11 17:00 | 10d | team VDW[3.0 #8] | 9254.4 | 1224.73 | 0 | 0 | 10479.13 | 2007-02-28 08:00 | 12d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
22 | steelframe II | 2007-03-16 08:00 | 2007-04-05 17:00 | 15d | team VDW[3.0 #8] | 13881.6 | 118992.5078 | 0 | 0 | 132874.1078 | 2007-04-30 08:00 | 15d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
23 | foundation plate | 2007-01-12 08:00 | 2007-01-12 17:00 | 1d | team VDW[5.0 #8] | 1542.4 | 234819.4375 | 0 | 0 | 236361.8375 | 2007-03-16 08:00 | 1d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
24 | concrete volt II | 2007-04-06 08:00 | 2007-04-26 17:00 | 15d | team VDW[4.0 #8] | 18508.8 | 117409.7188 | 0 | 0 | 135918.5187 | 2007-05-21 08:00 | 10d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
25 | facades | 2007-04-27 08:00 | 2007-05-24 17:00 | 20d | team VDW[2.0 #8] | 12339.2 | 339314 | 0 | 0 | 351653.2 | 2007-06-04 08:00 | 20d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
26 | outside windows | 2007-05-25 08:00 | 2007-06-07 17:00 | 10d | windows[3.0 #3] | 9120 | 150750.5938 | 0 | 0 | 159870.5938 | 2007-07-02 08:00 | 92d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
27 | v0 -masonry | 2007-08-29 10:00 | 2007-09-11 17:00 | 10d | mason | 3252 | 31200.9609 | 40.65 | 3252.0001 | 37704.9611 | 2007-08-29 08:00 | 10d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
28 | v0 polierbeton | 2007-06-08 08:00 | 2007-06-21 17:00 | 10d | team VDW[5.0 #8] | 15424 | 134400 | 0 | 0 | 149824 | 2007-07-25 08:00 | 5d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
29 | v0 electricity | 2007-08-29 10:00 | 2007-10-02 17:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 | 2007-08-02 08:00 | 15d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
30 | v0 sanitary | 2007-08-29 10:00 | 2007-09-11 17:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 | 2007-08-29 08:00 | 10d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
31 | construction leave | 2007-08-15 10:00 | 2007-08-28 17:00 | 10d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2007-08-08 08:00 | 10d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
32 | stucco | 2007-09-26 10:00 | 2007-10-16 17:00 | 15d | stucco[3.0 #4] | 14896.8 | 8642 | 0 | 0 | 23538.8 | 2007-11-05 08:00 | 15d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
34 | v1screed | 2007-08-29 10:00 | 2007-09-18 17:00 | 15d | chapen[2.0 #3] | 0 | 106140 | 0 | 0 | 106140 | 2007-08-29 08:00 | 15d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
35 | v0 floors | 2007-10-03 10:00 | 2007-10-30 17:00 | 20d | flooring | 6649.6 | 75000 | 0 | 0 | 81649.6 | 2007-09-26 08:00 | 20d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
36 | drywall | 2007-10-24 10:00 | 2007-11-27 17:00 | 25d |  | 0 | 48000 | 0 | 0 | 48000 | 2007-11-05 08:00 | 25d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
37 | techniques | 2007-10-31 10:00 | 2007-11-20 17:00 | 15d |  | 0 | 2156.0601 | 0 | 0 | 2156.0601 | 2007-11-26 08:00 | 15d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
38 | suspended ceiling | 2007-11-21 10:00 | 2007-11-27 17:00 | 5d |  | 0 | 32000 | 0 | 0 | 32000 | 2007-12-10 08:00 | 5d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
39 | painting | 2007-11-28 10:00 | 2007-12-18 17:00 | 15d | painter[4.0 #6] | 16800 | 83000 | 0 | 0 | 99800 | 2007-12-17 08:00 | 15d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
40 | furniture | 2007-12-19 10:00 | 2007-12-25 17:00 | 5d | furniture[5.0 #5] | 8400 | 130000 | 0 | 0 | 138400 | 2008-01-03 08:00 | 5d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
41 | kitchen and bar | 2007-10-31 10:00 | 2007-11-20 17:00 | 15d |  | 0 | 87000 | 0 | 0 | 87000 | 2007-11-26 08:00 | 20d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
42 | entrance doors | 2007-11-21 10:00 | 2007-12-04 17:00 | 10d |  | 0 | 16000 | 0 | 0 | 16000 | 2007-12-10 08:00 | 10d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
43 | elevator | 2007-11-21 10:00 | 2007-11-27 17:00 | 5d |  | 0 | 38817.8516 | 0 | 0 | 38817.8516 | 2007-12-10 08:00 | 5d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
44 | stairs | 2007-11-21 10:00 | 2007-12-04 17:00 | 10d |  | 0 | 33000 | 0 | 0 | 33000 | 2007-12-10 08:00 | 10d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
45 | vI masonry | 2007-08-29 10:00 | 2007-09-11 17:00 | 10d | mason | 3252 | 31200.9609 | 40.65 | 3252.0001 | 37704.9611 | 2007-08-29 08:00 | 10d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
49 | roof | 2007-04-27 08:00 | 2007-05-10 17:00 | 10d | roofing[4.0 #4] | 11520 | 70779.5703 | 40.3 | 3223.9999 | 85523.5703 | 2007-06-04 08:00 | 10d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
51 | vI electricity | 2007-08-29 10:00 | 2007-10-02 17:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 | 2007-08-29 08:00 | 25d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
52 | vI sanitary | 2007-08-29 10:00 | 2007-09-11 17:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 | 2007-08-29 08:00 | 10d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
53 | v2 sanitary | 2007-08-29 10:00 | 2007-09-11 17:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 | 2007-08-29 08:00 | 10d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
54 | v2 electricity | 2007-08-29 10:00 | 2007-10-02 17:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 | 2007-08-29 08:00 | 20d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
55 | v2 masonry | 2007-08-29 10:00 | 2007-09-11 17:00 | 10d | mason | 3252 | 31200.9609 | 0 | 0 | 34452.9609 | 2007-08-29 08:00 | 10d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
56 | v2 screed | 2007-08-29 10:00 | 2007-09-18 17:00 | 15d | chapen | 0 | 46116 | 0 | 0 | 46116 | 2007-08-29 08:00 | 15d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
57 | v1flooring | 2007-09-26 10:00 | 2007-10-23 17:00 | 20d | flooring | 6649.6 | 72500 | 0 | 0 | 79149.6 | 2007-10-03 08:00 | 20d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
58 | v2 flooring | 2007-09-26 10:00 | 2007-10-23 17:00 | 20d | flooring | 6649.6 | 31500 | 0 | 0 | 38149.6 | 2007-09-26 08:00 | 20d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
59 | v0 heating | 2007-08-29 10:00 | 2007-09-25 17:00 | 20d | heating | 6912 | 11651 | 0 | 0 | 18563 | 2007-08-29 08:00 | 20d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
60 | v1 heating | 2007-08-29 10:00 | 2007-09-25 17:00 | 20d | heating | 6912 | 11651 | 43.2 | 6912.0001 | 25475.0001 | 2007-08-29 08:00 | 20d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
61 | v2 heating | 2007-08-29 10:00 | 2007-09-25 17:00 | 20d | electrician | 5120 | 11651 | 0 | 0 | 16771 | 2007-08-29 08:00 | 20d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
67 | v1 drying screed | 2007-09-19 10:00 | 2007-09-25 17:00 | 5d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2007-09-19 08:00 | 5d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
68 | v2 drying screed | 2007-09-19 10:00 | 2007-09-25 17:00 | 5d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2007-09-19 08:00 | 5d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
69 | soil analyses | 2006-12-11 08:00 | 2006-12-12 17:00 | 2d | team VDW | 616.96 | 2000 | 0 | 0 | 2616.96 | 2007-02-08 08:00 | 12d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0

## TP8
| TP Status Date | 2008-01-11 08:00 |  | TP Name | Finish
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
2 | building permit | 2006-04-17 08:00 | 2006-07-07 17:00 | 60d |  | 0 | 75 | 0 | 0 | 75 | 2006-04-17 08:00 | 100d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
3 | hire contractor | 2006-07-10 08:00 | 2006-08-04 17:00 | 20d |  | 0 | 210000 | 0 | 0 | 210000 | 2006-09-04 08:00 | 30d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
4 | temporary offices | 2006-04-17 08:00 | 2006-05-12 17:00 | 20d |  | 0 | 3765.3101 | 0 | 0 | 3765.3101 | 2006-04-17 08:00 | 20d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
5 | temporary facilities | 2006-04-17 08:00 | 2006-07-07 17:00 | 60d |  | 0 | 1876.54 | 0 | 0 | 1876.54 | 2006-04-17 08:00 | 60d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
6 | demolition | 2006-10-30 08:00 | 2006-12-08 17:00 | 30d | team VDW[4.0 #8] | 37017.6 | 1070.11 | 0 | 0 | 38087.71 | 2006-11-27 08:00 | 54d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
16 | preparation contractor | 2006-08-07 08:00 | 2006-10-27 17:00 | 60d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2006-09-04 08:00 | 60d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
17 | excavation | 2006-12-11 08:00 | 2006-12-28 17:00 | 14d | team VDW | 4318.72 | 26000 | 0 | 0 | 30318.72 | 2007-02-08 08:00 | 10d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
18 | foundation beam | 2006-12-29 08:00 | 2007-02-01 17:00 | 25d | team VDW[3.0 #8] | 23136 | 98523.7266 | 0 | 0 | 121659.7266 | 2007-02-28 08:00 | 22d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
19 | steelframe I | 2007-02-02 08:00 | 2007-03-01 17:00 | 20d | team VDW[4.0 #8] | 24678.4 | 118992.5078 | 0 | 0 | 143670.9078 | 2007-04-02 08:00 | 15d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
20 | concrete vaults I | 2007-03-02 08:00 | 2007-03-15 17:00 | 10d | team VDW[4.0 #8] | 12339.2 | 117409.7188 | 0 | 0 | 129748.9187 | 2007-04-23 08:00 | 5d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
21 | placing sewerage | 2006-12-29 08:00 | 2007-01-11 17:00 | 10d | team VDW[3.0 #8] | 9254.4 | 1224.73 | 0 | 0 | 10479.13 | 2007-02-28 08:00 | 12d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
22 | steelframe II | 2007-03-16 08:00 | 2007-04-05 17:00 | 15d | team VDW[3.0 #8] | 13881.6 | 118992.5078 | 0 | 0 | 132874.1078 | 2007-04-30 08:00 | 15d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
23 | foundation plate | 2007-01-12 08:00 | 2007-01-12 17:00 | 1d | team VDW[5.0 #8] | 1542.4 | 234819.4375 | 0 | 0 | 236361.8375 | 2007-03-16 08:00 | 1d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
24 | concrete volt II | 2007-04-06 08:00 | 2007-04-26 17:00 | 15d | team VDW[4.0 #8] | 18508.8 | 117409.7188 | 0 | 0 | 135918.5187 | 2007-05-21 08:00 | 10d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
25 | facades | 2007-04-27 08:00 | 2007-05-24 17:00 | 20d | team VDW[2.0 #8] | 12339.2 | 339314 | 0 | 0 | 351653.2 | 2007-06-04 08:00 | 20d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
26 | outside windows | 2007-05-25 08:00 | 2007-06-07 17:00 | 10d | windows[3.0 #3] | 9120 | 150750.5938 | 0 | 0 | 159870.5938 | 2007-07-02 08:00 | 92d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
27 | v0 -masonry | 2007-08-29 10:00 | 2007-09-11 17:00 | 10d | mason | 3252 | 31200.9609 | 40.65 | 3252.0001 | 37704.9611 | 2007-08-29 08:00 | 10d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
28 | v0 polierbeton | 2007-06-08 08:00 | 2007-06-21 17:00 | 10d | team VDW[5.0 #8] | 15424 | 134400 | 0 | 0 | 149824 | 2007-07-25 08:00 | 5d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
29 | v0 electricity | 2007-08-29 10:00 | 2007-10-02 17:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 | 2007-08-02 08:00 | 15d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
30 | v0 sanitary | 2007-08-29 10:00 | 2007-09-11 17:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 | 2007-08-29 08:00 | 10d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
31 | construction leave | 2007-08-15 10:00 | 2007-08-28 17:00 | 10d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2007-08-08 08:00 | 10d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
32 | stucco | 2007-09-26 10:00 | 2007-10-16 17:00 | 15d | stucco[3.0 #4] | 14896.8 | 8642 | 0 | 0 | 23538.8 | 2007-11-05 08:00 | 15d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
34 | v1screed | 2007-08-29 10:00 | 2007-09-18 17:00 | 15d | chapen[2.0 #3] | 0 | 106140 | 0 | 0 | 106140 | 2007-08-29 08:00 | 15d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
35 | v0 floors | 2007-10-03 10:00 | 2007-10-30 17:00 | 20d | flooring | 6649.6 | 75000 | 0 | 0 | 81649.6 | 2007-09-26 08:00 | 20d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
36 | drywall | 2007-10-24 10:00 | 2007-11-27 17:00 | 25d |  | 0 | 48000 | 0 | 0 | 48000 | 2007-11-05 08:00 | 25d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
37 | techniques | 2007-10-31 10:00 | 2007-11-20 17:00 | 15d |  | 0 | 2156.0601 | 0 | 0 | 2156.0601 | 2007-11-26 08:00 | 15d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
38 | suspended ceiling | 2007-11-21 10:00 | 2007-11-27 17:00 | 5d |  | 0 | 32000 | 0 | 0 | 32000 | 2007-12-10 08:00 | 5d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
39 | painting | 2007-11-28 10:00 | 2007-12-18 17:00 | 15d | painter[4.0 #6] | 16800 | 83000 | 0 | 0 | 99800 | 2007-12-17 08:00 | 15d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
40 | furniture | 2007-12-19 10:00 | 2007-12-25 17:00 | 5d | furniture[5.0 #5] | 8400 | 130000 | 0 | 0 | 138400 | 2008-01-03 08:00 | 5d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
41 | kitchen and bar | 2007-10-31 10:00 | 2007-11-20 17:00 | 15d |  | 0 | 87000 | 0 | 0 | 87000 | 2007-11-26 08:00 | 20d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
42 | entrance doors | 2007-11-21 10:00 | 2007-12-04 17:00 | 10d |  | 0 | 16000 | 0 | 0 | 16000 | 2007-12-10 08:00 | 10d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
43 | elevator | 2007-11-21 10:00 | 2007-11-27 17:00 | 5d |  | 0 | 38817.8516 | 0 | 0 | 38817.8516 | 2007-12-10 08:00 | 5d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
44 | stairs | 2007-11-21 10:00 | 2007-12-04 17:00 | 10d |  | 0 | 33000 | 0 | 0 | 33000 | 2007-12-10 08:00 | 10d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
45 | vI masonry | 2007-08-29 10:00 | 2007-09-11 17:00 | 10d | mason | 3252 | 31200.9609 | 40.65 | 3252.0001 | 37704.9611 | 2007-08-29 08:00 | 10d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
49 | roof | 2007-04-27 08:00 | 2007-05-10 17:00 | 10d | roofing[4.0 #4] | 11520 | 70779.5703 | 40.3 | 3223.9999 | 85523.5703 | 2007-06-04 08:00 | 10d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
51 | vI electricity | 2007-08-29 10:00 | 2007-10-02 17:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 | 2007-08-29 08:00 | 25d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
52 | vI sanitary | 2007-08-29 10:00 | 2007-09-11 17:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 | 2007-08-29 08:00 | 10d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
53 | v2 sanitary | 2007-08-29 10:00 | 2007-09-11 17:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 | 2007-08-29 08:00 | 10d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
54 | v2 electricity | 2007-08-29 10:00 | 2007-10-02 17:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 | 2007-08-29 08:00 | 20d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
55 | v2 masonry | 2007-08-29 10:00 | 2007-09-11 17:00 | 10d | mason | 3252 | 31200.9609 | 0 | 0 | 34452.9609 | 2007-08-29 08:00 | 10d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
56 | v2 screed | 2007-08-29 10:00 | 2007-09-18 17:00 | 15d | chapen | 0 | 46116 | 0 | 0 | 46116 | 2007-08-29 08:00 | 15d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
57 | v1flooring | 2007-09-26 10:00 | 2007-10-23 17:00 | 20d | flooring | 6649.6 | 72500 | 0 | 0 | 79149.6 | 2007-10-03 08:00 | 20d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
58 | v2 flooring | 2007-09-26 10:00 | 2007-10-23 17:00 | 20d | flooring | 6649.6 | 31500 | 0 | 0 | 38149.6 | 2007-09-26 08:00 | 20d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
59 | v0 heating | 2007-08-29 10:00 | 2007-09-25 17:00 | 20d | heating | 6912 | 11651 | 0 | 0 | 18563 | 2007-08-29 08:00 | 20d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
60 | v1 heating | 2007-08-29 10:00 | 2007-09-25 17:00 | 20d | heating | 6912 | 11651 | 43.2 | 6912.0001 | 25475.0001 | 2007-08-29 08:00 | 20d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
61 | v2 heating | 2007-08-29 10:00 | 2007-09-25 17:00 | 20d | electrician | 5120 | 11651 | 0 | 0 | 16771 | 2007-08-29 08:00 | 20d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
67 | v1 drying screed | 2007-09-19 10:00 | 2007-09-25 17:00 | 5d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2007-09-19 08:00 | 5d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
68 | v2 drying screed | 2007-09-19 10:00 | 2007-09-25 17:00 | 5d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2007-09-19 08:00 | 5d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0
69 | soil analyses | 2006-12-11 08:00 | 2006-12-12 17:00 | 2d | team VDW | 616.96 | 2000 | 0 | 0 | 2616.96 | 2007-02-08 08:00 | 12d | 0 | 0 | 0 | 0 | 0 | 0 | -1 | 100.0% | Finished | 0 | 0

## Agenda
Working Hours |  | Working Days |  | Holidays
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No