## Baseline Schedule
General |  | Relations |  | Baseline |  |  | Resource Demand | Baseline Costs
ID | Name | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Fixed Cost | Cost/Hour | Variable Cost
CLAEYS-VERHELST
46 | preparation
2 | building permit |  | FS3 | 2006-04-17 08:00 | 2006-07-07 17:00 | 60d |  | 75 | 0 | 0 | Legend
3 | hire contractor | 2FS | FS16 | 2006-07-10 08:00 | 2006-08-04 17:00 | 20d |  | 210000 | 0 | 0 |  | Necessary input
4 | temporary offices |  |  | 2006-04-17 08:00 | 2006-05-12 17:00 | 20d |  | 3765.3101 | 0 | 0 |  | Alternative input*
5 | temporary facilities |  |  | 2006-04-17 08:00 | 2006-07-07 17:00 | 60d |  | 1876.54 | 0 | 0 |  | Additional input
16 | preparation contractor | 3FS | FS6 | 2006-08-07 08:00 | 2006-10-27 17:00 | 60d |  | 0.01 | 0 | 0 |  | Repeated input
6 | demolition | 16FS | FS17;FS69 | 2006-10-30 08:00 | 2006-12-08 17:00 | 30d | team subcontractor[4,00 #8] | 1070.11 | 0 | 0
47 | foundation | [9 empty] | * Baseline End is an alternative input for (Baseline) Duration,
17 | excavation | 6FS | FS18;FS21 | 2006-12-11 08:00 | 2006-12-28 17:00 | 14d | team subcontractor | 26000 | 0 | 0 | Cost/Hour is an alternative input for Variable (Baseline) Cost
69 | soil analyses | 6FS | FS18 | 2006-12-11 08:00 | 2006-12-12 17:00 | 2d | team subcontractor | 2000 | 0 | 0
18 | foundation beam | 17FS;69FS | FS19 | 2006-12-29 08:00 | 2007-02-01 17:00 | 25d | team subcontractor[3,00 #8] | 98523.7266 | 0 | 0 | For further explanation, see Guideline for project data input
21 | placing sewerage | 17FS | FS23 | 2006-12-29 08:00 | 2007-01-11 17:00 | 10d | team subcontractor[3,00 #8] | 1224.73 | 0 | 0
23 | foundation plate | 21FS | FS19 | 2007-01-12 08:00 | 2007-01-12 17:00 | 1d | team subcontractor[5,00 #8] | 234819.4375 | 0 | 0
48 | shell
19 | steelframe I | 18FS;23FS | FS20 | 2007-02-02 08:00 | 2007-03-01 17:00 | 20d | team subcontractor[4,00 #8] | 118992.5078 | 0 | 0
20 | concrete vaults I | 19FS | FS22 | 2007-03-02 08:00 | 2007-03-15 17:00 | 10d | team subcontractor[4,00 #8] | 117409.7188 | 0 | 0
22 | steelframe II | 20FS | FS24 | 2007-03-16 08:00 | 2007-04-05 17:00 | 15d | team subcontractor[3,00 #8] | 118992.5078 | 0 | 0
24 | concrete vaults II | 22FS | FS25;FS49 | 2007-04-06 08:00 | 2007-04-26 17:00 | 15d | team subcontractor[4,00 #8] | 117409.7188 | 0 | 0
50 | wind and water proof
25 | facades | 24FS | FS26 | 2007-04-27 08:00 | 2007-05-24 17:00 | 20d | team subcontractor[2,00 #8] | 339314 | 0 | 0
26 | outside windows | 25FS | FS28;FS29 | 2007-05-25 08:00 | 2007-06-07 17:00 | 10d | carpenter[3,00 #3] | 150750.5938 | 0 | 0
49 | roof | 24FS |  | 2007-04-27 08:00 | 2007-05-10 17:00 | 10d | roofer[4,00 #4] | 70779.5703 | 40.3 | 3224
62 | warehouse
28 | v0 concrete | 26FS | FS30;FS27;FS59;FS52;FS45;FS34;FS60;FS51 | 2007-06-08 08:00 | 2007-06-21 17:00 | 10d | team subcontractor[5,00 #8] | 134400 | 0 | 0
30 | v0 sanitary | 31FS;28FS | FS35 | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 4793 | 0 | 0
27 | v0 masonry | 31FS;28FS |  | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 31200.9609 | 40.65 | 3252
59 | v0 heating | 31FS;28FS | FS35 | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | heating engineer | 11651 | 0 | 0
29 | v0 electricity | 26FS;31FS | FS35 | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 0 | 0 | 0
35 | v0 floors | 59FS;29FS;30FS | FS41;FS37 | 2007-10-03 10:00 | 2007-10-31 10:00 | 20d | floor layer | 75000 | 0 | 0
66 | construction leave
31 | construction leave |  | FS53;FS55;FS56;FS61;FS54;FS30;FS27;FS59;FS52;FS45;FS34;FS60;FS51;FS29 | 2007-08-15 10:00 | 2007-08-29 10:00 | 10d |  | 0.01 | 0 | 0
63 | level 1
52 | v1 sanitary | 31FS;28FS |  | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 4793 | 0 | 0
45 | v1 masonry | 31FS;28FS |  | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 31200.9609 | 40.65 | 3252
34 | v1 screed | 31FS;28FS | FS67 | 2007-08-29 10:00 | 2007-09-19 10:00 | 15d | screed layer[2,00 #3] | 106140 | 0 | 0
60 | v1 heating | 31FS;28FS |  | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | heating engineer | 11651 | 43.2 | 6912
51 | v1 electricity | 31FS;28FS |  | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 0 | 0 | 0
67 | v1 drying screed | 34FS | FS57;FS32 | 2007-09-19 10:00 | 2007-09-26 10:00 | 5d |  | 0.01 | 0 | 0
57 | v1 flooring | 67FS | FS41;FS37;FS36 | 2007-09-26 10:00 | 2007-10-24 10:00 | 20d | floor layer | 72500 | 0 | 0
64 | level 2
53 | v2 sanitary | 31FS |  | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 4793 | 0 | 0
55 | v2 masonry | 31FS |  | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 31200.9609 | 0 | 0
56 | v2 screed | 31FS | FS68;FS36 | 2007-08-29 10:00 | 2007-09-19 10:00 | 15d | screed layer | 46116 | 0 | 0
61 | v2 heating | 31FS |  | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | electrician | 11651 | 0 | 0
54 | v2 electricity | 31FS |  | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 0 | 0 | 0
68 | v2 drying screed | 56FS | FS58;FS32 | 2007-09-19 10:00 | 2007-09-26 10:00 | 5d |  | 0.01 | 0 | 0
58 | v2 flooring | 68FS | FS41;FS37;FS36 | 2007-09-26 10:00 | 2007-10-24 10:00 | 20d | floor layer | 31500 | 0 | 0
65 | completion
32 | stucco | 68FS;67FS | FS41;FS37 | 2007-09-26 10:00 | 2007-10-17 10:00 | 15d | plasterer[3,00 #4] | 8642 | 0 | 0
36 | drywall | 58FS;57FS;56FS |  | 2007-10-24 10:00 | 2007-11-28 10:00 | 25d |  | 48000 | 0 | 0
41 | kitchen and bar | 32FS;58FS;57FS;35FS |  | 2007-10-31 10:00 | 2007-11-21 10:00 | 15d |  | 87000 | 0 | 0
37 | techniques | 32FS;58FS;57FS;35FS | FS38;FS42;FS43;FS44 | 2007-10-31 10:00 | 2007-11-21 10:00 | 15d |  | 2156.0601 | 0 | 0
44 | stairs | 37FS |  | 2007-11-21 10:00 | 2007-12-05 10:00 | 10d |  | 33000 | 0 | 0
42 | entrance doors | 37FS |  | 2007-11-21 10:00 | 2007-12-05 10:00 | 10d |  | 16000 | 0 | 0
43 | elevator | 37FS |  | 2007-11-21 10:00 | 2007-11-28 10:00 | 5d |  | 38817.8516 | 0 | 0
38 | suspended ceiling | 37FS | FS39 | 2007-11-21 10:00 | 2007-11-28 10:00 | 5d |  | 32000 | 0 | 0
39 | painting | 38FS | FS40 | 2007-11-28 10:00 | 2007-12-19 10:00 | 15d | painter[4,00 #6] | 83000 | 0 | 0
40 | furniture | 39FS |  | 2007-12-19 10:00 | 2007-12-26 10:00 | 5d | joiner[5,00 #5] | 130000 | 0 | 0

## Resources
General |  |  |  | Resource Cost
ID | Name | Type | Availibility | Cost/Use | Cost/Unit
1 | plumber | Renewable | 4,00 #4 | 0 | 36
2 | electrician | Renewable | 4,00 #4 | 0 | 32
3 | team subcontractor | Renewable | 8,00 #8 | 0 | 38.56
4 | mason | Renewable | 4,00 #4 | 0 | 40.65
5 | heating engineer | Renewable | 2,00 #2 | 0 | 43.2
6 | roofer | Renewable | 4,00 #4 | 0 | 36
7 | carpenter | Renewable | 3,00 #3 | 0 | 38
8 | floor layer | Renewable | 4,00 #4 | 0 | 41.56
9 | screed layer | Renewable | 3,00 #3 | 0 | 0
10 | plasterer | Renewable | 4,00 #4 | 0 | 41.38
11 | painter | Renewable | 6,00 #6 | 0 | 35
12 | joiner | Renewable | 5,00 #5 | 0 | 42

## Risk Analysis
General |  | Activity Duration Distribution Profiles
ID | Name | Description | Optimistic | Most Probable | Pessimistic
CLAEYS-VERHELST
46 | preparation
2 | building permit | manual - absolute | 402 | 480 | 812
3 | hire contractor | manual - absolute | 127 | 160 | 326
4 | temporary offices | standard - symmetric | 80 | 100 | 120
5 | temporary facilities | standard - symmetric | 80 | 100 | 120
16 | preparation contractor | standard - no risk | 99 | 100 | 101
6 | demolition | manual - absolute | 219 | 240 | 302
47 | foundation
17 | excavation | standard - symmetric | 80 | 100 | 120
69 | soil analyses | standard - symmetric | 80 | 100 | 120
18 | foundation beam | manual - absolute | 159 | 200 | 363
21 | placing sewerage | manual - absolute | 63 | 80 | 98
23 | foundation plate | manual - absolute | 6 | 8 | 10
48 | shell
19 | steelframe I | manual - absolute | 104 | 120 | 166
20 | concrete vaults I | manual - absolute | 32 | 40 | 48
22 | steelframe II | manual - absolute | 64 | 80 | 113
24 | concrete vaults II | manual - absolute | 66 | 80 | 121
50 | wind and water proof
25 | facades | manual - absolute | 128 | 160 | 463
26 | outside windows | manual - absolute | 64 | 80 | 175
49 | roof | standard - symmetric | 80 | 100 | 120
62 | warehouse
28 | v0 concrete | standard - symmetric | 80 | 100 | 120
30 | v0 sanitary | standard - no risk | 99 | 100 | 101
27 | v0 masonry | standard - no risk | 99 | 100 | 101
59 | v0 heating | standard - no risk | 99 | 100 | 101
29 | v0 electricity | standard - no risk | 99 | 100 | 101
35 | v0 floors | manual - absolute | 128 | 163 | 543
66 | construction leave
31 | construction leave | standard - no risk | 99 | 100 | 101
63 | level 1
52 | v1 sanitary | standard - no risk | 99 | 100 | 101
45 | v1 masonry | standard - no risk | 99 | 100 | 101
34 | v1 screed | standard - no risk | 99 | 100 | 101
60 | v1 heating | standard - no risk | 99 | 100 | 101
51 | v1 electricity | standard - no risk | 99 | 100 | 101
67 | v1 drying screed | standard - skewed left | 80 | 110 | 120
57 | v1 flooring | manual - absolute | 128 | 160 | 577
64 | level 2
53 | v2 sanitary | standard - no risk | 99 | 100 | 101
55 | v2 masonry | standard - no risk | 99 | 100 | 101
56 | v2 screed | standard - skewed left | 80 | 110 | 120
61 | v2 heating | standard - skewed left | 80 | 110 | 120
54 | v2 electricity | standard - no risk | 99 | 100 | 101
68 | v2 drying screed | standard - skewed left | 80 | 110 | 120
58 | v2 flooring | manual - absolute | 128 | 160 | 556
65 | completion
32 | stucco | manual - absolute | 96 | 120 | 451
36 | drywall | manual - absolute | 160 | 200 | 528
41 | kitchen and bar | standard - symmetric | 80 | 100 | 120
37 | techniques | standard - symmetric | 80 | 100 | 120
44 | stairs | standard - symmetric | 80 | 100 | 120
42 | entrance doors | standard - symmetric | 80 | 100 | 120
43 | elevator | standard - symmetric | 80 | 100 | 120
38 | suspended ceiling | standard - symmetric | 80 | 100 | 120
39 | painting | standard - symmetric | 80 | 100 | 120
40 | furniture | standard - symmetric | 80 | 100 | 120

## Project Control - TP1
| TP Status Date | 2006-07-07 17:00 | TP Name | Preparation1
General |  | Tracking
ID | Name | Actual Start | Actual Duration | Actual Cost | Percentage Completed
CLAEYS-VERHELST
46 | preparation
2 | building permit | 2006-04-17 08:00 | 60d | 75 | 100%
3 | hire contractor |  | 0 | 0 | 0%
4 | temporary offices | 2006-04-17 08:00 | 20d | 3765.3101 | 100%
5 | temporary facilities | 2006-04-17 08:00 | 60d | 1876.54 | 100%
16 | preparation contractor |  | 0 | 0 | 0%
6 | demolition |  | 0 | 0 | 0%
47 | foundation
17 | excavation |  | 0 | 0 | 0%
69 | soil analyses |  | 0 | 0 | 0%
18 | foundation beam |  | 0 | 0 | 0%
21 | placing sewerage |  | 0 | 0 | 0%
23 | foundation plate |  | 0 | 0 | 0%
48 | shell
19 | steelframe I |  | 0 | 0 | 0%
20 | concrete vaults I |  | 0 | 0 | 0%
22 | steelframe II |  | 0 | 0 | 0%
24 | concrete vaults II |  | 0 | 0 | 0%
50 | wind and water proof
25 | facades |  | 0 | 0 | 0%
26 | outside windows |  | 0 | 0 | 0%
49 | roof |  | 0 | 0 | 0%
62 | warehouse
28 | v0 concrete |  | 0 | 0 | 0%
30 | v0 sanitary |  | 0 | 0 | 0%
27 | v0 masonry |  | 0 | 0 | 0%
59 | v0 heating |  | 0 | 0 | 0%
29 | v0 electricity |  | 0 | 0 | 0%
35 | v0 floors |  | 0 | 0 | 0%
66 | construction leave
31 | construction leave |  | 0 | 0 | 0%
63 | level 1
52 | v1 sanitary |  | 0 | 0 | 0%
45 | v1 masonry |  | 0 | 0 | 0%
34 | v1 screed |  | 0 | 0 | 0%
60 | v1 heating |  | 0 | 0 | 0%
51 | v1 electricity |  | 0 | 0 | 0%
67 | v1 drying screed |  | 0 | 0 | 0%
57 | v1 flooring |  | 0 | 0 | 0%
64 | level 2
53 | v2 sanitary |  | 0 | 0 | 0%
55 | v2 masonry |  | 0 | 0 | 0%
56 | v2 screed |  | 0 | 0 | 0%
61 | v2 heating |  | 0 | 0 | 0%
54 | v2 electricity |  | 0 | 0 | 0%
68 | v2 drying screed |  | 0 | 0 | 0%
58 | v2 flooring |  | 0 | 0 | 0%
65 | completion
32 | stucco |  | 0 | 0 | 0%
36 | drywall |  | 0 | 0 | 0%
41 | kitchen and bar |  | 0 | 0 | 0%
37 | techniques |  | 0 | 0 | 0%
44 | stairs |  | 0 | 0 | 0%
42 | entrance doors |  | 0 | 0 | 0%
43 | elevator |  | 0 | 0 | 0%
38 | suspended ceiling |  | 0 | 0 | 0%
39 | painting |  | 0 | 0 | 0%
40 | furniture |  | 0 | 0 | 0%

## TP2
| TP Status Date | 2007-02-08 17:00 | TP Name | Preparation2
General |  | Tracking
ID | Name | Actual Start | Actual Duration | Actual Cost | Percentage Completed
CLAEYS-VERHELST
46 | preparation
2 | building permit | 2006-04-17 08:00 | 60d | 75 | 100%
3 | hire contractor | 2006-09-04 08:00 | 30d | 210000 | 100%
4 | temporary offices | 2006-04-17 08:00 | 20d | 3765.3101 | 100%
5 | temporary facilities | 2006-04-17 08:00 | 60d | 1876.54 | 100%
16 | preparation contractor | 2006-09-04 08:00 | 60d | 0.01 | 100%
6 | demolition | 2006-11-27 08:00 | 54d | 67701.7891 | 100%
47 | foundation
17 | excavation |  | 0 | 0 | 0%
69 | soil analyses |  | 0 | 0 | 0%
18 | foundation beam |  | 0 | 0 | 0%
21 | placing sewerage |  | 0 | 0 | 0%
23 | foundation plate |  | 0 | 0 | 0%
48 | shell
19 | steelframe I |  | 0 | 0 | 0%
20 | concrete vaults I |  | 0 | 0 | 0%
22 | steelframe II |  | 0 | 0 | 0%
24 | concrete vaults II |  | 0 | 0 | 0%
50 | wind and water proof
25 | facades |  | 0 | 0 | 0%
26 | outside windows |  | 0 | 0 | 0%
49 | roof |  | 0 | 0 | 0%
62 | warehouse
28 | v0 concrete |  | 0 | 0 | 0%
30 | v0 sanitary |  | 0 | 0 | 0%
27 | v0 masonry |  | 0 | 0 | 0%
59 | v0 heating |  | 0 | 0 | 0%
29 | v0 electricity |  | 0 | 0 | 0%
35 | v0 floors |  | 0 | 0 | 0%
66 | construction leave
31 | construction leave |  | 0 | 0 | 0%
63 | level 1
52 | v1 sanitary |  | 0 | 0 | 0%
45 | v1 masonry |  | 0 | 0 | 0%
34 | v1 screed |  | 0 | 0 | 0%
60 | v1 heating |  | 0 | 0 | 0%
51 | v1 electricity |  | 0 | 0 | 0%
67 | v1 drying screed |  | 0 | 0 | 0%
57 | v1 flooring |  | 0 | 0 | 0%
64 | level 2
53 | v2 sanitary |  | 0 | 0 | 0%
55 | v2 masonry |  | 0 | 0 | 0%
56 | v2 screed |  | 0 | 0 | 0%
61 | v2 heating |  | 0 | 0 | 0%
54 | v2 electricity |  | 0 | 0 | 0%
68 | v2 drying screed |  | 0 | 0 | 0%
58 | v2 flooring |  | 0 | 0 | 0%
65 | completion
32 | stucco |  | 0 | 0 | 0%
36 | drywall |  | 0 | 0 | 0%
41 | kitchen and bar |  | 0 | 0 | 0%
37 | techniques |  | 0 | 0 | 0%
44 | stairs |  | 0 | 0 | 0%
42 | entrance doors |  | 0 | 0 | 0%
43 | elevator |  | 0 | 0 | 0%
38 | suspended ceiling |  | 0 | 0 | 0%
39 | painting |  | 0 | 0 | 0%
40 | furniture |  | 0 | 0 | 0%

## TP3
| TP Status Date | 2007-03-16 17:00 | TP Name | Foundation
General |  | Tracking
ID | Name | Actual Start | Actual Duration | Actual Cost | Percentage Completed
CLAEYS-VERHELST
46 | preparation
2 | building permit | 2006-04-17 08:00 | 60d | 75 | 100%
3 | hire contractor | 2006-09-04 08:00 | 30d | 210000 | 100%
4 | temporary offices | 2006-04-17 08:00 | 20d | 3765.3101 | 100%
5 | temporary facilities | 2006-04-17 08:00 | 60d | 1876.54 | 100%
16 | preparation contractor | 2006-09-04 08:00 | 60d | 0.01 | 100%
6 | demolition | 2006-11-27 08:00 | 54d | 67701.7891 | 100%
47 | foundation
17 | excavation | 2007-02-09 08:00 | 10d | 29084.8008 | 100%
69 | soil analyses | 2007-02-09 08:00 | 12d | 5701.7603 | 100%
18 | foundation beam | 2007-02-28 08:00 | 13d | 110554.45 | 65%
21 | placing sewerage | 2007-02-28 08:00 | 12d | 12330.0098 | 100%
23 | foundation plate | 2007-03-16 08:00 | 1d | 236361.8438 | 100%
48 | shell
19 | steelframe I |  | 0 | 0 | 0%
20 | concrete vaults I |  | 0 | 0 | 0%
22 | steelframe II |  | 0 | 0 | 0%
24 | concrete vaults II |  | 0 | 0 | 0%
50 | wind and water proof
25 | facades |  | 0 | 0 | 0%
26 | outside windows |  | 0 | 0 | 0%
49 | roof |  | 0 | 0 | 0%
62 | warehouse
28 | v0 concrete |  | 0 | 0 | 0%
30 | v0 sanitary |  | 0 | 0 | 0%
27 | v0 masonry |  | 0 | 0 | 0%
59 | v0 heating |  | 0 | 0 | 0%
29 | v0 electricity |  | 0 | 0 | 0%
35 | v0 floors |  | 0 | 0 | 0%
66 | construction leave
31 | construction leave |  | 0 | 0 | 0%
63 | level 1
52 | v1 sanitary |  | 0 | 0 | 0%
45 | v1 masonry |  | 0 | 0 | 0%
34 | v1 screed |  | 0 | 0 | 0%
60 | v1 heating |  | 0 | 0 | 0%
51 | v1 electricity |  | 0 | 0 | 0%
67 | v1 drying screed |  | 0 | 0 | 0%
57 | v1 flooring |  | 0 | 0 | 0%
64 | level 2
53 | v2 sanitary |  | 0 | 0 | 0%
55 | v2 masonry |  | 0 | 0 | 0%
56 | v2 screed |  | 0 | 0 | 0%
61 | v2 heating |  | 0 | 0 | 0%
54 | v2 electricity |  | 0 | 0 | 0%
68 | v2 drying screed |  | 0 | 0 | 0%
58 | v2 flooring |  | 0 | 0 | 0%
65 | completion
32 | stucco |  | 0 | 0 | 0%
36 | drywall |  | 0 | 0 | 0%
41 | kitchen and bar |  | 0 | 0 | 0%
37 | techniques |  | 0 | 0 | 0%
44 | stairs |  | 0 | 0 | 0%
42 | entrance doors |  | 0 | 0 | 0%
43 | elevator |  | 0 | 0 | 0%
38 | suspended ceiling |  | 0 | 0 | 0%
39 | painting |  | 0 | 0 | 0%
40 | furniture |  | 0 | 0 | 0%

## TP4
| TP Status Date | 2007-06-01 17:00 | TP Name | Shell
General |  | Tracking
ID | Name | Actual Start | Actual Duration | Actual Cost | Percentage Completed
CLAEYS-VERHELST
46 | preparation
2 | building permit | 2006-04-17 08:00 | 60d | 75 | 100%
3 | hire contractor | 2006-09-04 08:00 | 30d | 210000 | 100%
4 | temporary offices | 2006-04-17 08:00 | 20d | 3765.3101 | 100%
5 | temporary facilities | 2006-04-17 08:00 | 60d | 1876.54 | 100%
16 | preparation contractor | 2006-09-04 08:00 | 60d | 0.01 | 100%
6 | demolition | 2006-11-27 08:00 | 54d | 67701.7891 | 100%
47 | foundation
17 | excavation | 2007-02-08 08:00 | 10d | 29084.8008 | 100%
69 | soil analyses | 2007-02-08 08:00 | 12d | 5701.7603 | 100%
18 | foundation beam | 2007-02-28 08:00 | 22d | 118883.4062 | 100%
21 | placing sewerage | 2007-02-28 08:00 | 12d | 12330.0098 | 100%
23 | foundation plate | 2007-03-16 08:00 | 1d | 236361.8438 | 100%
48 | shell
19 | steelframe I | 2007-04-02 08:00 | 15d | 137501.3125 | 100%
20 | concrete vaults I | 2007-04-23 08:00 | 5d | 123579.3203 | 100%
22 | steelframe II | 2007-04-30 08:00 | 15d | 132874.1094 | 100%
24 | concrete vaults II | 2007-05-21 08:00 | 10d | 129748.9219 | 100%
50 | wind and water proof
25 | facades |  | 0 | 0 | 0%
26 | outside windows |  | 0 | 0 | 0%
49 | roof |  | 0 | 0 | 0%
62 | warehouse
28 | v0 concrete |  | 0 | 0 | 0%
30 | v0 sanitary |  | 0 | 0 | 0%
27 | v0 masonry |  | 0 | 0 | 0%
59 | v0 heating |  | 0 | 0 | 0%
29 | v0 electricity |  | 0 | 0 | 0%
35 | v0 floors |  | 0 | 0 | 0%
66 | construction leave
31 | construction leave |  | 0 | 0 | 0%
63 | level 1
52 | v1 sanitary |  | 0 | 0 | 0%
45 | v1 masonry |  | 0 | 0 | 0%
34 | v1 screed |  | 0 | 0 | 0%
60 | v1 heating |  | 0 | 0 | 0%
51 | v1 electricity |  | 0 | 0 | 0%
67 | v1 drying screed |  | 0 | 0 | 0%
57 | v1 flooring |  | 0 | 0 | 0%
64 | level 2
53 | v2 sanitary |  | 0 | 0 | 0%
55 | v2 masonry |  | 0 | 0 | 0%
56 | v2 screed |  | 0 | 0 | 0%
61 | v2 heating |  | 0 | 0 | 0%
54 | v2 electricity |  | 0 | 0 | 0%
68 | v2 drying screed |  | 0 | 0 | 0%
58 | v2 flooring |  | 0 | 0 | 0%
65 | completion
32 | stucco |  | 0 | 0 | 0%
36 | drywall |  | 0 | 0 | 0%
41 | kitchen and bar |  | 0 | 0 | 0%
37 | techniques |  | 0 | 0 | 0%
44 | stairs |  | 0 | 0 | 0%
42 | entrance doors |  | 0 | 0 | 0%
43 | elevator |  | 0 | 0 | 0%
38 | suspended ceiling |  | 0 | 0 | 0%
39 | painting |  | 0 | 0 | 0%
40 | furniture |  | 0 | 0 | 0%

## TP5
| TP Status Date | 2007-06-29 17:00 | TP Name | Wind & waterproof
General |  | Tracking
ID | Name | Actual Start | Actual Duration | Actual Cost | Percentage Completed
CLAEYS-VERHELST
46 | preparation
2 | building permit | 2006-04-17 08:00 | 60d | 75 | 100%
3 | hire contractor | 2006-09-04 08:00 | 30d | 210000 | 100%
4 | temporary offices | 2006-04-17 08:00 | 20d | 3765.3101 | 100%
5 | temporary facilities | 2006-04-17 08:00 | 60d | 1876.54 | 100%
16 | preparation contractor | 2006-09-04 08:00 | 60d | 0.01 | 100%
6 | demolition | 2006-11-27 08:00 | 54d | 67701.7891 | 100%
47 | foundation
17 | excavation | 2007-02-08 08:00 | 10d | 29084.8008 | 100%
69 | soil analyses | 2007-02-08 08:00 | 12d | 5701.7603 | 100%
18 | foundation beam | 2007-02-28 08:00 | 22d | 118883.4062 | 100%
21 | placing sewerage | 2007-02-28 08:00 | 12d | 12330.0098 | 100%
23 | foundation plate | 2007-03-16 08:00 | 1d | 236361.8438 | 100%
48 | shell
19 | steelframe I | 2007-04-02 08:00 | 15d | 137501.3125 | 100%
20 | concrete vaults I | 2007-04-23 08:00 | 5d | 123579.3203 | 100%
22 | steelframe II | 2007-04-30 08:00 | 15d | 132874.1094 | 100%
24 | concrete vaults II | 2007-05-21 08:00 | 10d | 129748.9219 | 100%
50 | wind and water proof
25 | facades | 2007-06-04 08:00 | 20d | 351653.1875 | 100%
26 | outside windows |  | 0 | 0 | 0%
49 | roof | 2007-06-04 08:00 | 10d | 85523.5703 | 100%
62 | warehouse
28 | v0 concrete |  | 0 | 0 | 0%
30 | v0 sanitary |  | 0 | 0 | 0%
27 | v0 masonry |  | 0 | 0 | 0%
59 | v0 heating |  | 0 | 0 | 0%
29 | v0 electricity |  | 0 | 0 | 0%
35 | v0 floors |  | 0 | 0 | 0%
66 | construction leave
31 | construction leave |  | 0 | 0 | 0%
63 | level 1
52 | v1 sanitary |  | 0 | 0 | 0%
45 | v1 masonry |  | 0 | 0 | 0%
34 | v1 screed |  | 0 | 0 | 0%
60 | v1 heating |  | 0 | 0 | 0%
51 | v1 electricity |  | 0 | 0 | 0%
67 | v1 drying screed |  | 0 | 0 | 0%
57 | v1 flooring |  | 0 | 0 | 0%
64 | level 2
53 | v2 sanitary |  | 0 | 0 | 0%
55 | v2 masonry |  | 0 | 0 | 0%
56 | v2 screed |  | 0 | 0 | 0%
61 | v2 heating |  | 0 | 0 | 0%
54 | v2 electricity |  | 0 | 0 | 0%
68 | v2 drying screed |  | 0 | 0 | 0%
58 | v2 flooring |  | 0 | 0 | 0%
65 | completion
32 | stucco |  | 0 | 0 | 0%
36 | drywall |  | 0 | 0 | 0%
41 | kitchen and bar |  | 0 | 0 | 0%
37 | techniques |  | 0 | 0 | 0%
44 | stairs |  | 0 | 0 | 0%
42 | entrance doors |  | 0 | 0 | 0%
43 | elevator |  | 0 | 0 | 0%
38 | suspended ceiling |  | 0 | 0 | 0%
39 | painting |  | 0 | 0 | 0%
40 | furniture |  | 0 | 0 | 0%

## TP6
| TP Status Date | 2007-10-24 17:00 | TP Name | WH, L1, L2
General |  | Tracking
ID | Name | Actual Start | Actual Duration | Actual Cost | Percentage Completed
CLAEYS-VERHELST
46 | preparation
2 | building permit | 2006-04-17 08:00 | 60d | 75 | 100%
3 | hire contractor | 2006-09-04 08:00 | 30d | 210000 | 100%
4 | temporary offices | 2006-04-17 08:00 | 20d | 3765.3101 | 100%
5 | temporary facilities | 2006-04-17 08:00 | 60d | 1876.54 | 100%
16 | preparation contractor | 2006-09-04 08:00 | 60d | 0.01 | 100%
6 | demolition | 2006-11-27 08:00 | 54d | 67701.7891 | 100%
47 | foundation
17 | excavation | 2007-02-08 08:00 | 10d | 29084.8008 | 100%
69 | soil analyses | 2007-02-08 08:00 | 12d | 5701.7603 | 100%
18 | foundation beam | 2007-02-28 08:00 | 22d | 118883.4062 | 100%
21 | placing sewerage | 2007-02-28 08:00 | 12d | 12330.0098 | 100%
23 | foundation plate | 2007-03-16 08:00 | 1d | 236361.8438 | 100%
48 | shell
19 | steelframe I | 2007-04-02 08:00 | 15d | 137501.3125 | 100%
20 | concrete vaults I | 2007-04-23 08:00 | 5d | 123579.3203 | 100%
22 | steelframe II | 2007-04-30 08:00 | 15d | 132874.1094 | 100%
24 | concrete vaults II | 2007-05-21 08:00 | 10d | 129748.9219 | 100%
50 | wind and water proof
25 | facades | 2007-06-04 08:00 | 20d | 351653.1875 | 100%
26 | outside windows | 2007-07-02 08:00 | 83d | 226446.59 | 90%
49 | roof | 2007-06-04 08:00 | 10d | 85523.5703 | 100%
62 | warehouse
28 | v0 concrete | 2007-07-25 08:00 | 5d | 142112 | 100%
30 | v0 sanitary | 2007-08-29 08:00 | 10d | 7673 | 100%
27 | v0 masonry | 2007-08-29 08:00 | 10d | 37704.9609 | 100%
59 | v0 heating | 2007-08-29 08:00 | 20d | 18563 | 100%
29 | v0 electricity | 2007-08-02 08:00 | 15d | 3840 | 100%
35 | v0 floors | 2007-09-26 08:00 | 20d | 81649.6016 | 100%
66 | construction leave
31 | construction leave | 2007-08-08 08:00 | 10d | 0.01 | 100%
63 | level 1
52 | v1 sanitary | 2007-08-29 08:00 | 10d | 7673 | 100%
45 | v1 masonry | 2007-08-29 08:00 | 10d | 37704.9609 | 100%
34 | v1 screed | 2007-08-29 08:00 | 15d | 106140 | 100%
60 | v1 heating | 2007-08-29 08:00 | 20d | 25475 | 100%
51 | v1 electricity | 2007-08-29 08:00 | 25d | 6400 | 100%
67 | v1 drying screed | 2007-09-19 08:00 | 5d | 0.01 | 100%
57 | v1 flooring | 2007-10-03 08:00 | 15d | 77487.2 | 80%
64 | level 2
53 | v2 sanitary | 2007-08-29 08:00 | 10d | 7673 | 100%
55 | v2 masonry | 2007-08-29 08:00 | 10d | 34452.9609 | 100%
56 | v2 screed | 2007-08-29 08:00 | 15d | 46116 | 100%
61 | v2 heating | 2007-08-29 08:00 | 20d | 16771 | 100%
54 | v2 electricity | 2007-08-29 08:00 | 20d | 5120 | 100%
68 | v2 drying screed | 2007-09-19 08:00 | 5d | 0.01 | 100%
58 | v2 flooring | 2007-09-26 08:00 | 20d | 38149.6016 | 100%
65 | completion
32 | stucco |  | 0 | 0 | 0%
36 | drywall |  | 0 | 0 | 0%
41 | kitchen and bar |  | 0 | 0 | 0%
37 | techniques |  | 0 | 0 | 0%
44 | stairs |  | 0 | 0 | 0%
42 | entrance doors |  | 0 | 0 | 0%
43 | elevator |  | 0 | 0 | 0%
38 | suspended ceiling |  | 0 | 0 | 0%
39 | painting |  | 0 | 0 | 0%
40 | furniture |  | 0 | 0 | 0%

## TP7
| TP Status Date | 2008-01-09 17:00 | TP Name | Completion
General |  | Tracking
ID | Name | Actual Start | Actual Duration | Actual Cost | Percentage Completed
CLAEYS-VERHELST
46 | preparation
2 | building permit | 2006-04-17 08:00 | 60d | 75 | 100%
3 | hire contractor | 2006-09-04 08:00 | 30d | 210000 | 100%
4 | temporary offices | 2006-04-17 08:00 | 20d | 3765.3101 | 100%
5 | temporary facilities | 2006-04-17 08:00 | 60d | 1876.54 | 100%
16 | preparation contractor | 2006-09-04 08:00 | 60d | 0.01 | 100%
6 | demolition | 2006-11-27 08:00 | 54d | 67701.7891 | 100%
47 | foundation
17 | excavation | 2007-02-08 08:00 | 10d | 29084.8008 | 100%
69 | soil analyses | 2007-02-08 08:00 | 12d | 5701.7603 | 100%
18 | foundation beam | 2007-02-28 08:00 | 22d | 118883.4062 | 100%
21 | placing sewerage | 2007-02-28 08:00 | 12d | 12330.0098 | 100%
23 | foundation plate | 2007-03-16 08:00 | 1d | 236361.8438 | 100%
48 | shell
19 | steelframe I | 2007-04-02 08:00 | 15d | 137501.3125 | 100%
20 | concrete vaults I | 2007-04-23 08:00 | 5d | 123579.3203 | 100%
22 | steelframe II | 2007-04-30 08:00 | 15d | 132874.1094 | 100%
24 | concrete vaults II | 2007-05-21 08:00 | 10d | 129748.9219 | 100%
50 | wind and water proof
25 | facades | 2007-06-04 08:00 | 20d | 351653.1875 | 100%
26 | outside windows | 2007-07-02 08:00 | 92d | 234654.5938 | 100%
49 | roof | 2007-06-04 08:00 | 10d | 85523.5703 | 100%
62 | warehouse
28 | v0 concrete | 2007-07-25 08:00 | 5d | 142112 | 100%
30 | v0 sanitary | 2007-08-29 08:00 | 10d | 7673 | 100%
27 | v0 masonry | 2007-08-29 08:00 | 10d | 37704.9609 | 100%
59 | v0 heating | 2007-08-29 08:00 | 20d | 18563 | 100%
29 | v0 electricity | 2007-08-02 08:00 | 15d | 3840 | 100%
35 | v0 floors | 2007-09-26 08:00 | 20d | 81649.6016 | 100%
66 | construction leave
31 | construction leave | 2007-08-08 08:00 | 10d | 0.01 | 100%
63 | level 1
52 | v1 sanitary | 2007-08-29 08:00 | 10d | 7673 | 100%
45 | v1 masonry | 2007-08-29 08:00 | 10d | 37704.9609 | 100%
34 | v1 screed | 2007-08-29 08:00 | 15d | 106140 | 100%
60 | v1 heating | 2007-08-29 08:00 | 20d | 25475 | 100%
51 | v1 electricity | 2007-08-29 08:00 | 25d | 6400 | 100%
67 | v1 drying screed | 2007-09-19 08:00 | 5d | 0.01 | 100%
57 | v1 flooring | 2007-10-03 08:00 | 20d | 79149.6016 | 100%
64 | level 2
53 | v2 sanitary | 2007-08-29 08:00 | 10d | 7673 | 100%
55 | v2 masonry | 2007-08-29 08:00 | 10d | 34452.9609 | 100%
56 | v2 screed | 2007-08-29 08:00 | 15d | 46116 | 100%
61 | v2 heating | 2007-08-29 08:00 | 20d | 16771 | 100%
54 | v2 electricity | 2007-08-29 08:00 | 20d | 5120 | 100%
68 | v2 drying screed | 2007-09-19 08:00 | 5d | 0.01 | 100%
58 | v2 flooring | 2007-09-26 08:00 | 20d | 38149.6016 | 100%
65 | completion
32 | stucco | 2007-11-05 08:00 | 15d | 23538.8008 | 100%
36 | drywall | 2007-11-05 08:00 | 25d | 48000 | 100%
41 | kitchen and bar | 2007-11-26 08:00 | 20d | 87000 | 100%
37 | techniques | 2007-11-26 08:00 | 15d | 2156.0601 | 100%
44 | stairs | 2007-12-10 08:00 | 10d | 33000 | 100%
42 | entrance doors | 2007-12-10 08:00 | 10d | 16000 | 100%
43 | elevator | 2007-12-10 08:00 | 5d | 38817.8516 | 100%
38 | suspended ceiling | 2007-12-10 08:00 | 5d | 32000 | 100%
39 | painting | 2007-12-17 08:00 | 15d | 99800 | 100%
40 | furniture | 2008-01-03 08:00 | 5d | 138400 | 100%