## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in days)
0 | Claeys-Verhelst Premises | 1 |  |  | 2006-04-17 08:00 | 2007-12-26 10:00 | 618d 2h |  | 0 | 2700210.3057 | 0 | 0 | 3027133.1861 | 618.0833
46 | preparation | 1.1 |  |  | 2006-04-17 08:00 | 2006-12-08 17:00 | 235d 9h |  | 0 | 216786.9701 | 0 | 0 | 253804.5701 | 235.375
2 | building permit | 1.1.1 |  | FS3+0 | 2006-04-17 08:00 | 2006-07-07 17:00 | 60d |  | 0 | 75 | 0 | 0 | 75 | 81.375
3 | hire contractor | 1.1.2 | 2FS+0 | FS16+0 | 2006-07-10 08:00 | 2006-08-04 17:00 | 20d |  | 0 | 210000 | 0 | 0 | 210000 | 25.375
4 | temporary offices | 1.1.3 |  |  | 2006-04-17 08:00 | 2006-05-12 17:00 | 20d |  | 0 | 3765.3101 | 0 | 0 | 3765.3101 | 25.375
5 | temporary facilities | 1.1.4 |  |  | 2006-04-17 08:00 | 2006-07-07 17:00 | 60d |  | 0 | 1876.54 | 0 | 0 | 1876.54 | 81.375
16 | preparation contractor | 1.1.5 | 3FS+0 | FS6+0 | 2006-08-07 08:00 | 2006-10-27 17:00 | 60d |  | 0 | 0.01 | 0 | 0 | 0.01 | 81.375
6 | demolition | 1.1.6 | 16FS+0 | FS17+0;FS69+0 | 2006-10-30 08:00 | 2006-12-08 17:00 | 30d | team VDW[4.0 #8] | 37017.6 | 1070.11 | 0 | 0 | 38087.71 | 39.375
47 | foundation | 1.2 |  |  | 2006-12-11 08:00 | 2007-02-01 17:00 | 52d 9h |  | 0 | 362567.894 | 0 | 0 | 401436.374 | 52.375
17 | excavation | 1.2.1 | 6FS+0 | FS18+0;FS21+0 | 2006-12-11 08:00 | 2006-12-28 17:00 | 14d | team VDW | 4318.72 | 26000 | 0 | 0 | 30318.72 | 17.375
69 | soil analyses | 1.2.2 | 6FS+0 | FS18+0 | 2006-12-11 08:00 | 2006-12-12 17:00 | 2d | team VDW | 616.96 | 2000 | 0 | 0 | 2616.96 | 1.375
18 | foundation beam | 1.2.3 | 17FS+0;69FS+0 | FS19+0 | 2006-12-29 08:00 | 2007-02-01 17:00 | 25d | team VDW[3.0 #8] | 23136 | 98523.7266 | 0 | 0 | 121659.7266 | 34.375
21 | placing sewerage | 1.2.4 | 17FS+0 | FS23+0 | 2006-12-29 08:00 | 2007-01-11 17:00 | 10d | team VDW[3.0 #8] | 9254.4 | 1224.73 | 0 | 0 | 10479.13 | 13.375
23 | foundation plate | 1.2.5 | 21FS+0 | FS19+0 | 2007-01-12 08:00 | 2007-01-12 17:00 | 1d | team VDW[5.0 #8] | 1542.4 | 234819.4375 | 0 | 0 | 236361.8375 | 0.375
48 | shell | 1.3 |  |  | 2007-02-02 08:00 | 2007-04-26 17:00 | 83d 9h |  | 0 | 472804.4531 | 0 | 0 | 542212.4531 | 83.375
19 | steelframe I | 1.3.1 | 18FS+0;23FS+0 | FS20+0 | 2007-02-02 08:00 | 2007-03-01 17:00 | 20d | team VDW[4.0 #8] | 24678.4 | 118992.5078 | 0 | 0 | 143670.9078 | 27.375
20 | concrete vaults I | 1.3.2 | 19FS+0 | FS22+0 | 2007-03-02 08:00 | 2007-03-15 17:00 | 10d | team VDW[4.0 #8] | 12339.2 | 117409.7188 | 0 | 0 | 129748.9187 | 13.375
22 | steelframe II | 1.3.3 | 20FS+0 | FS24+0 | 2007-03-16 08:00 | 2007-04-05 17:00 | 15d | team VDW[3.0 #8] | 13881.6 | 118992.5078 | 0 | 0 | 132874.1078 | 20.375
24 | concrete volt II | 1.3.4 | 22FS+0 | FS25+0;FS49+0 | 2007-04-06 08:00 | 2007-04-26 17:00 | 15d | team VDW[4.0 #8] | 18508.8 | 117409.7188 | 0 | 0 | 135918.5187 | 20.375
50 | wind and water proof | 1.4 |  |  | 2007-04-27 08:00 | 2007-06-07 17:00 | 41d 9h |  | 0 | 560844.1641 | 0 | 0 | 597047.364 | 41.375
25 | facades | 1.4.1 | 24FS+0 | FS26+0 | 2007-04-27 08:00 | 2007-05-24 17:00 | 20d | team VDW[2.0 #8] | 12339.2 | 339314 | 0 | 0 | 351653.2 | 27.375
26 | outside windows | 1.4.2 | 25FS+0 | FS28+0;FS29+0 | 2007-05-25 08:00 | 2007-06-07 17:00 | 10d | windows[3.0 #3] | 9120 | 150750.5938 | 0 | 0 | 159870.5938 | 13.375
49 | roof | 1.4.3 | 24FS+0 |  | 2007-04-27 08:00 | 2007-05-10 17:00 | 10d | roofing[4.0 #4] | 11520 | 70779.5703 | 40.3 | 3223.9999 | 85523.5703 | 13.375
62 | warehouse | 1.5 |  |  | 2007-06-08 08:00 | 2007-10-31 10:00 | 145d 2h |  | 0 | 257044.9609 | 0 | 0 | 301814.5611 | 145.0833
28 | v0 polierbeton | 1.5.1 | 26FS+0 | FS30+0;FS27+0;FS59+0;FS52+0;FS45+0;FS34+0;FS60+0;FS51+0 | 2007-06-08 08:00 | 2007-06-21 17:00 | 10d | team VDW[5.0 #8] | 15424 | 134400 | 0 | 0 | 149824 | 13.375
30 | v0 sanitary | 1.5.2 | 31FS+0;28FS+0 | FS35+0 | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 | 14
27 | v0 -masonry | 1.5.3 | 31FS+0;28FS+0 |  | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 40.65 | 3252.0001 | 37704.9611 | 14
59 | v0 heating | 1.5.4 | 31FS+0;28FS+0 | FS35+0 | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | heating | 6912 | 11651 | 0 | 0 | 18563 | 28
29 | v0 electricity | 1.5.5 | 26FS+0;31FS+0 | FS35+0 | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 | 35
35 | v0 floors | 1.5.6 | 59FS+0;29FS+0;30FS+0 | FS41+0;FS37+0 | 2007-10-03 10:00 | 2007-10-31 10:00 | 20d | flooring | 6649.6 | 75000 | 0 | 0 | 81649.6 | 28
66 | construction leave | 1.6 |  |  | 2007-08-15 10:00 | 2007-08-29 10:00 | 14d |  | 0 | 0.01 | 0 | 0 | 0.01 | 14
31 | construction leave | 1.6.1 |  | FS53+0;FS55+0;FS56+0;FS61+0;FS54+0;FS30+0;FS27+0;FS59+0;FS52+0;FS45+0;FS34+0;FS60+0;FS51+0;FS29+0 | 2007-08-15 10:00 | 2007-08-29 10:00 | 10d |  | 0 | 0.01 | 0 | 0 | 0.01 | 14
63 | level 1 | 1.7 |  |  | 2007-08-29 10:00 | 2007-10-24 10:00 | 56d |  | 0 | 226284.9709 | 0 | 0 | 262542.5712 | 56
52 | vI sanitary | 1.7.1 | 31FS+0;28FS+0 |  | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 | 14
45 | vI masonry | 1.7.2 | 31FS+0;28FS+0 |  | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 40.65 | 3252.0001 | 37704.9611 | 14
34 | v1screed | 1.7.3 | 31FS+0;28FS+0 | FS67+0 | 2007-08-29 10:00 | 2007-09-19 10:00 | 15d | chapen[2.0 #3] | 0 | 106140 | 0 | 0 | 106140 | 21
60 | v1 heating | 1.7.4 | 31FS+0;28FS+0 |  | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | heating | 6912 | 11651 | 43.2 | 6912.0001 | 25475.0001 | 28
51 | vI electricity | 1.7.5 | 31FS+0;28FS+0 |  | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 | 35
67 | v1 drying screed | 1.7.6 | 34FS+0 | FS57+0;FS32+0 | 2007-09-19 10:00 | 2007-09-26 10:00 | 5d |  | 0 | 0.01 | 0 | 0 | 0.01 | 7
57 | v1flooring | 1.7.7 | 67FS+0 | FS41+0;FS37+0;FS36+0 | 2007-09-26 10:00 | 2007-10-24 10:00 | 20d | flooring | 6649.6 | 72500 | 0 | 0 | 79149.6 | 28
64 | level 2 | 1.8 |  |  | 2007-08-29 10:00 | 2007-10-24 10:00 | 56d |  | 0 | 125260.9709 | 0 | 0 | 149562.5709 | 56
53 | v2 sanitary | 1.8.1 | 31FS+0 |  | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 | 14
55 | v2 masonry | 1.8.2 | 31FS+0 |  | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 0 | 0 | 34452.9609 | 14
56 | v2 screed | 1.8.3 | 31FS+0 | FS68+0;FS36+0 | 2007-08-29 10:00 | 2007-09-19 10:00 | 15d | chapen | 0 | 46116 | 0 | 0 | 46116 | 21
61 | v2 heating | 1.8.4 | 31FS+0 |  | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | electrician | 5120 | 11651 | 0 | 0 | 16771 | 28
54 | v2 electricity | 1.8.5 | 31FS+0 |  | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 | 35
68 | v2 drying screed | 1.8.6 | 56FS+0 | FS58+0;FS32+0 | 2007-09-19 10:00 | 2007-09-26 10:00 | 5d |  | 0 | 0.01 | 0 | 0 | 0.01 | 7
58 | v2 flooring | 1.8.7 | 68FS+0 | FS41+0;FS37+0;FS36+0 | 2007-09-26 10:00 | 2007-10-24 10:00 | 20d | flooring | 6649.6 | 31500 | 0 | 0 | 38149.6 | 28
65 | completion | 1.9 |  |  | 2007-09-26 10:00 | 2007-12-26 10:00 | 91d |  | 0 | 478615.9116 | 0 | 0 | 518712.7116 | 91
32 | stucco | 1.9.1 | 68FS+0;67FS+0 | FS41+0;FS37+0 | 2007-09-26 10:00 | 2007-10-17 10:00 | 15d | stucco[3.0 #4] | 14896.8 | 8642 | 0 | 0 | 23538.8 | 21
36 | drywall | 1.9.2 | 58FS+0;57FS+0;56FS+0 |  | 2007-10-24 10:00 | 2007-11-28 10:00 | 25d |  | 0 | 48000 | 0 | 0 | 48000 | 35
41 | kitchen and bar | 1.9.3 | 32FS+0;58FS+0;57FS+0;35FS+0 |  | 2007-10-31 10:00 | 2007-11-21 10:00 | 15d |  | 0 | 87000 | 0 | 0 | 87000 | 21
37 | techniques | 1.9.4 | 32FS+0;58FS+0;57FS+0;35FS+0 | FS38+0;FS42+0;FS43+0;FS44+0 | 2007-10-31 10:00 | 2007-11-21 10:00 | 15d |  | 0 | 2156.0601 | 0 | 0 | 2156.0601 | 21
44 | stairs | 1.9.5 | 37FS+0 |  | 2007-11-21 10:00 | 2007-12-05 10:00 | 10d |  | 0 | 33000 | 0 | 0 | 33000 | 14
42 | entrance doors | 1.9.6 | 37FS+0 |  | 2007-11-21 10:00 | 2007-12-05 10:00 | 10d |  | 0 | 16000 | 0 | 0 | 16000 | 14
43 | elevator | 1.9.7 | 37FS+0 |  | 2007-11-21 10:00 | 2007-11-28 10:00 | 5d |  | 0 | 38817.8516 | 0 | 0 | 38817.8516 | 7
38 | suspended ceiling | 1.9.8 | 37FS+0 | FS39+0 | 2007-11-21 10:00 | 2007-11-28 10:00 | 5d |  | 0 | 32000 | 0 | 0 | 32000 | 7
39 | painting | 1.9.9 | 38FS+0 | FS40+0 | 2007-11-28 10:00 | 2007-12-19 10:00 | 15d | painter[4.0 #6] | 16800 | 83000 | 0 | 0 | 99800 | 21
40 | furniture | 1.9.10 | 39FS+0 |  | 2007-12-19 10:00 | 2007-12-26 10:00 | 5d | furniture[5.0 #5] | 8400 | 130000 | 0 | 0 | 138400 | 7

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost
1 | plumber | Renewable | 4 #4 | 0 | 36 | 30;52;53; | 8640
2 | electrician | Renewable | 4 #4 | 0 | 32 | 29;51;61;54; | 24320
3 | team VDW | Renewable | 8 #8 | 0 | 38.56 | 6[4 #8];17;69;18[3 #8];21[3 #8];23[5 #8];19[4 #8];20[4 #8];22[3 #8];24[4 #8];25[2 #8];28[5 #8]; | 173057.28
4 | mason | Renewable | 4 #4 | 0 | 40.65 | 27;45;55; | 9756
5 | heating | Renewable | 2 #2 | 0 | 43.2 | 59;60; | 13824
6 | roofing | Renewable | 4 #4 | 0 | 36 | 49[4 #4]; | 11520
7 | windows | Renewable | 3 #3 | 0 | 38 | 26[3 #3]; | 9120
8 | flooring | Renewable | 4 #4 | 0 | 41.56 | 35;57;58; | 19948.8
9 | chapen | Renewable | 3 #3 | 0 | 0 | 34[2 #3];56; | 0
10 | stucco | Renewable | 4 #4 | 0 | 41.38 | 32[3 #4]; | 14896.8
11 | painter | Renewable | 6 #6 | 0 | 35 | 39[4 #6]; | 16800
12 | furniture | Renewable | 5 #5 | 0 | 42 | 40[5 #5]; | 8400

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic | Most probable | Pessimistic
0 | Claeys-Verhelst Premises | 618d 2h | manual - absolute | 0 | 0 | 0 | 0 | 0 | 0
46 | preparation | 235d 9h | manual - absolute | 0 | 0 | 0 | 0 | 0 | 0
2 | building permit | 60d | manual - absolute | 402 | 480 | 812 | 402 | 480 | 812
3 | hire contractor | 20d | manual - absolute | 127 | 160 | 326 | 127 | 160 | 326
4 | temporary offices | 20d | standard - symmetric | 80 | 100 | 120 | 128 | 160 | 192
5 | temporary facilities | 60d | standard - symmetric | 80 | 100 | 120 | 384 | 480 | 576
16 | preparation contractor | 60d | standard - no risk | 99 | 100 | 101 | 475 | 480 | 484
6 | demolition | 30d | manual - absolute | 219 | 240 | 302 | 219 | 240 | 302
47 | foundation | 52d 9h | manual - absolute | 0 | 0 | 0 | 0 | 0 | 0
17 | excavation | 14d | standard - symmetric | 80 | 100 | 120 | 89 | 112 | 134
69 | soil analyses | 2d | standard - symmetric | 80 | 100 | 120 | 12 | 16 | 19
18 | foundation beam | 25d | manual - absolute | 159 | 200 | 363 | 159 | 200 | 363
21 | placing sewerage | 10d | manual - absolute | 63 | 80 | 98 | 63 | 80 | 98
23 | foundation plate | 1d | manual - absolute | 6 | 8 | 10 | 6 | 8 | 10
48 | shell | 83d 9h | manual - absolute | 0 | 0 | 0 | 0 | 0 | 0
19 | steelframe I | 20d | manual - absolute | 104 | 120 | 166 | 104 | 120 | 166
20 | concrete vaults I | 10d | manual - absolute | 32 | 40 | 48 | 32 | 40 | 48
22 | steelframe II | 15d | manual - absolute | 64 | 80 | 113 | 64 | 80 | 113
24 | concrete volt II | 15d | manual - absolute | 66 | 80 | 121 | 66 | 80 | 121
50 | wind and water proof | 41d 9h | manual - absolute | 0 | 0 | 0 | 0 | 0 | 0
25 | facades | 20d | manual - absolute | 128 | 160 | 463 | 128 | 160 | 463
26 | outside windows | 10d | manual - absolute | 64 | 80 | 175 | 64 | 80 | 175
49 | roof | 10d | standard - symmetric | 80 | 100 | 120 | 64 | 80 | 96
62 | warehouse | 145d 2h | manual - absolute | 0 | 0 | 0 | 0 | 0 | 0
28 | v0 polierbeton | 10d | standard - symmetric | 80 | 100 | 120 | 64 | 80 | 96
30 | v0 sanitary | 10d | standard - no risk | 99 | 100 | 101 | 79 | 80 | 80
27 | v0 -masonry | 10d | standard - no risk | 99 | 100 | 101 | 79 | 80 | 80
59 | v0 heating | 20d | standard - no risk | 99 | 100 | 101 | 158 | 160 | 161
29 | v0 electricity | 25d | standard - no risk | 99 | 100 | 101 | 198 | 200 | 202
35 | v0 floors | 20d | manual - absolute | 128 | 163 | 543 | 128 | 163 | 543
66 | construction leave | 14d | manual - absolute | 0 | 0 | 0 | 0 | 0 | 0
31 | construction leave | 10d | standard - no risk | 99 | 100 | 101 | 79 | 80 | 80
63 | level 1 | 56d | manual - absolute | 0 | 0 | 0 | 0 | 0 | 0
52 | vI sanitary | 10d | standard - no risk | 99 | 100 | 101 | 79 | 80 | 80
45 | vI masonry | 10d | standard - no risk | 99 | 100 | 101 | 79 | 80 | 80
34 | v1screed | 15d | standard - no risk | 99 | 100 | 101 | 118 | 120 | 121
60 | v1 heating | 20d | standard - no risk | 99 | 100 | 101 | 158 | 160 | 161
51 | vI electricity | 25d | standard - no risk | 99 | 100 | 101 | 198 | 200 | 202
67 | v1 drying screed | 5d | standard - skewed left | 80 | 110 | 120 | 32 | 44 | 48
57 | v1flooring | 20d | manual - absolute | 128 | 160 | 577 | 128 | 160 | 577
64 | level 2 | 56d | manual - absolute | 0 | 0 | 0 | 0 | 0 | 0
53 | v2 sanitary | 10d | manual - absolute | 99 | 100 | 101 | 99 | 100 | 101
55 | v2 masonry | 10d | manual - absolute | 99 | 100 | 101 | 99 | 100 | 101
56 | v2 screed | 15d | manual - absolute | 80 | 110 | 120 | 80 | 110 | 120
61 | v2 heating | 20d | manual - absolute | 80 | 110 | 120 | 80 | 110 | 120
54 | v2 electricity | 25d | manual - absolute | 99 | 100 | 101 | 99 | 100 | 101
68 | v2 drying screed | 5d | manual - absolute | 80 | 110 | 120 | 80 | 110 | 120
58 | v2 flooring | 20d | manual - absolute | 128 | 160 | 556 | 128 | 160 | 556
65 | completion | 91d | manual - absolute | 0 | 0 | 0 | 0 | 0 | 0
32 | stucco | 15d | manual - absolute | 96 | 120 | 451 | 96 | 120 | 451
36 | drywall | 25d | manual - absolute | 160 | 200 | 528 | 160 | 200 | 528
41 | kitchen and bar | 15d | standard - symmetric | 80 | 100 | 120 | 96 | 120 | 144
37 | techniques | 15d | standard - symmetric | 80 | 100 | 120 | 96 | 120 | 144
44 | stairs | 10d | standard - symmetric | 80 | 100 | 120 | 64 | 80 | 96
42 | entrance doors | 10d | standard - symmetric | 80 | 100 | 120 | 64 | 80 | 96
43 | elevator | 5d | standard - symmetric | 80 | 100 | 120 | 32 | 40 | 48
38 | suspended ceiling | 5d | standard - symmetric | 80 | 100 | 120 | 32 | 40 | 48
39 | painting | 15d | standard - symmetric | 80 | 100 | 120 | 96 | 120 | 144
40 | furniture | 5d | standard - symmetric | 80 | 100 | 120 | 32 | 40 | 48

## Project Control - TP1
| TP Status Date | 2006-07-07 08:00 |  | TP Name | Preparation1
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Absolute baseline duration | Absolute actual duration | Absolute completed | Baseline cost | Actual cost | Absolute percentage completed
2 | building permit | 2006-04-17 08:00 | 2006-07-07 17:00 | 60d |  | 0 | 75 | 0 | 0 | 75 | 2006-04-17 08:00 | 100d | 74.2574 | 0.74257 | 1d | 0 | 0 | 74.2574 | 0.74257 | 99.0099012851715% | Started | 75 | 75
3 | hire contractor | 2006-07-10 08:00 | 2006-08-04 17:00 | 20d |  | 0 | 210000 | 0 | 0 | 210000 | 2958466 | 0 | 0 | 210000 | 20d | 0 | 0 | 0 | 210000 | 0.0% | Not Started | 0 | 210000
4 | temporary offices | 2006-04-17 08:00 | 2006-05-12 17:00 | 20d |  | 0 | 3765.3101 | 0 | 0 | 3765.3101 | 2006-04-17 08:00 | 20d | 3765.3101 | 0 | 0 | 0 | 0 | 3765.3101 | 0 | 100.0% | Finished | 3765.3101 | 3765.3101
5 | temporary facilities | 2006-04-17 08:00 | 2006-07-07 17:00 | 60d |  | 0 | 1876.54 | 0 | 0 | 1876.54 | 2006-04-17 08:00 | 60d | 1845.7779 | 30.7621 | 1d | 0 | 0 | 1845.7779 | 30.7621 | 98.3606994152069% | Started | 1876.54 | 1876.54
6 | demolition | 2006-10-30 08:00 | 2006-12-08 17:00 | 30d | team VDW[4.0 #8] | 37017.6 | 1070.11 | 0 | 0 | 38087.71 | 2958466 | 0 | 0 | 38087.71 | 30d | 0 | 0 | 0 | 38087.71 | 0.0% | Not Started | 0 | 38087.71
16 | preparation contractor | 2006-08-07 08:00 | 2006-10-27 17:00 | 60d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2958466 | 0 | 0 | 0.01 | 60d | 0 | 0 | 0 | 0.01 | 0.0% | Not Started | 0 | 0.01
17 | excavation | 2006-12-11 08:00 | 2006-12-28 17:00 | 14d | team VDW | 4318.72 | 26000 | 0 | 0 | 30318.72 | 2958466 | 0 | 0 | 30318.72 | 14d | 0 | 0 | 0 | 30318.72 | 0.0% | Not Started | 0 | 30318.72
18 | foundation beam | 2006-12-29 08:00 | 2007-02-01 17:00 | 25d | team VDW[3.0 #8] | 23136 | 98523.7266 | 0 | 0 | 121659.7266 | 2958466 | 0 | 0 | 121659.7266 | 25d | 0 | 0 | 0 | 121659.7266 | 0.0% | Not Started | 0 | 121659.7266
19 | steelframe I | 2007-02-02 08:00 | 2007-03-01 17:00 | 20d | team VDW[4.0 #8] | 24678.4 | 118992.5078 | 0 | 0 | 143670.9078 | 2958466 | 0 | 0 | 143670.9078 | 20d | 0 | 0 | 0 | 143670.9078 | 0.0% | Not Started | 0 | 143670.9078
20 | concrete vaults I | 2007-03-02 08:00 | 2007-03-15 17:00 | 10d | team VDW[4.0 #8] | 12339.2 | 117409.7188 | 0 | 0 | 129748.9187 | 2958466 | 0 | 0 | 129748.9187 | 10d | 0 | 0 | 0 | 129748.9187 | 0.0% | Not Started | 0 | 129748.9187
21 | placing sewerage | 2006-12-29 08:00 | 2007-01-11 17:00 | 10d | team VDW[3.0 #8] | 9254.4 | 1224.73 | 0 | 0 | 10479.13 | 2958466 | 0 | 0 | 10479.13 | 10d | 0 | 0 | 0 | 10479.13 | 0.0% | Not Started | 0 | 10479.13
22 | steelframe II | 2007-03-16 08:00 | 2007-04-05 17:00 | 15d | team VDW[3.0 #8] | 13881.6 | 118992.5078 | 0 | 0 | 132874.1078 | 2958466 | 0 | 0 | 132874.1078 | 15d | 0 | 0 | 0 | 132874.1078 | 0.0% | Not Started | 0 | 132874.1078
23 | foundation plate | 2007-01-12 08:00 | 2007-01-12 17:00 | 1d | team VDW[5.0 #8] | 1542.4 | 234819.4375 | 0 | 0 | 236361.8375 | 2958466 | 0 | 0 | 236361.8375 | 1d | 0 | 0 | 0 | 236361.8375 | 0.0% | Not Started | 0 | 236361.8375
24 | concrete volt II | 2007-04-06 08:00 | 2007-04-26 17:00 | 15d | team VDW[4.0 #8] | 18508.8 | 117409.7188 | 0 | 0 | 135918.5187 | 2958466 | 0 | 0 | 135918.5187 | 15d | 0 | 0 | 0 | 135918.5187 | 0.0% | Not Started | 0 | 135918.5187
25 | facades | 2007-04-27 08:00 | 2007-05-24 17:00 | 20d | team VDW[2.0 #8] | 12339.2 | 339314 | 0 | 0 | 351653.2 | 2958466 | 0 | 0 | 351653.2 | 20d | 0 | 0 | 0 | 351653.2 | 0.0% | Not Started | 0 | 351653.2
26 | outside windows | 2007-05-25 08:00 | 2007-06-07 17:00 | 10d | windows[3.0 #3] | 9120 | 150750.5938 | 0 | 0 | 159870.5938 | 2958466 | 0 | 0 | 159870.5938 | 10d | 0 | 0 | 0 | 159870.5938 | 0.0% | Not Started | 0 | 159870.5938
27 | v0 -masonry | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 40.65 | 3252.0001 | 37704.9611 | 2958466 | 0 | 0 | 37704.9611 | 10d | 0 | 0 | 0 | 37704.9611 | 0.0% | Not Started | 0 | 37704.9611
28 | v0 polierbeton | 2007-06-08 08:00 | 2007-06-21 17:00 | 10d | team VDW[5.0 #8] | 15424 | 134400 | 0 | 0 | 149824 | 2958466 | 0 | 0 | 149824 | 10d | 0 | 0 | 0 | 149824 | 0.0% | Not Started | 0 | 149824
29 | v0 electricity | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 | 2958466 | 0 | 0 | 6400 | 25d | 0 | 0 | 0 | 6400 | 0.0% | Not Started | 0 | 6400
30 | v0 sanitary | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 | 2958466 | 0 | 0 | 7673 | 10d | 0 | 0 | 0 | 7673 | 0.0% | Not Started | 0 | 7673
31 | construction leave | 2007-08-15 10:00 | 2007-08-29 10:00 | 10d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2958466 | 0 | 0 | 0.01 | 10d | 0 | 0 | 0 | 0.01 | 0.0% | Not Started | 0 | 0.01
32 | stucco | 2007-09-26 10:00 | 2007-10-17 10:00 | 15d | stucco[3.0 #4] | 14896.8 | 8642 | 0 | 0 | 23538.8 | 2958466 | 0 | 0 | 23538.8 | 15d | 0 | 0 | 0 | 23538.8 | 0.0% | Not Started | 0 | 23538.8
34 | v1screed | 2007-08-29 10:00 | 2007-09-19 10:00 | 15d | chapen[2.0 #3] | 0 | 106140 | 0 | 0 | 106140 | 2958466 | 0 | 0 | 106140 | 15d | 0 | 0 | 0 | 106140 | 0.0% | Not Started | 0 | 106140
35 | v0 floors | 2007-10-03 10:00 | 2007-10-31 10:00 | 20d | flooring | 6649.6 | 75000 | 0 | 0 | 81649.6 | 2958466 | 0 | 0 | 81649.6 | 20d | 0 | 0 | 0 | 81649.6 | 0.0% | Not Started | 0 | 81649.6
36 | drywall | 2007-10-24 10:00 | 2007-11-28 10:00 | 25d |  | 0 | 48000 | 0 | 0 | 48000 | 2958466 | 0 | 0 | 48000 | 25d | 0 | 0 | 0 | 48000 | 0.0% | Not Started | 0 | 48000
37 | techniques | 2007-10-31 10:00 | 2007-11-21 10:00 | 15d |  | 0 | 2156.0601 | 0 | 0 | 2156.0601 | 2958466 | 0 | 0 | 2156.0601 | 15d | 0 | 0 | 0 | 2156.0601 | 0.0% | Not Started | 0 | 2156.0601
38 | suspended ceiling | 2007-11-21 10:00 | 2007-11-28 10:00 | 5d |  | 0 | 32000 | 0 | 0 | 32000 | 2958466 | 0 | 0 | 32000 | 5d | 0 | 0 | 0 | 32000 | 0.0% | Not Started | 0 | 32000
39 | painting | 2007-11-28 10:00 | 2007-12-19 10:00 | 15d | painter[4.0 #6] | 16800 | 83000 | 0 | 0 | 99800 | 2958466 | 0 | 0 | 99800 | 15d | 0 | 0 | 0 | 99800 | 0.0% | Not Started | 0 | 99800
40 | furniture | 2007-12-19 10:00 | 2007-12-26 10:00 | 5d | furniture[5.0 #5] | 8400 | 130000 | 0 | 0 | 138400 | 2958466 | 0 | 0 | 138400 | 5d | 0 | 0 | 0 | 138400 | 0.0% | Not Started | 0 | 138400
41 | kitchen and bar | 2007-10-31 10:00 | 2007-11-21 10:00 | 15d |  | 0 | 87000 | 0 | 0 | 87000 | 2958466 | 0 | 0 | 87000 | 15d | 0 | 0 | 0 | 87000 | 0.0% | Not Started | 0 | 87000
42 | entrance doors | 2007-11-21 10:00 | 2007-12-05 10:00 | 10d |  | 0 | 16000 | 0 | 0 | 16000 | 2958466 | 0 | 0 | 16000 | 10d | 0 | 0 | 0 | 16000 | 0.0% | Not Started | 0 | 16000
43 | elevator | 2007-11-21 10:00 | 2007-11-28 10:00 | 5d |  | 0 | 38817.8516 | 0 | 0 | 38817.8516 | 2958466 | 0 | 0 | 38817.8516 | 5d | 0 | 0 | 0 | 38817.8516 | 0.0% | Not Started | 0 | 38817.8516
44 | stairs | 2007-11-21 10:00 | 2007-12-05 10:00 | 10d |  | 0 | 33000 | 0 | 0 | 33000 | 2958466 | 0 | 0 | 33000 | 10d | 0 | 0 | 0 | 33000 | 0.0% | Not Started | 0 | 33000
45 | vI masonry | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 40.65 | 3252.0001 | 37704.9611 | 2958466 | 0 | 0 | 37704.9611 | 10d | 0 | 0 | 0 | 37704.9611 | 0.0% | Not Started | 0 | 37704.9611
49 | roof | 2007-04-27 08:00 | 2007-05-10 17:00 | 10d | roofing[4.0 #4] | 11520 | 70779.5703 | 40.3 | 3223.9999 | 85523.5703 | 2958466 | 0 | 0 | 85523.5703 | 10d | 0 | 0 | 0 | 85523.5703 | 0.0% | Not Started | 0 | 85523.5703
51 | vI electricity | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 | 2958466 | 0 | 0 | 6400 | 25d | 0 | 0 | 0 | 6400 | 0.0% | Not Started | 0 | 6400
52 | vI sanitary | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 | 2958466 | 0 | 0 | 7673 | 10d | 0 | 0 | 0 | 7673 | 0.0% | Not Started | 0 | 7673
53 | v2 sanitary | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 | 2958466 | 0 | 0 | 7673 | 10d | 0 | 0 | 0 | 7673 | 0.0% | Not Started | 0 | 7673
54 | v2 electricity | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 | 2958466 | 0 | 0 | 6400 | 25d | 0 | 0 | 0 | 6400 | 0.0% | Not Started | 0 | 6400
55 | v2 masonry | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 0 | 0 | 34452.9609 | 2958466 | 0 | 0 | 34452.9609 | 10d | 0 | 0 | 0 | 34452.9609 | 0.0% | Not Started | 0 | 34452.9609
56 | v2 screed | 2007-08-29 10:00 | 2007-09-19 10:00 | 15d | chapen | 0 | 46116 | 0 | 0 | 46116 | 2958466 | 0 | 0 | 46116 | 15d | 0 | 0 | 0 | 46116 | 0.0% | Not Started | 0 | 46116
57 | v1flooring | 2007-09-26 10:00 | 2007-10-24 10:00 | 20d | flooring | 6649.6 | 72500 | 0 | 0 | 79149.6 | 2958466 | 0 | 0 | 79149.6 | 20d | 0 | 0 | 0 | 79149.6 | 0.0% | Not Started | 0 | 79149.6
58 | v2 flooring | 2007-09-26 10:00 | 2007-10-24 10:00 | 20d | flooring | 6649.6 | 31500 | 0 | 0 | 38149.6 | 2958466 | 0 | 0 | 38149.6 | 20d | 0 | 0 | 0 | 38149.6 | 0.0% | Not Started | 0 | 38149.6
59 | v0 heating | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | heating | 6912 | 11651 | 0 | 0 | 18563 | 2958466 | 0 | 0 | 18563 | 20d | 0 | 0 | 0 | 18563 | 0.0% | Not Started | 0 | 18563
60 | v1 heating | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | heating | 6912 | 11651 | 43.2 | 6912.0001 | 25475.0001 | 2958466 | 0 | 0 | 25475.0001 | 20d | 0 | 0 | 0 | 25475.0001 | 0.0% | Not Started | 0 | 25475.0001
61 | v2 heating | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | electrician | 5120 | 11651 | 0 | 0 | 16771 | 2958466 | 0 | 0 | 16771 | 20d | 0 | 0 | 0 | 16771 | 0.0% | Not Started | 0 | 16771
67 | v1 drying screed | 2007-09-19 10:00 | 2007-09-26 10:00 | 5d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2958466 | 0 | 0 | 0.01 | 5d | 0 | 0 | 0 | 0.01 | 0.0% | Not Started | 0 | 0.01
68 | v2 drying screed | 2007-09-19 10:00 | 2007-09-26 10:00 | 5d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2958466 | 0 | 0 | 0.01 | 5d | 0 | 0 | 0 | 0.01 | 0.0% | Not Started | 0 | 0.01
69 | soil analyses | 2006-12-11 08:00 | 2006-12-12 17:00 | 2d | team VDW | 616.96 | 2000 | 0 | 0 | 2616.96 | 2958466 | 0 | 0 | 2616.96 | 2d | 0 | 0 | 0 | 2616.96 | 0.0% | Not Started | 0 | 2616.96

## TP2
| TP Status Date | 2007-02-08 08:00 |  | TP Name | Preparation2
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Absolute baseline duration | Absolute actual duration | Absolute completed | Baseline cost | Actual cost | Absolute percentage completed
2 | building permit | 2006-04-17 08:00 | 2006-07-07 17:00 | 60d |  | 0 | 75 | 0 | 0 | 75 | 2006-04-17 08:00 | 100d | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100.0% | Finished | 75 | 75
3 | hire contractor | 2006-07-10 08:00 | 2006-08-04 17:00 | 20d |  | 0 | 210000 | 0 | 0 | 210000 | 2006-09-04 08:00 | 30d | 210000 | 0 | 0 | 0 | 0 | 210000 | 0 | 100.0% | Finished | 210000 | 210000
4 | temporary offices | 2006-04-17 08:00 | 2006-05-12 17:00 | 20d |  | 0 | 3765.3101 | 0 | 0 | 3765.3101 | 2006-04-17 08:00 | 20d | 3765.3101 | 0 | 0 | 0 | 0 | 3765.3101 | 0 | 100.0% | Finished | 3765.3101 | 3765.3101
5 | temporary facilities | 2006-04-17 08:00 | 2006-07-07 17:00 | 60d |  | 0 | 1876.54 | 0 | 0 | 1876.54 | 2006-04-17 08:00 | 60d | 1876.54 | 0 | 0 | 0 | 0 | 1876.54 | 0 | 100.0% | Finished | 1876.54 | 1876.54
6 | demolition | 2006-10-30 08:00 | 2006-12-08 17:00 | 30d | team VDW[4.0 #8] | 37017.6 | 1070.11 | 0 | 0 | 38087.71 | 2006-11-27 08:00 | 54d | 38087.71 | 0 | 0 | 0 | 0 | 38087.71 | 0 | 100.0% | Finished | 38087.71 | 38087.71
16 | preparation contractor | 2006-08-07 08:00 | 2006-10-27 17:00 | 60d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2006-09-04 08:00 | 60d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100.0% | Finished | 0.01 | 0.01
17 | excavation | 2006-12-11 08:00 | 2006-12-28 17:00 | 14d | team VDW | 4318.72 | 26000 | 0 | 0 | 30318.72 | 2958466 | 0 | 0 | 30318.72 | 14d | 0 | 0 | 0 | 30318.72 | 0.0% | Not Started | 0 | 30318.72
18 | foundation beam | 2006-12-29 08:00 | 2007-02-01 17:00 | 25d | team VDW[3.0 #8] | 23136 | 98523.7266 | 0 | 0 | 121659.7266 | 2958466 | 0 | 0 | 121659.7266 | 25d | 0 | 0 | 0 | 121659.7266 | 0.0% | Not Started | 0 | 121659.7266
19 | steelframe I | 2007-02-02 08:00 | 2007-03-01 17:00 | 20d | team VDW[4.0 #8] | 24678.4 | 118992.5078 | 0 | 0 | 143670.9078 | 2958466 | 0 | 0 | 143670.9078 | 20d | 0 | 0 | 0 | 143670.9078 | 0.0% | Not Started | 0 | 143670.9078
20 | concrete vaults I | 2007-03-02 08:00 | 2007-03-15 17:00 | 10d | team VDW[4.0 #8] | 12339.2 | 117409.7188 | 0 | 0 | 129748.9187 | 2958466 | 0 | 0 | 129748.9187 | 10d | 0 | 0 | 0 | 129748.9187 | 0.0% | Not Started | 0 | 129748.9187
21 | placing sewerage | 2006-12-29 08:00 | 2007-01-11 17:00 | 10d | team VDW[3.0 #8] | 9254.4 | 1224.73 | 0 | 0 | 10479.13 | 2958466 | 0 | 0 | 10479.13 | 10d | 0 | 0 | 0 | 10479.13 | 0.0% | Not Started | 0 | 10479.13
22 | steelframe II | 2007-03-16 08:00 | 2007-04-05 17:00 | 15d | team VDW[3.0 #8] | 13881.6 | 118992.5078 | 0 | 0 | 132874.1078 | 2958466 | 0 | 0 | 132874.1078 | 15d | 0 | 0 | 0 | 132874.1078 | 0.0% | Not Started | 0 | 132874.1078
23 | foundation plate | 2007-01-12 08:00 | 2007-01-12 17:00 | 1d | team VDW[5.0 #8] | 1542.4 | 234819.4375 | 0 | 0 | 236361.8375 | 2958466 | 0 | 0 | 236361.8375 | 1d | 0 | 0 | 0 | 236361.8375 | 0.0% | Not Started | 0 | 236361.8375
24 | concrete volt II | 2007-04-06 08:00 | 2007-04-26 17:00 | 15d | team VDW[4.0 #8] | 18508.8 | 117409.7188 | 0 | 0 | 135918.5187 | 2958466 | 0 | 0 | 135918.5187 | 15d | 0 | 0 | 0 | 135918.5187 | 0.0% | Not Started | 0 | 135918.5187
25 | facades | 2007-04-27 08:00 | 2007-05-24 17:00 | 20d | team VDW[2.0 #8] | 12339.2 | 339314 | 0 | 0 | 351653.2 | 2958466 | 0 | 0 | 351653.2 | 20d | 0 | 0 | 0 | 351653.2 | 0.0% | Not Started | 0 | 351653.2
26 | outside windows | 2007-05-25 08:00 | 2007-06-07 17:00 | 10d | windows[3.0 #3] | 9120 | 150750.5938 | 0 | 0 | 159870.5938 | 2958466 | 0 | 0 | 159870.5938 | 10d | 0 | 0 | 0 | 159870.5938 | 0.0% | Not Started | 0 | 159870.5938
27 | v0 -masonry | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 40.65 | 3252.0001 | 37704.9611 | 2958466 | 0 | 0 | 37704.9611 | 10d | 0 | 0 | 0 | 37704.9611 | 0.0% | Not Started | 0 | 37704.9611
28 | v0 polierbeton | 2007-06-08 08:00 | 2007-06-21 17:00 | 10d | team VDW[5.0 #8] | 15424 | 134400 | 0 | 0 | 149824 | 2958466 | 0 | 0 | 149824 | 10d | 0 | 0 | 0 | 149824 | 0.0% | Not Started | 0 | 149824
29 | v0 electricity | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 | 2958466 | 0 | 0 | 6400 | 25d | 0 | 0 | 0 | 6400 | 0.0% | Not Started | 0 | 6400
30 | v0 sanitary | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 | 2958466 | 0 | 0 | 7673 | 10d | 0 | 0 | 0 | 7673 | 0.0% | Not Started | 0 | 7673
31 | construction leave | 2007-08-15 10:00 | 2007-08-29 10:00 | 10d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2958466 | 0 | 0 | 0.01 | 10d | 0 | 0 | 0 | 0.01 | 0.0% | Not Started | 0 | 0.01
32 | stucco | 2007-09-26 10:00 | 2007-10-17 10:00 | 15d | stucco[3.0 #4] | 14896.8 | 8642 | 0 | 0 | 23538.8 | 2958466 | 0 | 0 | 23538.8 | 15d | 0 | 0 | 0 | 23538.8 | 0.0% | Not Started | 0 | 23538.8
34 | v1screed | 2007-08-29 10:00 | 2007-09-19 10:00 | 15d | chapen[2.0 #3] | 0 | 106140 | 0 | 0 | 106140 | 2958466 | 0 | 0 | 106140 | 15d | 0 | 0 | 0 | 106140 | 0.0% | Not Started | 0 | 106140
35 | v0 floors | 2007-10-03 10:00 | 2007-10-31 10:00 | 20d | flooring | 6649.6 | 75000 | 0 | 0 | 81649.6 | 2958466 | 0 | 0 | 81649.6 | 20d | 0 | 0 | 0 | 81649.6 | 0.0% | Not Started | 0 | 81649.6
36 | drywall | 2007-10-24 10:00 | 2007-11-28 10:00 | 25d |  | 0 | 48000 | 0 | 0 | 48000 | 2958466 | 0 | 0 | 48000 | 25d | 0 | 0 | 0 | 48000 | 0.0% | Not Started | 0 | 48000
37 | techniques | 2007-10-31 10:00 | 2007-11-21 10:00 | 15d |  | 0 | 2156.0601 | 0 | 0 | 2156.0601 | 2958466 | 0 | 0 | 2156.0601 | 15d | 0 | 0 | 0 | 2156.0601 | 0.0% | Not Started | 0 | 2156.0601
38 | suspended ceiling | 2007-11-21 10:00 | 2007-11-28 10:00 | 5d |  | 0 | 32000 | 0 | 0 | 32000 | 2958466 | 0 | 0 | 32000 | 5d | 0 | 0 | 0 | 32000 | 0.0% | Not Started | 0 | 32000
39 | painting | 2007-11-28 10:00 | 2007-12-19 10:00 | 15d | painter[4.0 #6] | 16800 | 83000 | 0 | 0 | 99800 | 2958466 | 0 | 0 | 99800 | 15d | 0 | 0 | 0 | 99800 | 0.0% | Not Started | 0 | 99800
40 | furniture | 2007-12-19 10:00 | 2007-12-26 10:00 | 5d | furniture[5.0 #5] | 8400 | 130000 | 0 | 0 | 138400 | 2958466 | 0 | 0 | 138400 | 5d | 0 | 0 | 0 | 138400 | 0.0% | Not Started | 0 | 138400
41 | kitchen and bar | 2007-10-31 10:00 | 2007-11-21 10:00 | 15d |  | 0 | 87000 | 0 | 0 | 87000 | 2958466 | 0 | 0 | 87000 | 15d | 0 | 0 | 0 | 87000 | 0.0% | Not Started | 0 | 87000
42 | entrance doors | 2007-11-21 10:00 | 2007-12-05 10:00 | 10d |  | 0 | 16000 | 0 | 0 | 16000 | 2958466 | 0 | 0 | 16000 | 10d | 0 | 0 | 0 | 16000 | 0.0% | Not Started | 0 | 16000
43 | elevator | 2007-11-21 10:00 | 2007-11-28 10:00 | 5d |  | 0 | 38817.8516 | 0 | 0 | 38817.8516 | 2958466 | 0 | 0 | 38817.8516 | 5d | 0 | 0 | 0 | 38817.8516 | 0.0% | Not Started | 0 | 38817.8516
44 | stairs | 2007-11-21 10:00 | 2007-12-05 10:00 | 10d |  | 0 | 33000 | 0 | 0 | 33000 | 2958466 | 0 | 0 | 33000 | 10d | 0 | 0 | 0 | 33000 | 0.0% | Not Started | 0 | 33000
45 | vI masonry | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 40.65 | 3252.0001 | 37704.9611 | 2958466 | 0 | 0 | 37704.9611 | 10d | 0 | 0 | 0 | 37704.9611 | 0.0% | Not Started | 0 | 37704.9611
49 | roof | 2007-04-27 08:00 | 2007-05-10 17:00 | 10d | roofing[4.0 #4] | 11520 | 70779.5703 | 40.3 | 3223.9999 | 85523.5703 | 2958466 | 0 | 0 | 85523.5703 | 10d | 0 | 0 | 0 | 85523.5703 | 0.0% | Not Started | 0 | 85523.5703
51 | vI electricity | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 | 2958466 | 0 | 0 | 6400 | 25d | 0 | 0 | 0 | 6400 | 0.0% | Not Started | 0 | 6400
52 | vI sanitary | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 | 2958466 | 0 | 0 | 7673 | 10d | 0 | 0 | 0 | 7673 | 0.0% | Not Started | 0 | 7673
53 | v2 sanitary | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 | 2958466 | 0 | 0 | 7673 | 10d | 0 | 0 | 0 | 7673 | 0.0% | Not Started | 0 | 7673
54 | v2 electricity | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 | 2958466 | 0 | 0 | 6400 | 25d | 0 | 0 | 0 | 6400 | 0.0% | Not Started | 0 | 6400
55 | v2 masonry | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 0 | 0 | 34452.9609 | 2958466 | 0 | 0 | 34452.9609 | 10d | 0 | 0 | 0 | 34452.9609 | 0.0% | Not Started | 0 | 34452.9609
56 | v2 screed | 2007-08-29 10:00 | 2007-09-19 10:00 | 15d | chapen | 0 | 46116 | 0 | 0 | 46116 | 2958466 | 0 | 0 | 46116 | 15d | 0 | 0 | 0 | 46116 | 0.0% | Not Started | 0 | 46116
57 | v1flooring | 2007-09-26 10:00 | 2007-10-24 10:00 | 20d | flooring | 6649.6 | 72500 | 0 | 0 | 79149.6 | 2958466 | 0 | 0 | 79149.6 | 20d | 0 | 0 | 0 | 79149.6 | 0.0% | Not Started | 0 | 79149.6
58 | v2 flooring | 2007-09-26 10:00 | 2007-10-24 10:00 | 20d | flooring | 6649.6 | 31500 | 0 | 0 | 38149.6 | 2958466 | 0 | 0 | 38149.6 | 20d | 0 | 0 | 0 | 38149.6 | 0.0% | Not Started | 0 | 38149.6
59 | v0 heating | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | heating | 6912 | 11651 | 0 | 0 | 18563 | 2958466 | 0 | 0 | 18563 | 20d | 0 | 0 | 0 | 18563 | 0.0% | Not Started | 0 | 18563
60 | v1 heating | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | heating | 6912 | 11651 | 43.2 | 6912.0001 | 25475.0001 | 2958466 | 0 | 0 | 25475.0001 | 20d | 0 | 0 | 0 | 25475.0001 | 0.0% | Not Started | 0 | 25475.0001
61 | v2 heating | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | electrician | 5120 | 11651 | 0 | 0 | 16771 | 2958466 | 0 | 0 | 16771 | 20d | 0 | 0 | 0 | 16771 | 0.0% | Not Started | 0 | 16771
67 | v1 drying screed | 2007-09-19 10:00 | 2007-09-26 10:00 | 5d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2958466 | 0 | 0 | 0.01 | 5d | 0 | 0 | 0 | 0.01 | 0.0% | Not Started | 0 | 0.01
68 | v2 drying screed | 2007-09-19 10:00 | 2007-09-26 10:00 | 5d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2958466 | 0 | 0 | 0.01 | 5d | 0 | 0 | 0 | 0.01 | 0.0% | Not Started | 0 | 0.01
69 | soil analyses | 2006-12-11 08:00 | 2006-12-12 17:00 | 2d | team VDW | 616.96 | 2000 | 0 | 0 | 2616.96 | 2958466 | 0 | 0 | 2616.96 | 2d | 0 | 0 | 0 | 2616.96 | 0.0% | Not Started | 0 | 2616.96

## TP3
| TP Status Date | 2007-03-17 08:00 |  | TP Name | Foundation
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Absolute baseline duration | Absolute actual duration | Absolute completed | Baseline cost | Actual cost | Absolute percentage completed
2 | building permit | 2006-04-17 08:00 | 2006-07-07 17:00 | 60d |  | 0 | 75 | 0 | 0 | 75 | 2006-04-17 08:00 | 100d | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100.0% | Finished | 75 | 75
3 | hire contractor | 2006-07-10 08:00 | 2006-08-04 17:00 | 20d |  | 0 | 210000 | 0 | 0 | 210000 | 2006-09-04 08:00 | 30d | 210000 | 0 | 0 | 0 | 0 | 210000 | 0 | 100.0% | Finished | 210000 | 210000
4 | temporary offices | 2006-04-17 08:00 | 2006-05-12 17:00 | 20d |  | 0 | 3765.3101 | 0 | 0 | 3765.3101 | 2006-04-17 08:00 | 20d | 3765.3101 | 0 | 0 | 0 | 0 | 3765.3101 | 0 | 100.0% | Finished | 3765.3101 | 3765.3101
5 | temporary facilities | 2006-04-17 08:00 | 2006-07-07 17:00 | 60d |  | 0 | 1876.54 | 0 | 0 | 1876.54 | 2006-04-17 08:00 | 60d | 1876.54 | 0 | 0 | 0 | 0 | 1876.54 | 0 | 100.0% | Finished | 1876.54 | 1876.54
6 | demolition | 2006-10-30 08:00 | 2006-12-08 17:00 | 30d | team VDW[4.0 #8] | 37017.6 | 1070.11 | 0 | 0 | 38087.71 | 2006-11-27 08:00 | 54d | 38087.71 | 0 | 0 | 0 | 0 | 38087.71 | 0 | 100.0% | Finished | 38087.71 | 38087.71
16 | preparation contractor | 2006-08-07 08:00 | 2006-10-27 17:00 | 60d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2006-09-04 08:00 | 60d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100.0% | Finished | 0.01 | 0.01
17 | excavation | 2006-12-11 08:00 | 2006-12-28 17:00 | 14d | team VDW | 4318.72 | 26000 | 0 | 0 | 30318.72 | 2007-02-08 08:00 | 10d | 30318.72 | 0 | 0 | 0 | 0 | 30318.72 | 0 | 100.0% | Finished | 30318.72 | 30318.72
18 | foundation beam | 2006-12-29 08:00 | 2007-02-01 17:00 | 25d | team VDW[3.0 #8] | 23136 | 98523.7266 | 0 | 0 | 121659.7266 | 2007-02-28 08:00 | 22d | 78721.0239 | 42938.7027 | 12d | 0 | 0 | 78721.0239 | 42938.7027 | 64.705902338028% | Started | 113494.0841 | 121659.7266
19 | steelframe I | 2007-02-02 08:00 | 2007-03-01 17:00 | 20d | team VDW[4.0 #8] | 24678.4 | 118992.5078 | 0 | 0 | 143670.9078 | 2958466 | 0 | 0 | 143670.9078 | 20d | 0 | 0 | 0 | 143670.9078 | 0.0% | Not Started | 0 | 143670.9078
20 | concrete vaults I | 2007-03-02 08:00 | 2007-03-15 17:00 | 10d | team VDW[4.0 #8] | 12339.2 | 117409.7188 | 0 | 0 | 129748.9187 | 2958466 | 0 | 0 | 129748.9187 | 10d | 0 | 0 | 0 | 129748.9187 | 0.0% | Not Started | 0 | 129748.9187
21 | placing sewerage | 2006-12-29 08:00 | 2007-01-11 17:00 | 10d | team VDW[3.0 #8] | 9254.4 | 1224.73 | 0 | 0 | 10479.13 | 2007-02-28 08:00 | 12d | 10479.13 | 0 | 0 | 0 | 0 | 10479.13 | 0 | 100.0% | Finished | 10479.13 | 10479.13
22 | steelframe II | 2007-03-16 08:00 | 2007-04-05 17:00 | 15d | team VDW[3.0 #8] | 13881.6 | 118992.5078 | 0 | 0 | 132874.1078 | 2958466 | 0 | 0 | 132874.1078 | 15d | 0 | 0 | 0 | 132874.1078 | 0.0% | Not Started | 0 | 132874.1078
23 | foundation plate | 2007-01-12 08:00 | 2007-01-12 17:00 | 1d | team VDW[5.0 #8] | 1542.4 | 234819.4375 | 0 | 0 | 236361.8375 | 2007-03-16 08:00 | 1d | 236361.8375 | 0 | 0 | 0 | 0 | 236361.8375 | 0 | 100.0% | Finished | 236361.8375 | 236361.8375
24 | concrete volt II | 2007-04-06 08:00 | 2007-04-26 17:00 | 15d | team VDW[4.0 #8] | 18508.8 | 117409.7188 | 0 | 0 | 135918.5187 | 2958466 | 0 | 0 | 135918.5187 | 15d | 0 | 0 | 0 | 135918.5187 | 0.0% | Not Started | 0 | 135918.5187
25 | facades | 2007-04-27 08:00 | 2007-05-24 17:00 | 20d | team VDW[2.0 #8] | 12339.2 | 339314 | 0 | 0 | 351653.2 | 2958466 | 0 | 0 | 351653.2 | 20d | 0 | 0 | 0 | 351653.2 | 0.0% | Not Started | 0 | 351653.2
26 | outside windows | 2007-05-25 08:00 | 2007-06-07 17:00 | 10d | windows[3.0 #3] | 9120 | 150750.5938 | 0 | 0 | 159870.5938 | 2958466 | 0 | 0 | 159870.5938 | 10d | 0 | 0 | 0 | 159870.5938 | 0.0% | Not Started | 0 | 159870.5938
27 | v0 -masonry | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 40.65 | 3252.0001 | 37704.9611 | 2958466 | 0 | 0 | 37704.9611 | 10d | 0 | 0 | 0 | 37704.9611 | 0.0% | Not Started | 0 | 37704.9611
28 | v0 polierbeton | 2007-06-08 08:00 | 2007-06-21 17:00 | 10d | team VDW[5.0 #8] | 15424 | 134400 | 0 | 0 | 149824 | 2958466 | 0 | 0 | 149824 | 10d | 0 | 0 | 0 | 149824 | 0.0% | Not Started | 0 | 149824
29 | v0 electricity | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 | 2958466 | 0 | 0 | 6400 | 25d | 0 | 0 | 0 | 6400 | 0.0% | Not Started | 0 | 6400
30 | v0 sanitary | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 | 2958466 | 0 | 0 | 7673 | 10d | 0 | 0 | 0 | 7673 | 0.0% | Not Started | 0 | 7673
31 | construction leave | 2007-08-15 10:00 | 2007-08-29 10:00 | 10d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2958466 | 0 | 0 | 0.01 | 10d | 0 | 0 | 0 | 0.01 | 0.0% | Not Started | 0 | 0.01
32 | stucco | 2007-09-26 10:00 | 2007-10-17 10:00 | 15d | stucco[3.0 #4] | 14896.8 | 8642 | 0 | 0 | 23538.8 | 2958466 | 0 | 0 | 23538.8 | 15d | 0 | 0 | 0 | 23538.8 | 0.0% | Not Started | 0 | 23538.8
34 | v1screed | 2007-08-29 10:00 | 2007-09-19 10:00 | 15d | chapen[2.0 #3] | 0 | 106140 | 0 | 0 | 106140 | 2958466 | 0 | 0 | 106140 | 15d | 0 | 0 | 0 | 106140 | 0.0% | Not Started | 0 | 106140
35 | v0 floors | 2007-10-03 10:00 | 2007-10-31 10:00 | 20d | flooring | 6649.6 | 75000 | 0 | 0 | 81649.6 | 2958466 | 0 | 0 | 81649.6 | 20d | 0 | 0 | 0 | 81649.6 | 0.0% | Not Started | 0 | 81649.6
36 | drywall | 2007-10-24 10:00 | 2007-11-28 10:00 | 25d |  | 0 | 48000 | 0 | 0 | 48000 | 2958466 | 0 | 0 | 48000 | 25d | 0 | 0 | 0 | 48000 | 0.0% | Not Started | 0 | 48000
37 | techniques | 2007-10-31 10:00 | 2007-11-21 10:00 | 15d |  | 0 | 2156.0601 | 0 | 0 | 2156.0601 | 2958466 | 0 | 0 | 2156.0601 | 15d | 0 | 0 | 0 | 2156.0601 | 0.0% | Not Started | 0 | 2156.0601
38 | suspended ceiling | 2007-11-21 10:00 | 2007-11-28 10:00 | 5d |  | 0 | 32000 | 0 | 0 | 32000 | 2958466 | 0 | 0 | 32000 | 5d | 0 | 0 | 0 | 32000 | 0.0% | Not Started | 0 | 32000
39 | painting | 2007-11-28 10:00 | 2007-12-19 10:00 | 15d | painter[4.0 #6] | 16800 | 83000 | 0 | 0 | 99800 | 2958466 | 0 | 0 | 99800 | 15d | 0 | 0 | 0 | 99800 | 0.0% | Not Started | 0 | 99800
40 | furniture | 2007-12-19 10:00 | 2007-12-26 10:00 | 5d | furniture[5.0 #5] | 8400 | 130000 | 0 | 0 | 138400 | 2958466 | 0 | 0 | 138400 | 5d | 0 | 0 | 0 | 138400 | 0.0% | Not Started | 0 | 138400
41 | kitchen and bar | 2007-10-31 10:00 | 2007-11-21 10:00 | 15d |  | 0 | 87000 | 0 | 0 | 87000 | 2958466 | 0 | 0 | 87000 | 15d | 0 | 0 | 0 | 87000 | 0.0% | Not Started | 0 | 87000
42 | entrance doors | 2007-11-21 10:00 | 2007-12-05 10:00 | 10d |  | 0 | 16000 | 0 | 0 | 16000 | 2958466 | 0 | 0 | 16000 | 10d | 0 | 0 | 0 | 16000 | 0.0% | Not Started | 0 | 16000
43 | elevator | 2007-11-21 10:00 | 2007-11-28 10:00 | 5d |  | 0 | 38817.8516 | 0 | 0 | 38817.8516 | 2958466 | 0 | 0 | 38817.8516 | 5d | 0 | 0 | 0 | 38817.8516 | 0.0% | Not Started | 0 | 38817.8516
44 | stairs | 2007-11-21 10:00 | 2007-12-05 10:00 | 10d |  | 0 | 33000 | 0 | 0 | 33000 | 2958466 | 0 | 0 | 33000 | 10d | 0 | 0 | 0 | 33000 | 0.0% | Not Started | 0 | 33000
45 | vI masonry | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 40.65 | 3252.0001 | 37704.9611 | 2958466 | 0 | 0 | 37704.9611 | 10d | 0 | 0 | 0 | 37704.9611 | 0.0% | Not Started | 0 | 37704.9611
49 | roof | 2007-04-27 08:00 | 2007-05-10 17:00 | 10d | roofing[4.0 #4] | 11520 | 70779.5703 | 40.3 | 3223.9999 | 85523.5703 | 2958466 | 0 | 0 | 85523.5703 | 10d | 0 | 0 | 0 | 85523.5703 | 0.0% | Not Started | 0 | 85523.5703
51 | vI electricity | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 | 2958466 | 0 | 0 | 6400 | 25d | 0 | 0 | 0 | 6400 | 0.0% | Not Started | 0 | 6400
52 | vI sanitary | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 | 2958466 | 0 | 0 | 7673 | 10d | 0 | 0 | 0 | 7673 | 0.0% | Not Started | 0 | 7673
53 | v2 sanitary | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 | 2958466 | 0 | 0 | 7673 | 10d | 0 | 0 | 0 | 7673 | 0.0% | Not Started | 0 | 7673
54 | v2 electricity | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 | 2958466 | 0 | 0 | 6400 | 25d | 0 | 0 | 0 | 6400 | 0.0% | Not Started | 0 | 6400
55 | v2 masonry | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 0 | 0 | 34452.9609 | 2958466 | 0 | 0 | 34452.9609 | 10d | 0 | 0 | 0 | 34452.9609 | 0.0% | Not Started | 0 | 34452.9609
56 | v2 screed | 2007-08-29 10:00 | 2007-09-19 10:00 | 15d | chapen | 0 | 46116 | 0 | 0 | 46116 | 2958466 | 0 | 0 | 46116 | 15d | 0 | 0 | 0 | 46116 | 0.0% | Not Started | 0 | 46116
57 | v1flooring | 2007-09-26 10:00 | 2007-10-24 10:00 | 20d | flooring | 6649.6 | 72500 | 0 | 0 | 79149.6 | 2958466 | 0 | 0 | 79149.6 | 20d | 0 | 0 | 0 | 79149.6 | 0.0% | Not Started | 0 | 79149.6
58 | v2 flooring | 2007-09-26 10:00 | 2007-10-24 10:00 | 20d | flooring | 6649.6 | 31500 | 0 | 0 | 38149.6 | 2958466 | 0 | 0 | 38149.6 | 20d | 0 | 0 | 0 | 38149.6 | 0.0% | Not Started | 0 | 38149.6
59 | v0 heating | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | heating | 6912 | 11651 | 0 | 0 | 18563 | 2958466 | 0 | 0 | 18563 | 20d | 0 | 0 | 0 | 18563 | 0.0% | Not Started | 0 | 18563
60 | v1 heating | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | heating | 6912 | 11651 | 43.2 | 6912.0001 | 25475.0001 | 2958466 | 0 | 0 | 25475.0001 | 20d | 0 | 0 | 0 | 25475.0001 | 0.0% | Not Started | 0 | 25475.0001
61 | v2 heating | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | electrician | 5120 | 11651 | 0 | 0 | 16771 | 2958466 | 0 | 0 | 16771 | 20d | 0 | 0 | 0 | 16771 | 0.0% | Not Started | 0 | 16771
67 | v1 drying screed | 2007-09-19 10:00 | 2007-09-26 10:00 | 5d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2958466 | 0 | 0 | 0.01 | 5d | 0 | 0 | 0 | 0.01 | 0.0% | Not Started | 0 | 0.01
68 | v2 drying screed | 2007-09-19 10:00 | 2007-09-26 10:00 | 5d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2958466 | 0 | 0 | 0.01 | 5d | 0 | 0 | 0 | 0.01 | 0.0% | Not Started | 0 | 0.01
69 | soil analyses | 2006-12-11 08:00 | 2006-12-12 17:00 | 2d | team VDW | 616.96 | 2000 | 0 | 0 | 2616.96 | 2007-02-08 08:00 | 12d | 2616.96 | 0 | 0 | 0 | 0 | 2616.96 | 0 | 100.0% | Finished | 2616.96 | 2616.96

## TP4
| TP Status Date | 2007-06-04 08:00 |  | TP Name | Shell
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Absolute baseline duration | Absolute actual duration | Absolute completed | Baseline cost | Actual cost | Absolute percentage completed
2 | building permit | 2006-04-17 08:00 | 2006-07-07 17:00 | 60d |  | 0 | 75 | 0 | 0 | 75 | 2006-04-17 08:00 | 100d | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100.0% | Finished | 75 | 75
3 | hire contractor | 2006-07-10 08:00 | 2006-08-04 17:00 | 20d |  | 0 | 210000 | 0 | 0 | 210000 | 2006-09-04 08:00 | 30d | 210000 | 0 | 0 | 0 | 0 | 210000 | 0 | 100.0% | Finished | 210000 | 210000
4 | temporary offices | 2006-04-17 08:00 | 2006-05-12 17:00 | 20d |  | 0 | 3765.3101 | 0 | 0 | 3765.3101 | 2006-04-17 08:00 | 20d | 3765.3101 | 0 | 0 | 0 | 0 | 3765.3101 | 0 | 100.0% | Finished | 3765.3101 | 3765.3101
5 | temporary facilities | 2006-04-17 08:00 | 2006-07-07 17:00 | 60d |  | 0 | 1876.54 | 0 | 0 | 1876.54 | 2006-04-17 08:00 | 60d | 1876.54 | 0 | 0 | 0 | 0 | 1876.54 | 0 | 100.0% | Finished | 1876.54 | 1876.54
6 | demolition | 2006-10-30 08:00 | 2006-12-08 17:00 | 30d | team VDW[4.0 #8] | 37017.6 | 1070.11 | 0 | 0 | 38087.71 | 2006-11-27 08:00 | 54d | 38087.71 | 0 | 0 | 0 | 0 | 38087.71 | 0 | 100.0% | Finished | 38087.71 | 38087.71
16 | preparation contractor | 2006-08-07 08:00 | 2006-10-27 17:00 | 60d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2006-09-04 08:00 | 60d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100.0% | Finished | 0.01 | 0.01
17 | excavation | 2006-12-11 08:00 | 2006-12-28 17:00 | 14d | team VDW | 4318.72 | 26000 | 0 | 0 | 30318.72 | 2007-02-08 08:00 | 10d | 30318.72 | 0 | 0 | 0 | 0 | 30318.72 | 0 | 100.0% | Finished | 30318.72 | 30318.72
18 | foundation beam | 2006-12-29 08:00 | 2007-02-01 17:00 | 25d | team VDW[3.0 #8] | 23136 | 98523.7266 | 0 | 0 | 121659.7266 | 2007-02-28 08:00 | 22d | 121659.7266 | 0 | 0 | 0 | 0 | 121659.7266 | 0 | 100.0% | Finished | 121659.7266 | 121659.7266
19 | steelframe I | 2007-02-02 08:00 | 2007-03-01 17:00 | 20d | team VDW[4.0 #8] | 24678.4 | 118992.5078 | 0 | 0 | 143670.9078 | 2007-04-02 08:00 | 15d | 61794.0084 | 81876.8994 | 19d 21h | 0 | 0 | 61794.0084 | 81876.8994 | 43.010801076889% | Started | 129606.8853 | 143670.9078
20 | concrete vaults I | 2007-03-02 08:00 | 2007-03-15 17:00 | 10d | team VDW[4.0 #8] | 12339.2 | 117409.7188 | 0 | 0 | 129748.9187 | 2007-04-23 08:00 | 5d | 129748.9187 | 0 | 0 | 0 | 0 | 129748.9187 | 0 | 100.0% | Finished | 129748.9187 | 129748.9187
21 | placing sewerage | 2006-12-29 08:00 | 2007-01-11 17:00 | 10d | team VDW[3.0 #8] | 9254.4 | 1224.73 | 0 | 0 | 10479.13 | 2007-02-28 08:00 | 12d | 10479.13 | 0 | 0 | 0 | 0 | 10479.13 | 0 | 100.0% | Finished | 10479.13 | 10479.13
22 | steelframe II | 2007-03-16 08:00 | 2007-04-05 17:00 | 15d | team VDW[3.0 #8] | 13881.6 | 118992.5078 | 0 | 0 | 132874.1078 | 2007-04-30 08:00 | 15d | 132874.1078 | 0 | 0 | 0 | 0 | 132874.1078 | 0 | 100.0% | Finished | 132874.1078 | 132874.1078
23 | foundation plate | 2007-01-12 08:00 | 2007-01-12 17:00 | 1d | team VDW[5.0 #8] | 1542.4 | 234819.4375 | 0 | 0 | 236361.8375 | 2007-03-16 08:00 | 1d | 236361.8375 | 0 | 0 | 0 | 0 | 236361.8375 | 0 | 100.0% | Finished | 236361.8375 | 236361.8375
24 | concrete volt II | 2007-04-06 08:00 | 2007-04-26 17:00 | 15d | team VDW[4.0 #8] | 18508.8 | 117409.7188 | 0 | 0 | 135918.5187 | 2007-05-21 08:00 | 10d | 135918.5187 | 0 | 0 | 0 | 0 | 135918.5187 | 0 | 100.0% | Finished | 135918.5187 | 135918.5187
25 | facades | 2007-04-27 08:00 | 2007-05-24 17:00 | 20d | team VDW[2.0 #8] | 12339.2 | 339314 | 0 | 0 | 351653.2 | 2958466 | 0 | 0 | 351653.2 | 20d | 0 | 0 | 0 | 351653.2 | 0.0% | Not Started | 0 | 351653.2
26 | outside windows | 2007-05-25 08:00 | 2007-06-07 17:00 | 10d | windows[3.0 #3] | 9120 | 150750.5938 | 0 | 0 | 159870.5938 | 2958466 | 0 | 0 | 159870.5938 | 10d | 0 | 0 | 0 | 159870.5938 | 0.0% | Not Started | 0 | 159870.5938
27 | v0 -masonry | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 40.65 | 3252.0001 | 37704.9611 | 2958466 | 0 | 0 | 37704.9611 | 10d | 0 | 0 | 0 | 37704.9611 | 0.0% | Not Started | 0 | 37704.9611
28 | v0 polierbeton | 2007-06-08 08:00 | 2007-06-21 17:00 | 10d | team VDW[5.0 #8] | 15424 | 134400 | 0 | 0 | 149824 | 2958466 | 0 | 0 | 149824 | 10d | 0 | 0 | 0 | 149824 | 0.0% | Not Started | 0 | 149824
29 | v0 electricity | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 | 2958466 | 0 | 0 | 6400 | 25d | 0 | 0 | 0 | 6400 | 0.0% | Not Started | 0 | 6400
30 | v0 sanitary | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 | 2958466 | 0 | 0 | 7673 | 10d | 0 | 0 | 0 | 7673 | 0.0% | Not Started | 0 | 7673
31 | construction leave | 2007-08-15 10:00 | 2007-08-29 10:00 | 10d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2958466 | 0 | 0 | 0.01 | 10d | 0 | 0 | 0 | 0.01 | 0.0% | Not Started | 0 | 0.01
32 | stucco | 2007-09-26 10:00 | 2007-10-17 10:00 | 15d | stucco[3.0 #4] | 14896.8 | 8642 | 0 | 0 | 23538.8 | 2958466 | 0 | 0 | 23538.8 | 15d | 0 | 0 | 0 | 23538.8 | 0.0% | Not Started | 0 | 23538.8
34 | v1screed | 2007-08-29 10:00 | 2007-09-19 10:00 | 15d | chapen[2.0 #3] | 0 | 106140 | 0 | 0 | 106140 | 2958466 | 0 | 0 | 106140 | 15d | 0 | 0 | 0 | 106140 | 0.0% | Not Started | 0 | 106140
35 | v0 floors | 2007-10-03 10:00 | 2007-10-31 10:00 | 20d | flooring | 6649.6 | 75000 | 0 | 0 | 81649.6 | 2958466 | 0 | 0 | 81649.6 | 20d | 0 | 0 | 0 | 81649.6 | 0.0% | Not Started | 0 | 81649.6
36 | drywall | 2007-10-24 10:00 | 2007-11-28 10:00 | 25d |  | 0 | 48000 | 0 | 0 | 48000 | 2958466 | 0 | 0 | 48000 | 25d | 0 | 0 | 0 | 48000 | 0.0% | Not Started | 0 | 48000
37 | techniques | 2007-10-31 10:00 | 2007-11-21 10:00 | 15d |  | 0 | 2156.0601 | 0 | 0 | 2156.0601 | 2958466 | 0 | 0 | 2156.0601 | 15d | 0 | 0 | 0 | 2156.0601 | 0.0% | Not Started | 0 | 2156.0601
38 | suspended ceiling | 2007-11-21 10:00 | 2007-11-28 10:00 | 5d |  | 0 | 32000 | 0 | 0 | 32000 | 2958466 | 0 | 0 | 32000 | 5d | 0 | 0 | 0 | 32000 | 0.0% | Not Started | 0 | 32000
39 | painting | 2007-11-28 10:00 | 2007-12-19 10:00 | 15d | painter[4.0 #6] | 16800 | 83000 | 0 | 0 | 99800 | 2958466 | 0 | 0 | 99800 | 15d | 0 | 0 | 0 | 99800 | 0.0% | Not Started | 0 | 99800
40 | furniture | 2007-12-19 10:00 | 2007-12-26 10:00 | 5d | furniture[5.0 #5] | 8400 | 130000 | 0 | 0 | 138400 | 2958466 | 0 | 0 | 138400 | 5d | 0 | 0 | 0 | 138400 | 0.0% | Not Started | 0 | 138400
41 | kitchen and bar | 2007-10-31 10:00 | 2007-11-21 10:00 | 15d |  | 0 | 87000 | 0 | 0 | 87000 | 2958466 | 0 | 0 | 87000 | 15d | 0 | 0 | 0 | 87000 | 0.0% | Not Started | 0 | 87000
42 | entrance doors | 2007-11-21 10:00 | 2007-12-05 10:00 | 10d |  | 0 | 16000 | 0 | 0 | 16000 | 2958466 | 0 | 0 | 16000 | 10d | 0 | 0 | 0 | 16000 | 0.0% | Not Started | 0 | 16000
43 | elevator | 2007-11-21 10:00 | 2007-11-28 10:00 | 5d |  | 0 | 38817.8516 | 0 | 0 | 38817.8516 | 2958466 | 0 | 0 | 38817.8516 | 5d | 0 | 0 | 0 | 38817.8516 | 0.0% | Not Started | 0 | 38817.8516
44 | stairs | 2007-11-21 10:00 | 2007-12-05 10:00 | 10d |  | 0 | 33000 | 0 | 0 | 33000 | 2958466 | 0 | 0 | 33000 | 10d | 0 | 0 | 0 | 33000 | 0.0% | Not Started | 0 | 33000
45 | vI masonry | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 40.65 | 3252.0001 | 37704.9611 | 2958466 | 0 | 0 | 37704.9611 | 10d | 0 | 0 | 0 | 37704.9611 | 0.0% | Not Started | 0 | 37704.9611
49 | roof | 2007-04-27 08:00 | 2007-05-10 17:00 | 10d | roofing[4.0 #4] | 11520 | 70779.5703 | 40.3 | 3223.9999 | 85523.5703 | 2958466 | 0 | 0 | 85523.5703 | 10d | 0 | 0 | 0 | 85523.5703 | 0.0% | Not Started | 0 | 85523.5703
51 | vI electricity | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 | 2958466 | 0 | 0 | 6400 | 25d | 0 | 0 | 0 | 6400 | 0.0% | Not Started | 0 | 6400
52 | vI sanitary | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 | 2958466 | 0 | 0 | 7673 | 10d | 0 | 0 | 0 | 7673 | 0.0% | Not Started | 0 | 7673
53 | v2 sanitary | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 | 2958466 | 0 | 0 | 7673 | 10d | 0 | 0 | 0 | 7673 | 0.0% | Not Started | 0 | 7673
54 | v2 electricity | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 | 2958466 | 0 | 0 | 6400 | 25d | 0 | 0 | 0 | 6400 | 0.0% | Not Started | 0 | 6400
55 | v2 masonry | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 0 | 0 | 34452.9609 | 2958466 | 0 | 0 | 34452.9609 | 10d | 0 | 0 | 0 | 34452.9609 | 0.0% | Not Started | 0 | 34452.9609
56 | v2 screed | 2007-08-29 10:00 | 2007-09-19 10:00 | 15d | chapen | 0 | 46116 | 0 | 0 | 46116 | 2958466 | 0 | 0 | 46116 | 15d | 0 | 0 | 0 | 46116 | 0.0% | Not Started | 0 | 46116
57 | v1flooring | 2007-09-26 10:00 | 2007-10-24 10:00 | 20d | flooring | 6649.6 | 72500 | 0 | 0 | 79149.6 | 2958466 | 0 | 0 | 79149.6 | 20d | 0 | 0 | 0 | 79149.6 | 0.0% | Not Started | 0 | 79149.6
58 | v2 flooring | 2007-09-26 10:00 | 2007-10-24 10:00 | 20d | flooring | 6649.6 | 31500 | 0 | 0 | 38149.6 | 2958466 | 0 | 0 | 38149.6 | 20d | 0 | 0 | 0 | 38149.6 | 0.0% | Not Started | 0 | 38149.6
59 | v0 heating | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | heating | 6912 | 11651 | 0 | 0 | 18563 | 2958466 | 0 | 0 | 18563 | 20d | 0 | 0 | 0 | 18563 | 0.0% | Not Started | 0 | 18563
60 | v1 heating | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | heating | 6912 | 11651 | 43.2 | 6912.0001 | 25475.0001 | 2958466 | 0 | 0 | 25475.0001 | 20d | 0 | 0 | 0 | 25475.0001 | 0.0% | Not Started | 0 | 25475.0001
61 | v2 heating | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | electrician | 5120 | 11651 | 0 | 0 | 16771 | 2958466 | 0 | 0 | 16771 | 20d | 0 | 0 | 0 | 16771 | 0.0% | Not Started | 0 | 16771
67 | v1 drying screed | 2007-09-19 10:00 | 2007-09-26 10:00 | 5d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2958466 | 0 | 0 | 0.01 | 5d | 0 | 0 | 0 | 0.01 | 0.0% | Not Started | 0 | 0.01
68 | v2 drying screed | 2007-09-19 10:00 | 2007-09-26 10:00 | 5d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2958466 | 0 | 0 | 0.01 | 5d | 0 | 0 | 0 | 0.01 | 0.0% | Not Started | 0 | 0.01
69 | soil analyses | 2006-12-11 08:00 | 2006-12-12 17:00 | 2d | team VDW | 616.96 | 2000 | 0 | 0 | 2616.96 | 2007-02-08 08:00 | 12d | 2616.96 | 0 | 0 | 0 | 0 | 2616.96 | 0 | 100.0% | Finished | 2616.96 | 2616.96

## TP5
| TP Status Date | 2007-07-02 08:00 |  | TP Name | Wind&Waterproof
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Absolute baseline duration | Absolute actual duration | Absolute completed | Baseline cost | Actual cost | Absolute percentage completed
2 | building permit | 2006-04-17 08:00 | 2006-07-07 17:00 | 60d |  | 0 | 75 | 0 | 0 | 75 | 2006-04-17 08:00 | 100d | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100.0% | Finished | 75 | 75
3 | hire contractor | 2006-07-10 08:00 | 2006-08-04 17:00 | 20d |  | 0 | 210000 | 0 | 0 | 210000 | 2006-09-04 08:00 | 30d | 210000 | 0 | 0 | 0 | 0 | 210000 | 0 | 100.0% | Finished | 210000 | 210000
4 | temporary offices | 2006-04-17 08:00 | 2006-05-12 17:00 | 20d |  | 0 | 3765.3101 | 0 | 0 | 3765.3101 | 2006-04-17 08:00 | 20d | 3765.3101 | 0 | 0 | 0 | 0 | 3765.3101 | 0 | 100.0% | Finished | 3765.3101 | 3765.3101
5 | temporary facilities | 2006-04-17 08:00 | 2006-07-07 17:00 | 60d |  | 0 | 1876.54 | 0 | 0 | 1876.54 | 2006-04-17 08:00 | 60d | 1876.54 | 0 | 0 | 0 | 0 | 1876.54 | 0 | 100.0% | Finished | 1876.54 | 1876.54
6 | demolition | 2006-10-30 08:00 | 2006-12-08 17:00 | 30d | team VDW[4.0 #8] | 37017.6 | 1070.11 | 0 | 0 | 38087.71 | 2006-11-27 08:00 | 54d | 38087.71 | 0 | 0 | 0 | 0 | 38087.71 | 0 | 100.0% | Finished | 38087.71 | 38087.71
16 | preparation contractor | 2006-08-07 08:00 | 2006-10-27 17:00 | 60d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2006-09-04 08:00 | 60d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100.0% | Finished | 0.01 | 0.01
17 | excavation | 2006-12-11 08:00 | 2006-12-28 17:00 | 14d | team VDW | 4318.72 | 26000 | 0 | 0 | 30318.72 | 2007-02-08 08:00 | 10d | 30318.72 | 0 | 0 | 0 | 0 | 30318.72 | 0 | 100.0% | Finished | 30318.72 | 30318.72
18 | foundation beam | 2006-12-29 08:00 | 2007-02-01 17:00 | 25d | team VDW[3.0 #8] | 23136 | 98523.7266 | 0 | 0 | 121659.7266 | 2007-02-28 08:00 | 22d | 121659.7266 | 0 | 0 | 0 | 0 | 121659.7266 | 0 | 100.0% | Finished | 121659.7266 | 121659.7266
19 | steelframe I | 2007-02-02 08:00 | 2007-03-01 17:00 | 20d | team VDW[4.0 #8] | 24678.4 | 118992.5078 | 0 | 0 | 143670.9078 | 2007-04-02 08:00 | 15d | 143670.9078 | 0 | 0 | 0 | 0 | 143670.9078 | 0 | 100.0% | Finished | 143670.9078 | 143670.9078
20 | concrete vaults I | 2007-03-02 08:00 | 2007-03-15 17:00 | 10d | team VDW[4.0 #8] | 12339.2 | 117409.7188 | 0 | 0 | 129748.9187 | 2007-04-23 08:00 | 5d | 129748.9187 | 0 | 0 | 0 | 0 | 129748.9187 | 0 | 100.0% | Finished | 129748.9187 | 129748.9187
21 | placing sewerage | 2006-12-29 08:00 | 2007-01-11 17:00 | 10d | team VDW[3.0 #8] | 9254.4 | 1224.73 | 0 | 0 | 10479.13 | 2007-02-28 08:00 | 12d | 10479.13 | 0 | 0 | 0 | 0 | 10479.13 | 0 | 100.0% | Finished | 10479.13 | 10479.13
22 | steelframe II | 2007-03-16 08:00 | 2007-04-05 17:00 | 15d | team VDW[3.0 #8] | 13881.6 | 118992.5078 | 0 | 0 | 132874.1078 | 2007-04-30 08:00 | 15d | 132874.1078 | 0 | 0 | 0 | 0 | 132874.1078 | 0 | 100.0% | Finished | 132874.1078 | 132874.1078
23 | foundation plate | 2007-01-12 08:00 | 2007-01-12 17:00 | 1d | team VDW[5.0 #8] | 1542.4 | 234819.4375 | 0 | 0 | 236361.8375 | 2007-03-16 08:00 | 1d | 236361.8375 | 0 | 0 | 0 | 0 | 236361.8375 | 0 | 100.0% | Finished | 236361.8375 | 236361.8375
24 | concrete volt II | 2007-04-06 08:00 | 2007-04-26 17:00 | 15d | team VDW[4.0 #8] | 18508.8 | 117409.7188 | 0 | 0 | 135918.5187 | 2007-05-21 08:00 | 10d | 135918.5187 | 0 | 0 | 0 | 0 | 135918.5187 | 0 | 100.0% | Finished | 135918.5187 | 135918.5187
25 | facades | 2007-04-27 08:00 | 2007-05-24 17:00 | 20d | team VDW[2.0 #8] | 12339.2 | 339314 | 0 | 0 | 351653.2 | 2007-06-04 08:00 | 20d | 251180.8631 | 100472.3369 | 8d | 0 | 0 | 251180.8631 | 100472.3369 | 71.42857313156131% | Started | 348127.7145 | 351653.2
26 | outside windows | 2007-05-25 08:00 | 2007-06-07 17:00 | 10d | windows[3.0 #3] | 9120 | 150750.5938 | 0 | 0 | 159870.5938 | 2007-07-02 08:00 | 92d | 144373.9326 | 15496.6612 | 9d 21h | 0 | 0 | 144373.9326 | 15496.6612 | 90.30674695968631% | Started | 158986.5691 | 159870.5938
27 | v0 -masonry | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 40.65 | 3252.0001 | 37704.9611 | 2958466 | 0 | 0 | 37704.9611 | 10d | 0 | 0 | 0 | 37704.9611 | 0.0% | Not Started | 0 | 37704.9611
28 | v0 polierbeton | 2007-06-08 08:00 | 2007-06-21 17:00 | 10d | team VDW[5.0 #8] | 15424 | 134400 | 0 | 0 | 149824 | 2958466 | 0 | 0 | 149824 | 10d | 0 | 0 | 0 | 149824 | 0.0% | Not Started | 0 | 149824
29 | v0 electricity | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 | 2958466 | 0 | 0 | 6400 | 25d | 0 | 0 | 0 | 6400 | 0.0% | Not Started | 0 | 6400
30 | v0 sanitary | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 | 2958466 | 0 | 0 | 7673 | 10d | 0 | 0 | 0 | 7673 | 0.0% | Not Started | 0 | 7673
31 | construction leave | 2007-08-15 10:00 | 2007-08-29 10:00 | 10d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2958466 | 0 | 0 | 0.01 | 10d | 0 | 0 | 0 | 0.01 | 0.0% | Not Started | 0 | 0.01
32 | stucco | 2007-09-26 10:00 | 2007-10-17 10:00 | 15d | stucco[3.0 #4] | 14896.8 | 8642 | 0 | 0 | 23538.8 | 2958466 | 0 | 0 | 23538.8 | 15d | 0 | 0 | 0 | 23538.8 | 0.0% | Not Started | 0 | 23538.8
34 | v1screed | 2007-08-29 10:00 | 2007-09-19 10:00 | 15d | chapen[2.0 #3] | 0 | 106140 | 0 | 0 | 106140 | 2958466 | 0 | 0 | 106140 | 15d | 0 | 0 | 0 | 106140 | 0.0% | Not Started | 0 | 106140
35 | v0 floors | 2007-10-03 10:00 | 2007-10-31 10:00 | 20d | flooring | 6649.6 | 75000 | 0 | 0 | 81649.6 | 2958466 | 0 | 0 | 81649.6 | 20d | 0 | 0 | 0 | 81649.6 | 0.0% | Not Started | 0 | 81649.6
36 | drywall | 2007-10-24 10:00 | 2007-11-28 10:00 | 25d |  | 0 | 48000 | 0 | 0 | 48000 | 2958466 | 0 | 0 | 48000 | 25d | 0 | 0 | 0 | 48000 | 0.0% | Not Started | 0 | 48000
37 | techniques | 2007-10-31 10:00 | 2007-11-21 10:00 | 15d |  | 0 | 2156.0601 | 0 | 0 | 2156.0601 | 2958466 | 0 | 0 | 2156.0601 | 15d | 0 | 0 | 0 | 2156.0601 | 0.0% | Not Started | 0 | 2156.0601
38 | suspended ceiling | 2007-11-21 10:00 | 2007-11-28 10:00 | 5d |  | 0 | 32000 | 0 | 0 | 32000 | 2958466 | 0 | 0 | 32000 | 5d | 0 | 0 | 0 | 32000 | 0.0% | Not Started | 0 | 32000
39 | painting | 2007-11-28 10:00 | 2007-12-19 10:00 | 15d | painter[4.0 #6] | 16800 | 83000 | 0 | 0 | 99800 | 2958466 | 0 | 0 | 99800 | 15d | 0 | 0 | 0 | 99800 | 0.0% | Not Started | 0 | 99800
40 | furniture | 2007-12-19 10:00 | 2007-12-26 10:00 | 5d | furniture[5.0 #5] | 8400 | 130000 | 0 | 0 | 138400 | 2958466 | 0 | 0 | 138400 | 5d | 0 | 0 | 0 | 138400 | 0.0% | Not Started | 0 | 138400
41 | kitchen and bar | 2007-10-31 10:00 | 2007-11-21 10:00 | 15d |  | 0 | 87000 | 0 | 0 | 87000 | 2958466 | 0 | 0 | 87000 | 15d | 0 | 0 | 0 | 87000 | 0.0% | Not Started | 0 | 87000
42 | entrance doors | 2007-11-21 10:00 | 2007-12-05 10:00 | 10d |  | 0 | 16000 | 0 | 0 | 16000 | 2958466 | 0 | 0 | 16000 | 10d | 0 | 0 | 0 | 16000 | 0.0% | Not Started | 0 | 16000
43 | elevator | 2007-11-21 10:00 | 2007-11-28 10:00 | 5d |  | 0 | 38817.8516 | 0 | 0 | 38817.8516 | 2958466 | 0 | 0 | 38817.8516 | 5d | 0 | 0 | 0 | 38817.8516 | 0.0% | Not Started | 0 | 38817.8516
44 | stairs | 2007-11-21 10:00 | 2007-12-05 10:00 | 10d |  | 0 | 33000 | 0 | 0 | 33000 | 2958466 | 0 | 0 | 33000 | 10d | 0 | 0 | 0 | 33000 | 0.0% | Not Started | 0 | 33000
45 | vI masonry | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 40.65 | 3252.0001 | 37704.9611 | 2958466 | 0 | 0 | 37704.9611 | 10d | 0 | 0 | 0 | 37704.9611 | 0.0% | Not Started | 0 | 37704.9611
49 | roof | 2007-04-27 08:00 | 2007-05-10 17:00 | 10d | roofing[4.0 #4] | 11520 | 70779.5703 | 40.3 | 3223.9999 | 85523.5703 | 2007-06-04 08:00 | 10d | 85523.5703 | 0 | 0 | 0 | 0 | 85523.5703 | 0 | 100.0% | Finished | 114539.5697 | 85523.5703
51 | vI electricity | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 | 2958466 | 0 | 0 | 6400 | 25d | 0 | 0 | 0 | 6400 | 0.0% | Not Started | 0 | 6400
52 | vI sanitary | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 | 2958466 | 0 | 0 | 7673 | 10d | 0 | 0 | 0 | 7673 | 0.0% | Not Started | 0 | 7673
53 | v2 sanitary | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 | 2958466 | 0 | 0 | 7673 | 10d | 0 | 0 | 0 | 7673 | 0.0% | Not Started | 0 | 7673
54 | v2 electricity | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 | 2958466 | 0 | 0 | 6400 | 25d | 0 | 0 | 0 | 6400 | 0.0% | Not Started | 0 | 6400
55 | v2 masonry | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 0 | 0 | 34452.9609 | 2958466 | 0 | 0 | 34452.9609 | 10d | 0 | 0 | 0 | 34452.9609 | 0.0% | Not Started | 0 | 34452.9609
56 | v2 screed | 2007-08-29 10:00 | 2007-09-19 10:00 | 15d | chapen | 0 | 46116 | 0 | 0 | 46116 | 2958466 | 0 | 0 | 46116 | 15d | 0 | 0 | 0 | 46116 | 0.0% | Not Started | 0 | 46116
57 | v1flooring | 2007-09-26 10:00 | 2007-10-24 10:00 | 20d | flooring | 6649.6 | 72500 | 0 | 0 | 79149.6 | 2958466 | 0 | 0 | 79149.6 | 20d | 0 | 0 | 0 | 79149.6 | 0.0% | Not Started | 0 | 79149.6
58 | v2 flooring | 2007-09-26 10:00 | 2007-10-24 10:00 | 20d | flooring | 6649.6 | 31500 | 0 | 0 | 38149.6 | 2958466 | 0 | 0 | 38149.6 | 20d | 0 | 0 | 0 | 38149.6 | 0.0% | Not Started | 0 | 38149.6
59 | v0 heating | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | heating | 6912 | 11651 | 0 | 0 | 18563 | 2958466 | 0 | 0 | 18563 | 20d | 0 | 0 | 0 | 18563 | 0.0% | Not Started | 0 | 18563
60 | v1 heating | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | heating | 6912 | 11651 | 43.2 | 6912.0001 | 25475.0001 | 2958466 | 0 | 0 | 25475.0001 | 20d | 0 | 0 | 0 | 25475.0001 | 0.0% | Not Started | 0 | 25475.0001
61 | v2 heating | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | electrician | 5120 | 11651 | 0 | 0 | 16771 | 2958466 | 0 | 0 | 16771 | 20d | 0 | 0 | 0 | 16771 | 0.0% | Not Started | 0 | 16771
67 | v1 drying screed | 2007-09-19 10:00 | 2007-09-26 10:00 | 5d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2958466 | 0 | 0 | 0.01 | 5d | 0 | 0 | 0 | 0.01 | 0.0% | Not Started | 0 | 0.01
68 | v2 drying screed | 2007-09-19 10:00 | 2007-09-26 10:00 | 5d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2958466 | 0 | 0 | 0.01 | 5d | 0 | 0 | 0 | 0.01 | 0.0% | Not Started | 0 | 0.01
69 | soil analyses | 2006-12-11 08:00 | 2006-12-12 17:00 | 2d | team VDW | 616.96 | 2000 | 0 | 0 | 2616.96 | 2007-02-08 08:00 | 12d | 2616.96 | 0 | 0 | 0 | 0 | 2616.96 | 0 | 100.0% | Finished | 2616.96 | 2616.96

## TP6
| TP Status Date | 2007-10-24 08:00 |  | TP Name | WH, L1, L2
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Absolute baseline duration | Absolute actual duration | Absolute completed | Baseline cost | Actual cost | Absolute percentage completed
2 | building permit | 2006-04-17 08:00 | 2006-07-07 17:00 | 60d |  | 0 | 75 | 0 | 0 | 75 | 2006-04-17 08:00 | 100d | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100.0% | Finished | 75 | 75
3 | hire contractor | 2006-07-10 08:00 | 2006-08-04 17:00 | 20d |  | 0 | 210000 | 0 | 0 | 210000 | 2006-09-04 08:00 | 30d | 210000 | 0 | 0 | 0 | 0 | 210000 | 0 | 100.0% | Finished | 210000 | 210000
4 | temporary offices | 2006-04-17 08:00 | 2006-05-12 17:00 | 20d |  | 0 | 3765.3101 | 0 | 0 | 3765.3101 | 2006-04-17 08:00 | 20d | 3765.3101 | 0 | 0 | 0 | 0 | 3765.3101 | 0 | 100.0% | Finished | 3765.3101 | 3765.3101
5 | temporary facilities | 2006-04-17 08:00 | 2006-07-07 17:00 | 60d |  | 0 | 1876.54 | 0 | 0 | 1876.54 | 2006-04-17 08:00 | 60d | 1876.54 | 0 | 0 | 0 | 0 | 1876.54 | 0 | 100.0% | Finished | 1876.54 | 1876.54
6 | demolition | 2006-10-30 08:00 | 2006-12-08 17:00 | 30d | team VDW[4.0 #8] | 37017.6 | 1070.11 | 0 | 0 | 38087.71 | 2006-11-27 08:00 | 54d | 38087.71 | 0 | 0 | 0 | 0 | 38087.71 | 0 | 100.0% | Finished | 38087.71 | 38087.71
16 | preparation contractor | 2006-08-07 08:00 | 2006-10-27 17:00 | 60d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2006-09-04 08:00 | 60d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100.0% | Finished | 0.01 | 0.01
17 | excavation | 2006-12-11 08:00 | 2006-12-28 17:00 | 14d | team VDW | 4318.72 | 26000 | 0 | 0 | 30318.72 | 2007-02-08 08:00 | 10d | 30318.72 | 0 | 0 | 0 | 0 | 30318.72 | 0 | 100.0% | Finished | 30318.72 | 30318.72
18 | foundation beam | 2006-12-29 08:00 | 2007-02-01 17:00 | 25d | team VDW[3.0 #8] | 23136 | 98523.7266 | 0 | 0 | 121659.7266 | 2007-02-28 08:00 | 22d | 121659.7266 | 0 | 0 | 0 | 0 | 121659.7266 | 0 | 100.0% | Finished | 121659.7266 | 121659.7266
19 | steelframe I | 2007-02-02 08:00 | 2007-03-01 17:00 | 20d | team VDW[4.0 #8] | 24678.4 | 118992.5078 | 0 | 0 | 143670.9078 | 2007-04-02 08:00 | 15d | 143670.9078 | 0 | 0 | 0 | 0 | 143670.9078 | 0 | 100.0% | Finished | 143670.9078 | 143670.9078
20 | concrete vaults I | 2007-03-02 08:00 | 2007-03-15 17:00 | 10d | team VDW[4.0 #8] | 12339.2 | 117409.7188 | 0 | 0 | 129748.9187 | 2007-04-23 08:00 | 5d | 129748.9187 | 0 | 0 | 0 | 0 | 129748.9187 | 0 | 100.0% | Finished | 129748.9187 | 129748.9187
21 | placing sewerage | 2006-12-29 08:00 | 2007-01-11 17:00 | 10d | team VDW[3.0 #8] | 9254.4 | 1224.73 | 0 | 0 | 10479.13 | 2007-02-28 08:00 | 12d | 10479.13 | 0 | 0 | 0 | 0 | 10479.13 | 0 | 100.0% | Finished | 10479.13 | 10479.13
22 | steelframe II | 2007-03-16 08:00 | 2007-04-05 17:00 | 15d | team VDW[3.0 #8] | 13881.6 | 118992.5078 | 0 | 0 | 132874.1078 | 2007-04-30 08:00 | 15d | 132874.1078 | 0 | 0 | 0 | 0 | 132874.1078 | 0 | 100.0% | Finished | 132874.1078 | 132874.1078
23 | foundation plate | 2007-01-12 08:00 | 2007-01-12 17:00 | 1d | team VDW[5.0 #8] | 1542.4 | 234819.4375 | 0 | 0 | 236361.8375 | 2007-03-16 08:00 | 1d | 236361.8375 | 0 | 0 | 0 | 0 | 236361.8375 | 0 | 100.0% | Finished | 236361.8375 | 236361.8375
24 | concrete volt II | 2007-04-06 08:00 | 2007-04-26 17:00 | 15d | team VDW[4.0 #8] | 18508.8 | 117409.7188 | 0 | 0 | 135918.5187 | 2007-05-21 08:00 | 10d | 135918.5187 | 0 | 0 | 0 | 0 | 135918.5187 | 0 | 100.0% | Finished | 135918.5187 | 135918.5187
25 | facades | 2007-04-27 08:00 | 2007-05-24 17:00 | 20d | team VDW[2.0 #8] | 12339.2 | 339314 | 0 | 0 | 351653.2 | 2007-06-04 08:00 | 20d | 351653.2 | 0 | 0 | 0 | 0 | 351653.2 | 0 | 100.0% | Finished | 351653.2 | 351653.2
26 | outside windows | 2007-05-25 08:00 | 2007-06-07 17:00 | 10d | windows[3.0 #3] | 9120 | 150750.5938 | 0 | 0 | 159870.5938 | 2007-07-02 08:00 | 92d | 144373.9326 | 15496.6612 | 9d 21h | 0 | 0 | 144373.9326 | 15496.6612 | 90.30674695968631% | Started | 158986.5691 | 159870.5938
27 | v0 -masonry | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 40.65 | 3252.0001 | 37704.9611 | 2007-08-29 08:00 | 10d | 37704.9611 | 0 | 0 | 0 | 0 | 37704.9611 | 0 | 100.0% | Finished | 66972.9622 | 37704.9611
28 | v0 polierbeton | 2007-06-08 08:00 | 2007-06-21 17:00 | 10d | team VDW[5.0 #8] | 15424 | 134400 | 0 | 0 | 149824 | 2007-07-25 08:00 | 5d | 149824 | 0 | 0 | 0 | 0 | 149824 | 0 | 100.0% | Finished | 149824 | 149824
29 | v0 electricity | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 | 2007-08-02 08:00 | 15d | 6400 | 0 | 0 | 0 | 0 | 6400 | 0 | 100.0% | Finished | 6400 | 6400
30 | v0 sanitary | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 | 2007-08-29 08:00 | 10d | 7673 | 0 | 0 | 0 | 0 | 7673 | 0 | 100.0% | Finished | 7673 | 7673
31 | construction leave | 2007-08-15 10:00 | 2007-08-29 10:00 | 10d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2007-08-08 08:00 | 10d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100.0% | Finished | 0.01 | 0.01
32 | stucco | 2007-09-26 10:00 | 2007-10-17 10:00 | 15d | stucco[3.0 #4] | 14896.8 | 8642 | 0 | 0 | 23538.8 | 2958466 | 0 | 0 | 23538.8 | 15d | 0 | 0 | 0 | 23538.8 | 0.0% | Not Started | 0 | 23538.8
34 | v1screed | 2007-08-29 10:00 | 2007-09-19 10:00 | 15d | chapen[2.0 #3] | 0 | 106140 | 0 | 0 | 106140 | 2007-08-29 08:00 | 15d | 106140 | 0 | 0 | 0 | 0 | 106140 | 0 | 100.0% | Finished | 106140 | 106140
35 | v0 floors | 2007-10-03 10:00 | 2007-10-31 10:00 | 20d | flooring | 6649.6 | 75000 | 0 | 0 | 81649.6 | 2007-09-26 08:00 | 20d | 81649.6 | 0 | 0 | 0 | 0 | 81649.6 | 0 | 100.0% | Finished | 81649.6 | 81649.6
36 | drywall | 2007-10-24 10:00 | 2007-11-28 10:00 | 25d |  | 0 | 48000 | 0 | 0 | 48000 | 2958466 | 0 | 0 | 48000 | 25d | 0 | 0 | 0 | 48000 | 0.0% | Not Started | 0 | 48000
37 | techniques | 2007-10-31 10:00 | 2007-11-21 10:00 | 15d |  | 0 | 2156.0601 | 0 | 0 | 2156.0601 | 2958466 | 0 | 0 | 2156.0601 | 15d | 0 | 0 | 0 | 2156.0601 | 0.0% | Not Started | 0 | 2156.0601
38 | suspended ceiling | 2007-11-21 10:00 | 2007-11-28 10:00 | 5d |  | 0 | 32000 | 0 | 0 | 32000 | 2958466 | 0 | 0 | 32000 | 5d | 0 | 0 | 0 | 32000 | 0.0% | Not Started | 0 | 32000
39 | painting | 2007-11-28 10:00 | 2007-12-19 10:00 | 15d | painter[4.0 #6] | 16800 | 83000 | 0 | 0 | 99800 | 2958466 | 0 | 0 | 99800 | 15d | 0 | 0 | 0 | 99800 | 0.0% | Not Started | 0 | 99800
40 | furniture | 2007-12-19 10:00 | 2007-12-26 10:00 | 5d | furniture[5.0 #5] | 8400 | 130000 | 0 | 0 | 138400 | 2958466 | 0 | 0 | 138400 | 5d | 0 | 0 | 0 | 138400 | 0.0% | Not Started | 0 | 138400
41 | kitchen and bar | 2007-10-31 10:00 | 2007-11-21 10:00 | 15d |  | 0 | 87000 | 0 | 0 | 87000 | 2958466 | 0 | 0 | 87000 | 15d | 0 | 0 | 0 | 87000 | 0.0% | Not Started | 0 | 87000
42 | entrance doors | 2007-11-21 10:00 | 2007-12-05 10:00 | 10d |  | 0 | 16000 | 0 | 0 | 16000 | 2958466 | 0 | 0 | 16000 | 10d | 0 | 0 | 0 | 16000 | 0.0% | Not Started | 0 | 16000
43 | elevator | 2007-11-21 10:00 | 2007-11-28 10:00 | 5d |  | 0 | 38817.8516 | 0 | 0 | 38817.8516 | 2958466 | 0 | 0 | 38817.8516 | 5d | 0 | 0 | 0 | 38817.8516 | 0.0% | Not Started | 0 | 38817.8516
44 | stairs | 2007-11-21 10:00 | 2007-12-05 10:00 | 10d |  | 0 | 33000 | 0 | 0 | 33000 | 2958466 | 0 | 0 | 33000 | 10d | 0 | 0 | 0 | 33000 | 0.0% | Not Started | 0 | 33000
45 | vI masonry | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 40.65 | 3252.0001 | 37704.9611 | 2007-08-29 08:00 | 10d | 37704.9611 | 0 | 0 | 0 | 0 | 37704.9611 | 0 | 100.0% | Finished | 66972.9622 | 37704.9611
49 | roof | 2007-04-27 08:00 | 2007-05-10 17:00 | 10d | roofing[4.0 #4] | 11520 | 70779.5703 | 40.3 | 3223.9999 | 85523.5703 | 2007-06-04 08:00 | 10d | 85523.5703 | 0 | 0 | 0 | 0 | 85523.5703 | 0 | 100.0% | Finished | 114539.5697 | 85523.5703
51 | vI electricity | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 | 2007-08-29 08:00 | 25d | 6400 | 0 | 0 | 0 | 0 | 6400 | 0 | 100.0% | Finished | 6400 | 6400
52 | vI sanitary | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 | 2007-08-29 08:00 | 10d | 7673 | 0 | 0 | 0 | 0 | 7673 | 0 | 100.0% | Finished | 7673 | 7673
53 | v2 sanitary | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 | 2007-08-29 08:00 | 10d | 7673 | 0 | 0 | 0 | 0 | 7673 | 0 | 100.0% | Finished | 7673 | 7673
54 | v2 electricity | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 | 2007-08-29 08:00 | 20d | 6400 | 0 | 0 | 0 | 0 | 6400 | 0 | 100.0% | Finished | 6400 | 6400
55 | v2 masonry | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 0 | 0 | 34452.9609 | 2007-08-29 08:00 | 10d | 34452.9609 | 0 | 0 | 0 | 0 | 34452.9609 | 0 | 100.0% | Finished | 34452.9609 | 34452.9609
56 | v2 screed | 2007-08-29 10:00 | 2007-09-19 10:00 | 15d | chapen | 0 | 46116 | 0 | 0 | 46116 | 2007-08-29 08:00 | 15d | 46116 | 0 | 0 | 0 | 0 | 46116 | 0 | 100.0% | Finished | 46116 | 46116
57 | v1flooring | 2007-09-26 10:00 | 2007-10-24 10:00 | 20d | flooring | 6649.6 | 72500 | 0 | 0 | 79149.6 | 2007-10-03 08:00 | 20d | 63319.6809 | 15829.9191 | 5d | 0 | 0 | 63319.6809 | 15829.9191 | 80.0000011920929% | Started | 77819.6801 | 79149.6
58 | v2 flooring | 2007-09-26 10:00 | 2007-10-24 10:00 | 20d | flooring | 6649.6 | 31500 | 0 | 0 | 38149.6 | 2007-09-26 08:00 | 20d | 38149.6 | 0 | 0 | 0 | 0 | 38149.6 | 0 | 100.0% | Finished | 38149.6 | 38149.6
59 | v0 heating | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | heating | 6912 | 11651 | 0 | 0 | 18563 | 2007-08-29 08:00 | 20d | 18563 | 0 | 0 | 0 | 0 | 18563 | 0 | 100.0% | Finished | 18563 | 18563
60 | v1 heating | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | heating | 6912 | 11651 | 43.2 | 6912.0001 | 25475.0001 | 2007-08-29 08:00 | 20d | 25475.0001 | 0 | 0 | 0 | 0 | 25475.0001 | 0 | 100.0% | Finished | 156803.0024 | 25475.0001
61 | v2 heating | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | electrician | 5120 | 11651 | 0 | 0 | 16771 | 2007-08-29 08:00 | 20d | 16771 | 0 | 0 | 0 | 0 | 16771 | 0 | 100.0% | Finished | 16771 | 16771
67 | v1 drying screed | 2007-09-19 10:00 | 2007-09-26 10:00 | 5d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2007-09-19 08:00 | 5d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100.0% | Finished | 0.01 | 0.01
68 | v2 drying screed | 2007-09-19 10:00 | 2007-09-26 10:00 | 5d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2007-09-19 08:00 | 5d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100.0% | Finished | 0.01 | 0.01
69 | soil analyses | 2006-12-11 08:00 | 2006-12-12 17:00 | 2d | team VDW | 616.96 | 2000 | 0 | 0 | 2616.96 | 2007-02-08 08:00 | 12d | 2616.96 | 0 | 0 | 0 | 0 | 2616.96 | 0 | 100.0% | Finished | 2616.96 | 2616.96

## TP7
| TP Status Date | 2008-01-10 08:00 |  | TP Name | Completion
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Absolute baseline duration | Absolute actual duration | Absolute completed | Baseline cost | Actual cost | Absolute percentage completed
2 | building permit | 2006-04-17 08:00 | 2006-07-07 17:00 | 60d |  | 0 | 75 | 0 | 0 | 75 | 2006-04-17 08:00 | 100d | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100.0% | Finished | 75 | 75
3 | hire contractor | 2006-07-10 08:00 | 2006-08-04 17:00 | 20d |  | 0 | 210000 | 0 | 0 | 210000 | 2006-09-04 08:00 | 30d | 210000 | 0 | 0 | 0 | 0 | 210000 | 0 | 100.0% | Finished | 210000 | 210000
4 | temporary offices | 2006-04-17 08:00 | 2006-05-12 17:00 | 20d |  | 0 | 3765.3101 | 0 | 0 | 3765.3101 | 2006-04-17 08:00 | 20d | 3765.3101 | 0 | 0 | 0 | 0 | 3765.3101 | 0 | 100.0% | Finished | 3765.3101 | 3765.3101
5 | temporary facilities | 2006-04-17 08:00 | 2006-07-07 17:00 | 60d |  | 0 | 1876.54 | 0 | 0 | 1876.54 | 2006-04-17 08:00 | 60d | 1876.54 | 0 | 0 | 0 | 0 | 1876.54 | 0 | 100.0% | Finished | 1876.54 | 1876.54
6 | demolition | 2006-10-30 08:00 | 2006-12-08 17:00 | 30d | team VDW[4.0 #8] | 37017.6 | 1070.11 | 0 | 0 | 38087.71 | 2006-11-27 08:00 | 54d | 38087.71 | 0 | 0 | 0 | 0 | 38087.71 | 0 | 100.0% | Finished | 38087.71 | 38087.71
16 | preparation contractor | 2006-08-07 08:00 | 2006-10-27 17:00 | 60d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2006-09-04 08:00 | 60d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100.0% | Finished | 0.01 | 0.01
17 | excavation | 2006-12-11 08:00 | 2006-12-28 17:00 | 14d | team VDW | 4318.72 | 26000 | 0 | 0 | 30318.72 | 2007-02-08 08:00 | 10d | 30318.72 | 0 | 0 | 0 | 0 | 30318.72 | 0 | 100.0% | Finished | 30318.72 | 30318.72
18 | foundation beam | 2006-12-29 08:00 | 2007-02-01 17:00 | 25d | team VDW[3.0 #8] | 23136 | 98523.7266 | 0 | 0 | 121659.7266 | 2007-02-28 08:00 | 22d | 121659.7266 | 0 | 0 | 0 | 0 | 121659.7266 | 0 | 100.0% | Finished | 121659.7266 | 121659.7266
19 | steelframe I | 2007-02-02 08:00 | 2007-03-01 17:00 | 20d | team VDW[4.0 #8] | 24678.4 | 118992.5078 | 0 | 0 | 143670.9078 | 2007-04-02 08:00 | 15d | 143670.9078 | 0 | 0 | 0 | 0 | 143670.9078 | 0 | 100.0% | Finished | 143670.9078 | 143670.9078
20 | concrete vaults I | 2007-03-02 08:00 | 2007-03-15 17:00 | 10d | team VDW[4.0 #8] | 12339.2 | 117409.7188 | 0 | 0 | 129748.9187 | 2007-04-23 08:00 | 5d | 129748.9187 | 0 | 0 | 0 | 0 | 129748.9187 | 0 | 100.0% | Finished | 129748.9187 | 129748.9187
21 | placing sewerage | 2006-12-29 08:00 | 2007-01-11 17:00 | 10d | team VDW[3.0 #8] | 9254.4 | 1224.73 | 0 | 0 | 10479.13 | 2007-02-28 08:00 | 12d | 10479.13 | 0 | 0 | 0 | 0 | 10479.13 | 0 | 100.0% | Finished | 10479.13 | 10479.13
22 | steelframe II | 2007-03-16 08:00 | 2007-04-05 17:00 | 15d | team VDW[3.0 #8] | 13881.6 | 118992.5078 | 0 | 0 | 132874.1078 | 2007-04-30 08:00 | 15d | 132874.1078 | 0 | 0 | 0 | 0 | 132874.1078 | 0 | 100.0% | Finished | 132874.1078 | 132874.1078
23 | foundation plate | 2007-01-12 08:00 | 2007-01-12 17:00 | 1d | team VDW[5.0 #8] | 1542.4 | 234819.4375 | 0 | 0 | 236361.8375 | 2007-03-16 08:00 | 1d | 236361.8375 | 0 | 0 | 0 | 0 | 236361.8375 | 0 | 100.0% | Finished | 236361.8375 | 236361.8375
24 | concrete volt II | 2007-04-06 08:00 | 2007-04-26 17:00 | 15d | team VDW[4.0 #8] | 18508.8 | 117409.7188 | 0 | 0 | 135918.5187 | 2007-05-21 08:00 | 10d | 135918.5187 | 0 | 0 | 0 | 0 | 135918.5187 | 0 | 100.0% | Finished | 135918.5187 | 135918.5187
25 | facades | 2007-04-27 08:00 | 2007-05-24 17:00 | 20d | team VDW[2.0 #8] | 12339.2 | 339314 | 0 | 0 | 351653.2 | 2007-06-04 08:00 | 20d | 351653.2 | 0 | 0 | 0 | 0 | 351653.2 | 0 | 100.0% | Finished | 351653.2 | 351653.2
26 | outside windows | 2007-05-25 08:00 | 2007-06-07 17:00 | 10d | windows[3.0 #3] | 9120 | 150750.5938 | 0 | 0 | 159870.5938 | 2007-07-02 08:00 | 92d | 159870.5938 | 0 | 0 | 0 | 0 | 159870.5938 | 0 | 100.0% | Finished | 159870.5938 | 159870.5938
27 | v0 -masonry | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 40.65 | 3252.0001 | 37704.9611 | 2007-08-29 08:00 | 10d | 37704.9611 | 0 | 0 | 0 | 0 | 37704.9611 | 0 | 100.0% | Finished | 66972.9622 | 37704.9611
28 | v0 polierbeton | 2007-06-08 08:00 | 2007-06-21 17:00 | 10d | team VDW[5.0 #8] | 15424 | 134400 | 0 | 0 | 149824 | 2007-07-25 08:00 | 5d | 149824 | 0 | 0 | 0 | 0 | 149824 | 0 | 100.0% | Finished | 149824 | 149824
29 | v0 electricity | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 | 2007-08-02 08:00 | 15d | 6400 | 0 | 0 | 0 | 0 | 6400 | 0 | 100.0% | Finished | 6400 | 6400
30 | v0 sanitary | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 | 2007-08-29 08:00 | 10d | 7673 | 0 | 0 | 0 | 0 | 7673 | 0 | 100.0% | Finished | 7673 | 7673
31 | construction leave | 2007-08-15 10:00 | 2007-08-29 10:00 | 10d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2007-08-08 08:00 | 10d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100.0% | Finished | 0.01 | 0.01
32 | stucco | 2007-09-26 10:00 | 2007-10-17 10:00 | 15d | stucco[3.0 #4] | 14896.8 | 8642 | 0 | 0 | 23538.8 | 2007-11-05 08:00 | 15d | 23538.8 | 0 | 0 | 0 | 0 | 23538.8 | 0 | 100.0% | Finished | 23538.8 | 23538.8
34 | v1screed | 2007-08-29 10:00 | 2007-09-19 10:00 | 15d | chapen[2.0 #3] | 0 | 106140 | 0 | 0 | 106140 | 2007-08-29 08:00 | 15d | 106140 | 0 | 0 | 0 | 0 | 106140 | 0 | 100.0% | Finished | 106140 | 106140
35 | v0 floors | 2007-10-03 10:00 | 2007-10-31 10:00 | 20d | flooring | 6649.6 | 75000 | 0 | 0 | 81649.6 | 2007-09-26 08:00 | 20d | 81649.6 | 0 | 0 | 0 | 0 | 81649.6 | 0 | 100.0% | Finished | 81649.6 | 81649.6
36 | drywall | 2007-10-24 10:00 | 2007-11-28 10:00 | 25d |  | 0 | 48000 | 0 | 0 | 48000 | 2007-11-05 08:00 | 25d | 48000 | 0 | 0 | 0 | 0 | 48000 | 0 | 100.0% | Finished | 48000 | 48000
37 | techniques | 2007-10-31 10:00 | 2007-11-21 10:00 | 15d |  | 0 | 2156.0601 | 0 | 0 | 2156.0601 | 2007-11-26 08:00 | 15d | 2156.0601 | 0 | 0 | 0 | 0 | 2156.0601 | 0 | 100.0% | Finished | 2156.0601 | 2156.0601
38 | suspended ceiling | 2007-11-21 10:00 | 2007-11-28 10:00 | 5d |  | 0 | 32000 | 0 | 0 | 32000 | 2007-12-10 08:00 | 5d | 32000 | 0 | 0 | 0 | 0 | 32000 | 0 | 100.0% | Finished | 32000 | 32000
39 | painting | 2007-11-28 10:00 | 2007-12-19 10:00 | 15d | painter[4.0 #6] | 16800 | 83000 | 0 | 0 | 99800 | 2007-12-17 08:00 | 15d | 99800 | 0 | 0 | 0 | 0 | 99800 | 0 | 100.0% | Finished | 99800 | 99800
40 | furniture | 2007-12-19 10:00 | 2007-12-26 10:00 | 5d | furniture[5.0 #5] | 8400 | 130000 | 0 | 0 | 138400 | 2008-01-03 08:00 | 5d | 138400 | 0 | 0 | 0 | 0 | 138400 | 0 | 100.0% | Finished | 138400 | 138400
41 | kitchen and bar | 2007-10-31 10:00 | 2007-11-21 10:00 | 15d |  | 0 | 87000 | 0 | 0 | 87000 | 2007-11-26 08:00 | 20d | 87000 | 0 | 0 | 0 | 0 | 87000 | 0 | 100.0% | Finished | 87000 | 87000
42 | entrance doors | 2007-11-21 10:00 | 2007-12-05 10:00 | 10d |  | 0 | 16000 | 0 | 0 | 16000 | 2007-12-10 08:00 | 10d | 16000 | 0 | 0 | 0 | 0 | 16000 | 0 | 100.0% | Finished | 16000 | 16000
43 | elevator | 2007-11-21 10:00 | 2007-11-28 10:00 | 5d |  | 0 | 38817.8516 | 0 | 0 | 38817.8516 | 2007-12-10 08:00 | 5d | 38817.8516 | 0 | 0 | 0 | 0 | 38817.8516 | 0 | 100.0% | Finished | 38817.8516 | 38817.8516
44 | stairs | 2007-11-21 10:00 | 2007-12-05 10:00 | 10d |  | 0 | 33000 | 0 | 0 | 33000 | 2007-12-10 08:00 | 10d | 33000 | 0 | 0 | 0 | 0 | 33000 | 0 | 100.0% | Finished | 33000 | 33000
45 | vI masonry | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 40.65 | 3252.0001 | 37704.9611 | 2007-08-29 08:00 | 10d | 37704.9611 | 0 | 0 | 0 | 0 | 37704.9611 | 0 | 100.0% | Finished | 66972.9622 | 37704.9611
49 | roof | 2007-04-27 08:00 | 2007-05-10 17:00 | 10d | roofing[4.0 #4] | 11520 | 70779.5703 | 40.3 | 3223.9999 | 85523.5703 | 2007-06-04 08:00 | 10d | 85523.5703 | 0 | 0 | 0 | 0 | 85523.5703 | 0 | 100.0% | Finished | 114539.5697 | 85523.5703
51 | vI electricity | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 | 2007-08-29 08:00 | 25d | 6400 | 0 | 0 | 0 | 0 | 6400 | 0 | 100.0% | Finished | 6400 | 6400
52 | vI sanitary | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 | 2007-08-29 08:00 | 10d | 7673 | 0 | 0 | 0 | 0 | 7673 | 0 | 100.0% | Finished | 7673 | 7673
53 | v2 sanitary | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 | 2007-08-29 08:00 | 10d | 7673 | 0 | 0 | 0 | 0 | 7673 | 0 | 100.0% | Finished | 7673 | 7673
54 | v2 electricity | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 | 2007-08-29 08:00 | 20d | 6400 | 0 | 0 | 0 | 0 | 6400 | 0 | 100.0% | Finished | 6400 | 6400
55 | v2 masonry | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 0 | 0 | 34452.9609 | 2007-08-29 08:00 | 10d | 34452.9609 | 0 | 0 | 0 | 0 | 34452.9609 | 0 | 100.0% | Finished | 34452.9609 | 34452.9609
56 | v2 screed | 2007-08-29 10:00 | 2007-09-19 10:00 | 15d | chapen | 0 | 46116 | 0 | 0 | 46116 | 2007-08-29 08:00 | 15d | 46116 | 0 | 0 | 0 | 0 | 46116 | 0 | 100.0% | Finished | 46116 | 46116
57 | v1flooring | 2007-09-26 10:00 | 2007-10-24 10:00 | 20d | flooring | 6649.6 | 72500 | 0 | 0 | 79149.6 | 2007-10-03 08:00 | 20d | 79149.6 | 0 | 0 | 0 | 0 | 79149.6 | 0 | 100.0% | Finished | 79149.6 | 79149.6
58 | v2 flooring | 2007-09-26 10:00 | 2007-10-24 10:00 | 20d | flooring | 6649.6 | 31500 | 0 | 0 | 38149.6 | 2007-09-26 08:00 | 20d | 38149.6 | 0 | 0 | 0 | 0 | 38149.6 | 0 | 100.0% | Finished | 38149.6 | 38149.6
59 | v0 heating | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | heating | 6912 | 11651 | 0 | 0 | 18563 | 2007-08-29 08:00 | 20d | 18563 | 0 | 0 | 0 | 0 | 18563 | 0 | 100.0% | Finished | 18563 | 18563
60 | v1 heating | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | heating | 6912 | 11651 | 43.2 | 6912.0001 | 25475.0001 | 2007-08-29 08:00 | 20d | 25475.0001 | 0 | 0 | 0 | 0 | 25475.0001 | 0 | 100.0% | Finished | 156803.0024 | 25475.0001
61 | v2 heating | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | electrician | 5120 | 11651 | 0 | 0 | 16771 | 2007-08-29 08:00 | 20d | 16771 | 0 | 0 | 0 | 0 | 16771 | 0 | 100.0% | Finished | 16771 | 16771
67 | v1 drying screed | 2007-09-19 10:00 | 2007-09-26 10:00 | 5d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2007-09-19 08:00 | 5d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100.0% | Finished | 0.01 | 0.01
68 | v2 drying screed | 2007-09-19 10:00 | 2007-09-26 10:00 | 5d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2007-09-19 08:00 | 5d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100.0% | Finished | 0.01 | 0.01
69 | soil analyses | 2006-12-11 08:00 | 2006-12-12 17:00 | 2d | team VDW | 616.96 | 2000 | 0 | 0 | 2616.96 | 2007-02-08 08:00 | 12d | 2616.96 | 0 | 0 | 0 | 0 | 2616.96 | 0 | 100.0% | Finished | 2616.96 | 2616.96

## TP8
| TP Status Date | 2008-01-11 08:00 |  | TP Name | Finish
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking | [12 empty] | Time |  |  | Costs
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Absolute baseline duration | Absolute actual duration | Absolute completed | Baseline cost | Actual cost | Absolute percentage completed
2 | building permit | 2006-04-17 08:00 | 2006-07-07 17:00 | 60d |  | 0 | 75 | 0 | 0 | 75 | 2006-04-17 08:00 | 100d | 75 | 0 | 0 | 0 | 0 | 75 | 0 | 100.0% | Finished | 75 | 75
3 | hire contractor | 2006-07-10 08:00 | 2006-08-04 17:00 | 20d |  | 0 | 210000 | 0 | 0 | 210000 | 2006-09-04 08:00 | 30d | 210000 | 0 | 0 | 0 | 0 | 210000 | 0 | 100.0% | Finished | 210000 | 210000
4 | temporary offices | 2006-04-17 08:00 | 2006-05-12 17:00 | 20d |  | 0 | 3765.3101 | 0 | 0 | 3765.3101 | 2006-04-17 08:00 | 20d | 3765.3101 | 0 | 0 | 0 | 0 | 3765.3101 | 0 | 100.0% | Finished | 3765.3101 | 3765.3101
5 | temporary facilities | 2006-04-17 08:00 | 2006-07-07 17:00 | 60d |  | 0 | 1876.54 | 0 | 0 | 1876.54 | 2006-04-17 08:00 | 60d | 1876.54 | 0 | 0 | 0 | 0 | 1876.54 | 0 | 100.0% | Finished | 1876.54 | 1876.54
6 | demolition | 2006-10-30 08:00 | 2006-12-08 17:00 | 30d | team VDW[4.0 #8] | 37017.6 | 1070.11 | 0 | 0 | 38087.71 | 2006-11-27 08:00 | 54d | 38087.71 | 0 | 0 | 0 | 0 | 38087.71 | 0 | 100.0% | Finished | 38087.71 | 38087.71
16 | preparation contractor | 2006-08-07 08:00 | 2006-10-27 17:00 | 60d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2006-09-04 08:00 | 60d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100.0% | Finished | 0.01 | 0.01
17 | excavation | 2006-12-11 08:00 | 2006-12-28 17:00 | 14d | team VDW | 4318.72 | 26000 | 0 | 0 | 30318.72 | 2007-02-08 08:00 | 10d | 30318.72 | 0 | 0 | 0 | 0 | 30318.72 | 0 | 100.0% | Finished | 30318.72 | 30318.72
18 | foundation beam | 2006-12-29 08:00 | 2007-02-01 17:00 | 25d | team VDW[3.0 #8] | 23136 | 98523.7266 | 0 | 0 | 121659.7266 | 2007-02-28 08:00 | 22d | 121659.7266 | 0 | 0 | 0 | 0 | 121659.7266 | 0 | 100.0% | Finished | 121659.7266 | 121659.7266
19 | steelframe I | 2007-02-02 08:00 | 2007-03-01 17:00 | 20d | team VDW[4.0 #8] | 24678.4 | 118992.5078 | 0 | 0 | 143670.9078 | 2007-04-02 08:00 | 15d | 143670.9078 | 0 | 0 | 0 | 0 | 143670.9078 | 0 | 100.0% | Finished | 143670.9078 | 143670.9078
20 | concrete vaults I | 2007-03-02 08:00 | 2007-03-15 17:00 | 10d | team VDW[4.0 #8] | 12339.2 | 117409.7188 | 0 | 0 | 129748.9187 | 2007-04-23 08:00 | 5d | 129748.9187 | 0 | 0 | 0 | 0 | 129748.9187 | 0 | 100.0% | Finished | 129748.9187 | 129748.9187
21 | placing sewerage | 2006-12-29 08:00 | 2007-01-11 17:00 | 10d | team VDW[3.0 #8] | 9254.4 | 1224.73 | 0 | 0 | 10479.13 | 2007-02-28 08:00 | 12d | 10479.13 | 0 | 0 | 0 | 0 | 10479.13 | 0 | 100.0% | Finished | 10479.13 | 10479.13
22 | steelframe II | 2007-03-16 08:00 | 2007-04-05 17:00 | 15d | team VDW[3.0 #8] | 13881.6 | 118992.5078 | 0 | 0 | 132874.1078 | 2007-04-30 08:00 | 15d | 132874.1078 | 0 | 0 | 0 | 0 | 132874.1078 | 0 | 100.0% | Finished | 132874.1078 | 132874.1078
23 | foundation plate | 2007-01-12 08:00 | 2007-01-12 17:00 | 1d | team VDW[5.0 #8] | 1542.4 | 234819.4375 | 0 | 0 | 236361.8375 | 2007-03-16 08:00 | 1d | 236361.8375 | 0 | 0 | 0 | 0 | 236361.8375 | 0 | 100.0% | Finished | 236361.8375 | 236361.8375
24 | concrete volt II | 2007-04-06 08:00 | 2007-04-26 17:00 | 15d | team VDW[4.0 #8] | 18508.8 | 117409.7188 | 0 | 0 | 135918.5187 | 2007-05-21 08:00 | 10d | 135918.5187 | 0 | 0 | 0 | 0 | 135918.5187 | 0 | 100.0% | Finished | 135918.5187 | 135918.5187
25 | facades | 2007-04-27 08:00 | 2007-05-24 17:00 | 20d | team VDW[2.0 #8] | 12339.2 | 339314 | 0 | 0 | 351653.2 | 2007-06-04 08:00 | 20d | 351653.2 | 0 | 0 | 0 | 0 | 351653.2 | 0 | 100.0% | Finished | 351653.2 | 351653.2
26 | outside windows | 2007-05-25 08:00 | 2007-06-07 17:00 | 10d | windows[3.0 #3] | 9120 | 150750.5938 | 0 | 0 | 159870.5938 | 2007-07-02 08:00 | 92d | 159870.5938 | 0 | 0 | 0 | 0 | 159870.5938 | 0 | 100.0% | Finished | 159870.5938 | 159870.5938
27 | v0 -masonry | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 40.65 | 3252.0001 | 37704.9611 | 2007-08-29 08:00 | 10d | 37704.9611 | 0 | 0 | 0 | 0 | 37704.9611 | 0 | 100.0% | Finished | 66972.9622 | 37704.9611
28 | v0 polierbeton | 2007-06-08 08:00 | 2007-06-21 17:00 | 10d | team VDW[5.0 #8] | 15424 | 134400 | 0 | 0 | 149824 | 2007-07-25 08:00 | 5d | 149824 | 0 | 0 | 0 | 0 | 149824 | 0 | 100.0% | Finished | 149824 | 149824
29 | v0 electricity | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 | 2007-08-02 08:00 | 15d | 6400 | 0 | 0 | 0 | 0 | 6400 | 0 | 100.0% | Finished | 6400 | 6400
30 | v0 sanitary | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 | 2007-08-29 08:00 | 10d | 7673 | 0 | 0 | 0 | 0 | 7673 | 0 | 100.0% | Finished | 7673 | 7673
31 | construction leave | 2007-08-15 10:00 | 2007-08-29 10:00 | 10d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2007-08-08 08:00 | 10d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100.0% | Finished | 0.01 | 0.01
32 | stucco | 2007-09-26 10:00 | 2007-10-17 10:00 | 15d | stucco[3.0 #4] | 14896.8 | 8642 | 0 | 0 | 23538.8 | 2007-11-05 08:00 | 15d | 23538.8 | 0 | 0 | 0 | 0 | 23538.8 | 0 | 100.0% | Finished | 23538.8 | 23538.8
34 | v1screed | 2007-08-29 10:00 | 2007-09-19 10:00 | 15d | chapen[2.0 #3] | 0 | 106140 | 0 | 0 | 106140 | 2007-08-29 08:00 | 15d | 106140 | 0 | 0 | 0 | 0 | 106140 | 0 | 100.0% | Finished | 106140 | 106140
35 | v0 floors | 2007-10-03 10:00 | 2007-10-31 10:00 | 20d | flooring | 6649.6 | 75000 | 0 | 0 | 81649.6 | 2007-09-26 08:00 | 20d | 81649.6 | 0 | 0 | 0 | 0 | 81649.6 | 0 | 100.0% | Finished | 81649.6 | 81649.6
36 | drywall | 2007-10-24 10:00 | 2007-11-28 10:00 | 25d |  | 0 | 48000 | 0 | 0 | 48000 | 2007-11-05 08:00 | 25d | 48000 | 0 | 0 | 0 | 0 | 48000 | 0 | 100.0% | Finished | 48000 | 48000
37 | techniques | 2007-10-31 10:00 | 2007-11-21 10:00 | 15d |  | 0 | 2156.0601 | 0 | 0 | 2156.0601 | 2007-11-26 08:00 | 15d | 2156.0601 | 0 | 0 | 0 | 0 | 2156.0601 | 0 | 100.0% | Finished | 2156.0601 | 2156.0601
38 | suspended ceiling | 2007-11-21 10:00 | 2007-11-28 10:00 | 5d |  | 0 | 32000 | 0 | 0 | 32000 | 2007-12-10 08:00 | 5d | 32000 | 0 | 0 | 0 | 0 | 32000 | 0 | 100.0% | Finished | 32000 | 32000
39 | painting | 2007-11-28 10:00 | 2007-12-19 10:00 | 15d | painter[4.0 #6] | 16800 | 83000 | 0 | 0 | 99800 | 2007-12-17 08:00 | 15d | 99800 | 0 | 0 | 0 | 0 | 99800 | 0 | 100.0% | Finished | 99800 | 99800
40 | furniture | 2007-12-19 10:00 | 2007-12-26 10:00 | 5d | furniture[5.0 #5] | 8400 | 130000 | 0 | 0 | 138400 | 2008-01-03 08:00 | 5d | 138400 | 0 | 0 | 0 | 0 | 138400 | 0 | 100.0% | Finished | 138400 | 138400
41 | kitchen and bar | 2007-10-31 10:00 | 2007-11-21 10:00 | 15d |  | 0 | 87000 | 0 | 0 | 87000 | 2007-11-26 08:00 | 20d | 87000 | 0 | 0 | 0 | 0 | 87000 | 0 | 100.0% | Finished | 87000 | 87000
42 | entrance doors | 2007-11-21 10:00 | 2007-12-05 10:00 | 10d |  | 0 | 16000 | 0 | 0 | 16000 | 2007-12-10 08:00 | 10d | 16000 | 0 | 0 | 0 | 0 | 16000 | 0 | 100.0% | Finished | 16000 | 16000
43 | elevator | 2007-11-21 10:00 | 2007-11-28 10:00 | 5d |  | 0 | 38817.8516 | 0 | 0 | 38817.8516 | 2007-12-10 08:00 | 5d | 38817.8516 | 0 | 0 | 0 | 0 | 38817.8516 | 0 | 100.0% | Finished | 38817.8516 | 38817.8516
44 | stairs | 2007-11-21 10:00 | 2007-12-05 10:00 | 10d |  | 0 | 33000 | 0 | 0 | 33000 | 2007-12-10 08:00 | 10d | 33000 | 0 | 0 | 0 | 0 | 33000 | 0 | 100.0% | Finished | 33000 | 33000
45 | vI masonry | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 40.65 | 3252.0001 | 37704.9611 | 2007-08-29 08:00 | 10d | 37704.9611 | 0 | 0 | 0 | 0 | 37704.9611 | 0 | 100.0% | Finished | 66972.9622 | 37704.9611
49 | roof | 2007-04-27 08:00 | 2007-05-10 17:00 | 10d | roofing[4.0 #4] | 11520 | 70779.5703 | 40.3 | 3223.9999 | 85523.5703 | 2007-06-04 08:00 | 10d | 85523.5703 | 0 | 0 | 0 | 0 | 85523.5703 | 0 | 100.0% | Finished | 114539.5697 | 85523.5703
51 | vI electricity | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 | 2007-08-29 08:00 | 25d | 6400 | 0 | 0 | 0 | 0 | 6400 | 0 | 100.0% | Finished | 6400 | 6400
52 | vI sanitary | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 | 2007-08-29 08:00 | 10d | 7673 | 0 | 0 | 0 | 0 | 7673 | 0 | 100.0% | Finished | 7673 | 7673
53 | v2 sanitary | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673 | 2007-08-29 08:00 | 10d | 7673 | 0 | 0 | 0 | 0 | 7673 | 0 | 100.0% | Finished | 7673 | 7673
54 | v2 electricity | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400 | 2007-08-29 08:00 | 20d | 6400 | 0 | 0 | 0 | 0 | 6400 | 0 | 100.0% | Finished | 6400 | 6400
55 | v2 masonry | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 0 | 0 | 34452.9609 | 2007-08-29 08:00 | 10d | 34452.9609 | 0 | 0 | 0 | 0 | 34452.9609 | 0 | 100.0% | Finished | 34452.9609 | 34452.9609
56 | v2 screed | 2007-08-29 10:00 | 2007-09-19 10:00 | 15d | chapen | 0 | 46116 | 0 | 0 | 46116 | 2007-08-29 08:00 | 15d | 46116 | 0 | 0 | 0 | 0 | 46116 | 0 | 100.0% | Finished | 46116 | 46116
57 | v1flooring | 2007-09-26 10:00 | 2007-10-24 10:00 | 20d | flooring | 6649.6 | 72500 | 0 | 0 | 79149.6 | 2007-10-03 08:00 | 20d | 79149.6 | 0 | 0 | 0 | 0 | 79149.6 | 0 | 100.0% | Finished | 79149.6 | 79149.6
58 | v2 flooring | 2007-09-26 10:00 | 2007-10-24 10:00 | 20d | flooring | 6649.6 | 31500 | 0 | 0 | 38149.6 | 2007-09-26 08:00 | 20d | 38149.6 | 0 | 0 | 0 | 0 | 38149.6 | 0 | 100.0% | Finished | 38149.6 | 38149.6
59 | v0 heating | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | heating | 6912 | 11651 | 0 | 0 | 18563 | 2007-08-29 08:00 | 20d | 18563 | 0 | 0 | 0 | 0 | 18563 | 0 | 100.0% | Finished | 18563 | 18563
60 | v1 heating | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | heating | 6912 | 11651 | 43.2 | 6912.0001 | 25475.0001 | 2007-08-29 08:00 | 20d | 25475.0001 | 0 | 0 | 0 | 0 | 25475.0001 | 0 | 100.0% | Finished | 156803.0024 | 25475.0001
61 | v2 heating | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | electrician | 5120 | 11651 | 0 | 0 | 16771 | 2007-08-29 08:00 | 20d | 16771 | 0 | 0 | 0 | 0 | 16771 | 0 | 100.0% | Finished | 16771 | 16771
67 | v1 drying screed | 2007-09-19 10:00 | 2007-09-26 10:00 | 5d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2007-09-19 08:00 | 5d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100.0% | Finished | 0.01 | 0.01
68 | v2 drying screed | 2007-09-19 10:00 | 2007-09-26 10:00 | 5d |  | 0 | 0.01 | 0 | 0 | 0.01 | 2007-09-19 08:00 | 5d | 0.01 | 0 | 0 | 0 | 0 | 0.01 | 0 | 100.0% | Finished | 0.01 | 0.01
69 | soil analyses | 2006-12-11 08:00 | 2006-12-12 17:00 | 2d | team VDW | 616.96 | 2000 | 0 | 0 | 2616.96 | 2007-02-08 08:00 | 12d | 2616.96 | 0 | 0 | 0 | 0 | 2616.96 | 0 | 100.0% | Finished | 2616.96 | 2616.96

## Agenda
Working Hours |  | Working Days |  | Holidays
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI | CPI | SPI(t) | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
Preparation1 | 2006-04-17 08:00 | 2006-07-07 08:00 | 3027133.1861 | 5716.8501 | 5685.3454 | 2006-04-17 08:00 | -3021416.336 | 0% | 31.5047 | 101% | -59d | 0% | 0% | [9 empty] | -31.5047 | 0 | -3021447.8407 |  |  |  | -1418.0011 |  | 0.0018885 | 1.0055 | 0 | 0 | -472 | 1.0055 | 0.2 | 0 | 0.1
Preparation2 | 2006-07-07 08:00 | 2007-02-08 08:00 | 3027133.1861 | 253804.5701 | 253804.5701 | 2006-04-17 08:00 | -2773328.616 | 8% | 0 | 100% | -213d | 0% | 0% | [9 empty] | 0 | 0 | -2773328.616 |  |  |  | -56937.7343 |  | 0.083843 | 1 | 0 | 0 | -1704 | 1 | 0.24286 | 0 | 0.18571
Foundation | 2007-02-08 08:00 | 2007-03-17 08:00 | 3027133.1861 | 647075.3017 | 612302.2414 | 2006-04-17 08:00 | -2380057.8844 | 21% | 34773.0603 | 106% | -240d | 0% | 0% | [9 empty] | -34773.0603 | 1.1642e-10 | -2414830.9446 |  |  |  | -116235.0114 |  | 0.21376 | 1.0568 | 0 | 0 | -1920 | 1.0568 | 0.28571 | 0 | 0.27143
Shell | 2007-03-17 08:00 | 2007-06-04 08:00 | 3027133.1861 | 1183389.3748 | 1115576.4978 | 2006-04-17 08:00 | -1843743.8113 | 39% | 67812.877 | 106% | -295d | 0% | 0% | [9 empty] | -67812.877 | 0 | -1911556.6882 |  |  |  | -161257.5695 |  | 0.39093 | 1.0608 | 0 | 0 | -2360 | 1.0608 | 0.32857 | 0 | 0.35714
Wind&Waterproof | 2007-06-04 08:00 | 2007-07-02 08:00 | 3027133.1861 | 1819107.2505 | 1678531.7632 | 2006-04-17 08:00 | -1208025.9355 | 60% | 140575.4873 | 108% | -315d | 0% | 0% | [9 empty] | -140575.4873 | 0 | -1348601.4229 |  |  |  | -164187.9838 |  | 0.60093 | 1.0837 | 0 | 0 | -2520 | 1.0837 | 0.37143 | 0 | 0.44286
WH, L1, L2 | 2007-07-02 08:00 | 2007-10-24 08:00 | 3027133.1861 | 2725086.5338 | 2477093.8942 | 2006-04-17 08:00 | -302046.6523 | 90% | 247992.6396 | 110% | -397d | 0% | 0% | [9 empty] | -247992.6396 | 0 | -550039.2919 |  |  |  | -93413.8111 |  | 0.90022 | 1.1001 | 0 | 0 | -3176 | 1.1001 | 0.41429 | 0 | 0.52857
Completion | 2007-10-24 08:00 | 2008-01-10 08:00 | 3027133.1861 | 3246013.19 | 3027133.1861 | 2006-12-08 17:00 | 218880.004 | 107% | 218880.004 | 107% | -283d | 38% | 100% | [9 empty] | -218880.004 | 0 | 0 |  |  |  | 0 |  | 1.0723 | 1.0723 | 0.37528 | 1 | -2264 | 1.0723 | 0.45714 | 0.37528 | 0.61429
Finish | 2008-01-10 08:00 | 2008-01-11 08:00 | 3027133.1861 | 3246013.19 | 3027133.1861 | 2006-12-08 17:00 | 218880.004 | 107% | 218880.004 | 107% | -284d | 37% | 100% | [9 empty] | -218880.004 | 0 | 0 |  |  |  | 0 |  | 1.0723 | 1.0723 | 0.37445 | 1 | -2272 | 1.0723 | 0.5 | 0.37445 | 0.7