## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost |  |  | Cost/Hour (calc) | Resources (calc) | [17 empty] | Resource Demand (calc) | [17 empty] | Cost/Use (calc) | [18 empty] | Cost/Unit (calc)
0 | PROJECT CLAEYS-VERHELST | 1
46 | preparation | 1.1
2 | building permit | 1.1.1 |  | FS3 | 2006-04-17 08:00 |  | 60d |  |  | 75 |  | 0 |  | Legend |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | hire contractor | 1.1.2 | 2FS | FS16 | 2006-07-10 08:00 |  | 20d |  |  | 210000 |  | 0 |  |  | Necessary input | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | temporary offices | 1.1.3 |  |  | 2006-04-17 08:00 |  | 20d |  |  | 3765.3101 |  | 0 |  |  | Additional input | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | temporary facilities | 1.1.4 |  |  | 2006-04-17 08:00 |  | 60d |  |  | 1876.54 |  | 0 |  |  | Output | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | preparation contractor | 1.1.5 | 3FS | FS6 | 2006-08-07 08:00 |  | 60d |  |  | 0.01 |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | demolition | 1.1.6 | 16FS | FS17;FS69 | 2006-10-30 08:00 |  | 30d | team subcontractor[4,00 #8] |  | 1070.11 |  | 0 |  | For further explanation, see Guideline for project data input |  | 0 | team subcontractor[4,00 #8] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4,00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154.24
47 | foundation | 1.2
17 | excavation | 1.2.1 | 6FS | FS18;FS21 | 2006-12-11 08:00 |  | 14d | team subcontractor |  | 26000 |  | 0 |  |  |  | 0 | team subcontractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.56
69 | soil analyses | 1.2.2 | 6FS | FS18 | 2006-12-11 08:00 |  | 2d | team subcontractor |  | 2000 |  | 0 |  |  |  | 0 | team subcontractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.56
18 | foundation beam | 1.2.3 | 17FS;69FS | FS19 | 2006-12-29 08:00 |  | 25d | team subcontractor[3,00 #8] |  | 98523.7266 |  | 0 |  |  |  | 0 | team subcontractor[3,00 #8] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3,00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115.68
21 | placing sewerage | 1.2.4 | 17FS | FS23 | 2006-12-29 08:00 |  | 10d | team subcontractor[3,00 #8] |  | 1224.73 |  | 0 |  |  |  | 0 | team subcontractor[3,00 #8] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3,00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115.68
23 | foundation plate | 1.2.5 | 21FS | FS19 | 2007-01-12 08:00 |  | 1d | team subcontractor[5,00 #8] |  | 234819.4375 |  | 0 |  |  |  | 0 | team subcontractor[5,00 #8] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5,00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 192.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 192.8
48 | shell | 1.3
19 | steelframe I | 1.3.1 | 18FS;23FS | FS20 | 2007-02-02 08:00 |  | 20d | team subcontractor[4,00 #8] |  | 118992.5078 |  | 0 |  |  |  | 0 | team subcontractor[4,00 #8] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4,00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154.24
20 | concrete vaults I | 1.3.2 | 19FS | FS22 | 2007-03-02 08:00 |  | 10d | team subcontractor[4,00 #8] |  | 117409.7188 |  | 0 |  |  |  | 0 | team subcontractor[4,00 #8] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4,00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154.24
22 | steelframe II | 1.3.3 | 20FS | FS24 | 2007-03-16 08:00 |  | 15d | team subcontractor[3,00 #8] |  | 118992.5078 |  | 0 |  |  |  | 0 | team subcontractor[3,00 #8] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3,00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115.68
24 | concrete vaults II | 1.3.4 | 22FS | FS25;FS49 | 2007-04-06 08:00 |  | 15d | team subcontractor[4,00 #8] |  | 117409.7188 |  | 0 |  |  |  | 0 | team subcontractor[4,00 #8] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4,00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154.24
50 | wind and water proof | 1.4
25 | facades | 1.4.1 | 24FS | FS26 | 2007-04-27 08:00 |  | 20d | team subcontractor[2,00 #8] |  | 339314 |  | 0 |  |  |  | 0 | team subcontractor[2,00 #8] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2,00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77.12
26 | outside windows | 1.4.2 | 25FS | FS28;FS29 | 2007-05-25 08:00 |  | 10d | carpenter[3,00 #3] |  | 150750.5938 |  | 0 |  |  |  | 0 | carpenter[3,00 #3] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3,00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 114
49 | roof | 1.4.3 | 24FS |  | 2007-04-27 08:00 |  | 10d | roofer[4,00 #4] |  | 70779.5703 |  | 3224 |  |  |  | 40.3 | roofer[4,00 #4] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4,00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144
62 | warehouse | 1.5
28 | v0 concrete | 1.5.1 | 26FS | FS30;FS27;FS59;FS52;FS45;FS34;FS60;FS51 | 2007-06-08 08:00 |  | 10d | team subcontractor[5,00 #8] |  | 134400 |  | 0 |  |  |  | 0 | team subcontractor[5,00 #8] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5,00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 192.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 192.8
30 | v0 sanitary | 1.5.2 | 31FS;28FS | FS35 | 2007-08-29 10:00 |  | 10d | plumber |  | 4793 |  | 0 |  |  |  | 0 | plumber | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36
27 | v0 masonry | 1.5.3 | 31FS;28FS |  | 2007-08-29 10:00 |  | 10d | mason |  | 31200.9609 |  | 3252 |  |  |  | 40.65 | mason | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40.65
59 | v0 heating | 1.5.4 | 31FS;28FS | FS35 | 2007-08-29 10:00 |  | 20d | heating engineer |  | 11651 |  | 0 |  |  |  | 0 | heating engineer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43.2
29 | v0 electricity | 1.5.5 | 26FS;31FS | FS35 | 2007-08-29 10:00 |  | 25d | electrician |  | 0 |  | 0 |  |  |  | 0 | electrician | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32
35 | v0 floors | 1.5.6 | 59FS;29FS;30FS | FS41;FS37 | 2007-10-03 10:00 |  | 20d | floor layer |  | 75000 |  | 0 |  |  |  | 0 | floor layer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41.56
66 | construction leave | 1.6
31 | construction leave | 1.6.1 |  | FS53;FS55;FS56;FS61;FS54;FS30;FS27;FS59;FS52;FS45;FS34;FS60;FS51;FS29 | 2007-08-15 10:00 |  | 10d |  |  | 0.01 |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
63 | level 1 | 1.7
52 | v1 sanitary | 1.7.1 | 31FS;28FS |  | 2007-08-29 10:00 |  | 10d | plumber |  | 4793 |  | 0 |  |  |  | 0 | plumber | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36
45 | v1 masonry | 1.7.2 | 31FS;28FS |  | 2007-08-29 10:00 |  | 10d | mason |  | 31200.9609 |  | 3252 |  |  |  | 40.65 | mason | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40.65
34 | v1 screed | 1.7.3 | 31FS;28FS | FS67 | 2007-08-29 10:00 |  | 15d | screed layer[2,00 #3] |  | 106140 |  | 0 |  |  |  | 0 | screed layer[2,00 #3] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2,00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
60 | v1 heating | 1.7.4 | 31FS;28FS |  | 2007-08-29 10:00 |  | 20d | heating engineer |  | 11651 |  | 6912 |  |  |  | 43.2 | heating engineer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43.2
51 | v1 electricity | 1.7.5 | 31FS;28FS |  | 2007-08-29 10:00 |  | 25d | electrician |  | 0 |  | 0 |  |  |  | 0 | electrician | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32
67 | v1 drying screed | 1.7.6 | 34FS | FS57;FS32 | 2007-09-19 10:00 |  | 5d |  |  | 0.01 |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
57 | v1 flooring | 1.7.7 | 67FS | FS41;FS37;FS36 | 2007-09-26 10:00 |  | 20d | floor layer |  | 72500 |  | 0 |  |  |  | 0 | floor layer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41.56
64 | level 2 | 1.8
53 | v2 sanitary | 1.8.1 | 31FS |  | 2007-08-29 10:00 |  | 10d | plumber |  | 4793 |  | 0 |  |  |  | 0 | plumber | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36
55 | v2 masonry | 1.8.2 | 31FS |  | 2007-08-29 10:00 |  | 10d | mason |  | 31200.9609 |  | 0 |  |  |  | 0 | mason | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40.65
56 | v2 screed | 1.8.3 | 31FS | FS68;FS36 | 2007-08-29 10:00 |  | 15d | screed layer |  | 46116 |  | 0 |  |  |  | 0 | screed layer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
61 | v2 heating | 1.8.4 | 31FS |  | 2007-08-29 10:00 |  | 20d | electrician |  | 11651 |  | 0 |  |  |  | 0 | electrician | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32
54 | v2 electricity | 1.8.5 | 31FS |  | 2007-08-29 10:00 |  | 25d | electrician |  | 0 |  | 0 |  |  |  | 0 | electrician | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32
68 | v2 drying screed | 1.8.6 | 56FS | FS58;FS32 | 2007-09-19 10:00 |  | 5d |  |  | 0.01 |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
58 | v2 flooring | 1.8.7 | 68FS | FS41;FS37;FS36 | 2007-09-26 10:00 |  | 20d | floor layer |  | 31500 |  | 0 |  |  |  | 0 | floor layer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41.56
65 | completion | 1.9
32 | stucco | 1.9.1 | 68FS;67FS | FS41;FS37 | 2007-09-26 10:00 |  | 15d | plasterer[3,00 #4] |  | 8642 |  | 0 |  |  |  | 0 | plasterer[3,00 #4] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3,00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124.14
36 | drywall | 1.9.2 | 58FS;57FS;56FS |  | 2007-10-24 10:00 |  | 25d |  |  | 48000 |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
41 | kitchen and bar | 1.9.3 | 32FS;58FS;57FS;35FS |  | 2007-10-31 10:00 |  | 15d |  |  | 87000 |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
37 | techniques | 1.9.4 | 32FS;58FS;57FS;35FS | FS38;FS42;FS43;FS44 | 2007-10-31 10:00 |  | 15d |  |  | 2156.0601 |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44 | stairs | 1.9.5 | 37FS |  | 2007-11-21 10:00 |  | 10d |  |  | 33000 |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
42 | entrance doors | 1.9.6 | 37FS |  | 2007-11-21 10:00 |  | 10d |  |  | 16000 |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
43 | elevator | 1.9.7 | 37FS |  | 2007-11-21 10:00 |  | 5d |  |  | 38817.8516 |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38 | suspended ceiling | 1.9.8 | 37FS | FS39 | 2007-11-21 10:00 |  | 5d |  |  | 32000 |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39 | painting | 1.9.9 | 38FS | FS40 | 2007-11-28 10:00 |  | 15d | painter[4,00 #6] |  | 83000 |  | 0 |  |  |  | 0 | painter[4,00 #6] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4,00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140
40 | furniture | 1.9.10 | 39FS |  | 2007-12-19 10:00 |  | 5d | joiner[5,00 #5] |  | 130000 |  | 0 |  |  |  | 0 | joiner[5,00 #5] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5,00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 210 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 210

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availibility | Cost/Use | Cost/Unit | Assigned To | Total Cost
1 | plumber | Renewable | 4,00 #4 | 0 | 36
2 | electrician | Renewable | 4,00 #4 | 0 | 32
3 | team subcontractor | Renewable | 8,00 #8 | 0 | 38.56
4 | mason | Renewable | 4,00 #4 | 0 | 40.65
5 | heating engineer | Renewable | 2,00 #2 | 0 | 43.2
6 | roofer | Renewable | 4,00 #4 | 0 | 36
7 | carpenter | Renewable | 3,00 #3 | 0 | 38
8 | floor layer | Renewable | 4,00 #4 | 0 | 41.56
9 | screed layer | Renewable | 3,00 #3 | 0 | 0
10 | plasterer | Renewable | 4,00 #4 | 0 | 41.38
11 | painter | Renewable | 6,00 #6 | 0 | 35
12 | joiner | Renewable | 5,00 #5 | 0 | 42

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic
0 | PROJECT CLAEYS-VERHELST
46 | preparation
2 | building permit |  | manual - absolute | 402 | 480 | 812
3 | hire contractor |  | manual - absolute | 127 | 160 | 326
4 | temporary offices |  | standard - symmetric | 80 | 100 | 120
5 | temporary facilities |  | standard - symmetric | 80 | 100 | 120
16 | preparation contractor |  | standard - no risk | 99 | 100 | 101
6 | demolition |  | manual - absolute | 219 | 240 | 302
47 | foundation
17 | excavation |  | standard - symmetric | 80 | 100 | 120
69 | soil analyses |  | standard - symmetric | 80 | 100 | 120
18 | foundation beam |  | manual - absolute | 159 | 200 | 363
21 | placing sewerage |  | manual - absolute | 63 | 80 | 98
23 | foundation plate |  | manual - absolute | 6 | 8 | 10
48 | shell
19 | steelframe I |  | manual - absolute | 104 | 120 | 166
20 | concrete vaults I |  | manual - absolute | 32 | 40 | 48
22 | steelframe II |  | manual - absolute | 64 | 80 | 113
24 | concrete vaults II |  | manual - absolute | 66 | 80 | 121
50 | wind and water proof
25 | facades |  | manual - absolute | 128 | 160 | 463
26 | outside windows |  | manual - absolute | 64 | 80 | 175
49 | roof |  | standard - symmetric | 80 | 100 | 120
62 | warehouse
28 | v0 concrete |  | standard - symmetric | 80 | 100 | 120
30 | v0 sanitary |  | standard - no risk | 99 | 100 | 101
27 | v0 masonry |  | standard - no risk | 99 | 100 | 101
59 | v0 heating |  | standard - no risk | 99 | 100 | 101
29 | v0 electricity |  | standard - no risk | 99 | 100 | 101
35 | v0 floors |  | manual - absolute | 128 | 163 | 543
66 | construction leave
31 | construction leave |  | standard - no risk | 99 | 100 | 101
63 | level 1
52 | v1 sanitary |  | standard - no risk | 99 | 100 | 101
45 | v1 masonry |  | standard - no risk | 99 | 100 | 101
34 | v1 screed |  | standard - no risk | 99 | 100 | 101
60 | v1 heating |  | standard - no risk | 99 | 100 | 101
51 | v1 electricity |  | standard - no risk | 99 | 100 | 101
67 | v1 drying screed |  | standard - skewed left | 80 | 110 | 120
57 | v1 flooring |  | manual - absolute | 128 | 160 | 577
64 | level 2
53 | v2 sanitary |  | standard - no risk | 99 | 100 | 101
55 | v2 masonry |  | standard - no risk | 99 | 100 | 101
56 | v2 screed |  | standard - skewed left | 80 | 110 | 120
61 | v2 heating |  | standard - skewed left | 80 | 110 | 120
54 | v2 electricity |  | standard - no risk | 99 | 100 | 101
68 | v2 drying screed |  | standard - skewed left | 80 | 110 | 120
58 | v2 flooring |  | manual - absolute | 128 | 160 | 556
65 | completion
32 | stucco |  | manual - absolute | 96 | 120 | 451
36 | drywall |  | manual - absolute | 160 | 200 | 528
41 | kitchen and bar |  | standard - symmetric | 80 | 100 | 120
37 | techniques |  | standard - symmetric | 80 | 100 | 120
44 | stairs |  | standard - symmetric | 80 | 100 | 120
42 | entrance doors |  | standard - symmetric | 80 | 100 | 120
43 | elevator |  | standard - symmetric | 80 | 100 | 120
38 | suspended ceiling |  | standard - symmetric | 80 | 100 | 120
39 | painting |  | standard - symmetric | 80 | 100 | 120
40 | furniture |  | standard - symmetric | 80 | 100 | 120

## Project Control - TP1
| TP Status Date | 2006-07-07 17:00 |  | TP Name | Preparation1
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Actual Duration [h] | PAC (calc) | PAC Dev (calc)
0 | PROJECT CLAEYS-VERHELST | [14 empty] | Paste values of PAC Dev (calc)
46 | preparation
2 | building permit | [9 empty] | 2006-04-17 08:00 | 60d |  |  |  | 0 |  | 75 |  | 100% |  |  |  | 480 | 75 | 0
3 | hire contractor | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
4 | temporary offices | [9 empty] | 2006-04-17 08:00 | 20d |  |  |  | 0 |  | 3765.3101 |  | 100% |  |  |  | 160 | 3765.3101 | 0
5 | temporary facilities | [9 empty] | 2006-04-17 08:00 | 60d |  |  |  | 0 |  | 1876.54 |  | 100% |  |  |  | 480 | 1876.54 | 0
16 | preparation contractor | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
6 | demolition | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
47 | foundation
17 | excavation | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
69 | soil analyses | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
18 | foundation beam | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
21 | placing sewerage | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
23 | foundation plate | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
48 | shell
19 | steelframe I | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
20 | concrete vaults I | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
22 | steelframe II | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
24 | concrete vaults II | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
50 | wind and water proof
25 | facades | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
26 | outside windows | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
49 | roof | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
62 | warehouse
28 | v0 concrete | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
30 | v0 sanitary | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
27 | v0 masonry | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
59 | v0 heating | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
29 | v0 electricity | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
35 | v0 floors | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
66 | construction leave
31 | construction leave | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
63 | level 1
52 | v1 sanitary | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
45 | v1 masonry | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
34 | v1 screed | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
60 | v1 heating | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
51 | v1 electricity | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
67 | v1 drying screed | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
57 | v1 flooring | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
64 | level 2
53 | v2 sanitary | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
55 | v2 masonry | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
56 | v2 screed | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
61 | v2 heating | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
54 | v2 electricity | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
68 | v2 drying screed | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
58 | v2 flooring | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
65 | completion
32 | stucco | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
36 | drywall | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
41 | kitchen and bar | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
37 | techniques | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
44 | stairs | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
42 | entrance doors | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
43 | elevator | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
38 | suspended ceiling | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
39 | painting | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
40 | furniture | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0

## TP2
| TP Status Date | 2007-02-08 17:00 |  | TP Name | Preparation2
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Actual Duration [h] | PAC (calc) | PAC Dev (calc)
0 | PROJECT CLAEYS-VERHELST | [14 empty] | Paste values of PAC Dev (calc)
46 | preparation
2 | building permit | [9 empty] | 2006-04-17 08:00 | 60d |  |  |  | 0 |  | 75 |  | 100% |  |  |  | 480 | 75 | 0
3 | hire contractor | [9 empty] | 2006-09-04 08:00 | 30d |  |  |  | 0 |  | 210000 |  | 100% |  |  |  | 240 | 210000 | 0
4 | temporary offices | [9 empty] | 2006-04-17 08:00 | 20d |  |  |  | 0 |  | 3765.3101 |  | 100% |  |  |  | 160 | 3765.3101 | 0
5 | temporary facilities | [9 empty] | 2006-04-17 08:00 | 60d |  |  |  | 0 |  | 1876.54 |  | 100% |  |  |  | 480 | 1876.54 | 0
16 | preparation contractor | [9 empty] | 2006-09-04 08:00 | 60d |  |  |  | 0 |  | 0.01 |  | 100% |  |  |  | 480 | 0.01 | 0
6 | demolition | [9 empty] | 2006-11-27 08:00 | 54d |  |  |  | -0.0009 |  | 67701.7891 |  | 100% |  |  |  | 432 | 67701.79 | -0.0009
47 | foundation
17 | excavation | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
69 | soil analyses | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
18 | foundation beam | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
21 | placing sewerage | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
23 | foundation plate | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
48 | shell
19 | steelframe I | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
20 | concrete vaults I | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
22 | steelframe II | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
24 | concrete vaults II | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
50 | wind and water proof
25 | facades | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
26 | outside windows | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
49 | roof | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
62 | warehouse
28 | v0 concrete | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
30 | v0 sanitary | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
27 | v0 masonry | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
59 | v0 heating | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
29 | v0 electricity | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
35 | v0 floors | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
66 | construction leave
31 | construction leave | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
63 | level 1
52 | v1 sanitary | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
45 | v1 masonry | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
34 | v1 screed | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
60 | v1 heating | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
51 | v1 electricity | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
67 | v1 drying screed | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
57 | v1 flooring | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
64 | level 2
53 | v2 sanitary | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
55 | v2 masonry | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
56 | v2 screed | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
61 | v2 heating | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
54 | v2 electricity | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
68 | v2 drying screed | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
58 | v2 flooring | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
65 | completion
32 | stucco | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
36 | drywall | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
41 | kitchen and bar | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
37 | techniques | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
44 | stairs | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
42 | entrance doors | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
43 | elevator | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
38 | suspended ceiling | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
39 | painting | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
40 | furniture | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0

## TP3
| TP Status Date | 2007-03-16 17:00 |  | TP Name | Foundation
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Actual Duration [h] | PAC (calc) | PAC Dev (calc)
0 | PROJECT CLAEYS-VERHELST | [14 empty] | Paste values of PAC Dev (calc)
46 | preparation
2 | building permit | [9 empty] | 2006-04-17 08:00 | 60d |  |  |  | 0 |  | 75 |  | 100% |  |  |  | 480 | 75 | 0
3 | hire contractor | [9 empty] | 2006-09-04 08:00 | 30d |  |  |  | 0 |  | 210000 |  | 100% |  |  |  | 240 | 210000 | 0
4 | temporary offices | [9 empty] | 2006-04-17 08:00 | 20d |  |  |  | 0 |  | 3765.3101 |  | 100% |  |  |  | 160 | 3765.3101 | 0
5 | temporary facilities | [9 empty] | 2006-04-17 08:00 | 60d |  |  |  | 0 |  | 1876.54 |  | 100% |  |  |  | 480 | 1876.54 | 0
16 | preparation contractor | [9 empty] | 2006-09-04 08:00 | 60d |  |  |  | 0 |  | 0.01 |  | 100% |  |  |  | 480 | 0.01 | 0
6 | demolition | [9 empty] | 2006-11-27 08:00 | 54d |  |  |  | -0.0009 |  | 67701.7891 |  | 100% |  |  |  | 432 | 67701.79 | -0.0009
47 | foundation
17 | excavation | [9 empty] | 2007-02-09 08:00 | 10d |  |  |  | 0.0008 |  | 29084.8008 |  | 100% |  |  |  | 80 | 29084.8 | 0.0008
69 | soil analyses | [9 empty] | 2007-02-09 08:00 | 12d |  |  |  | 0.0003 |  | 5701.7603 |  | 100% |  |  |  | 96 | 5701.76 | 0.0003
18 | foundation beam | [9 empty] | 2007-02-28 08:00 | 13d |  |  |  | 0.0034 |  | 110554.45 |  | 65% |  |  |  | 104 | 110554.4466 | 0.0034
21 | placing sewerage | [9 empty] | 2007-02-28 08:00 | 12d |  |  |  | -0.0002 |  | 12330.0098 |  | 100% |  |  |  | 96 | 12330.01 | -0.0002
23 | foundation plate | [9 empty] | 2007-03-16 08:00 | 1d |  |  |  | 0.0063 |  | 236361.8438 |  | 100% |  |  |  | 8 | 236361.8375 | 0.0063
48 | shell
19 | steelframe I | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
20 | concrete vaults I | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
22 | steelframe II | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
24 | concrete vaults II | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
50 | wind and water proof
25 | facades | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
26 | outside windows | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
49 | roof | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
62 | warehouse
28 | v0 concrete | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
30 | v0 sanitary | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
27 | v0 masonry | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
59 | v0 heating | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
29 | v0 electricity | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
35 | v0 floors | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
66 | construction leave
31 | construction leave | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
63 | level 1
52 | v1 sanitary | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
45 | v1 masonry | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
34 | v1 screed | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
60 | v1 heating | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
51 | v1 electricity | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
67 | v1 drying screed | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
57 | v1 flooring | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
64 | level 2
53 | v2 sanitary | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
55 | v2 masonry | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
56 | v2 screed | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
61 | v2 heating | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
54 | v2 electricity | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
68 | v2 drying screed | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
58 | v2 flooring | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
65 | completion
32 | stucco | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
36 | drywall | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
41 | kitchen and bar | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
37 | techniques | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
44 | stairs | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
42 | entrance doors | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
43 | elevator | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
38 | suspended ceiling | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
39 | painting | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
40 | furniture | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0

## TP4
| TP Status Date | 2007-06-01 17:00 |  | TP Name | Shell
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Actual Duration [h] | PAC (calc) | PAC Dev (calc)
0 | PROJECT CLAEYS-VERHELST | [14 empty] | Paste values of PAC Dev (calc)
46 | preparation
2 | building permit | [9 empty] | 2006-04-17 08:00 | 60d |  |  |  | 0 |  | 75 |  | 100% |  |  |  | 480 | 75 | 0
3 | hire contractor | [9 empty] | 2006-09-04 08:00 | 30d |  |  |  | 0 |  | 210000 |  | 100% |  |  |  | 240 | 210000 | 0
4 | temporary offices | [9 empty] | 2006-04-17 08:00 | 20d |  |  |  | 0 |  | 3765.3101 |  | 100% |  |  |  | 160 | 3765.3101 | 0
5 | temporary facilities | [9 empty] | 2006-04-17 08:00 | 60d |  |  |  | 0 |  | 1876.54 |  | 100% |  |  |  | 480 | 1876.54 | 0
16 | preparation contractor | [9 empty] | 2006-09-04 08:00 | 60d |  |  |  | 0 |  | 0.01 |  | 100% |  |  |  | 480 | 0.01 | 0
6 | demolition | [9 empty] | 2006-11-27 08:00 | 54d |  |  |  | -0.0009 |  | 67701.7891 |  | 100% |  |  |  | 432 | 67701.79 | -0.0009
47 | foundation
17 | excavation | [9 empty] | 2007-02-08 08:00 | 10d |  |  |  | 0.0008 |  | 29084.8008 |  | 100% |  |  |  | 80 | 29084.8 | 0.0008
69 | soil analyses | [9 empty] | 2007-02-08 08:00 | 12d |  |  |  | 0.0003 |  | 5701.7603 |  | 100% |  |  |  | 96 | 5701.76 | 0.0003
18 | foundation beam | [9 empty] | 2007-02-28 08:00 | 22d |  |  |  | -0.0004 |  | 118883.4062 |  | 100% |  |  |  | 176 | 118883.4066 | -0.0004
21 | placing sewerage | [9 empty] | 2007-02-28 08:00 | 12d |  |  |  | -0.0002 |  | 12330.0098 |  | 100% |  |  |  | 96 | 12330.01 | -0.0002
23 | foundation plate | [9 empty] | 2007-03-16 08:00 | 1d |  |  |  | 0.0063 |  | 236361.8438 |  | 100% |  |  |  | 8 | 236361.8375 | 0.0063
48 | shell
19 | steelframe I | [9 empty] | 2007-04-02 08:00 | 15d |  |  |  | 0.0047 |  | 137501.3125 |  | 100% |  |  |  | 120 | 137501.3078 | 0.0047
20 | concrete vaults I | [9 empty] | 2007-04-23 08:00 | 5d |  |  |  | 0.0015 |  | 123579.3203 |  | 100% |  |  |  | 40 | 123579.3188 | 0.0015
22 | steelframe II | [9 empty] | 2007-04-30 08:00 | 15d |  |  |  | 0.0016 |  | 132874.1094 |  | 100% |  |  |  | 120 | 132874.1078 | 0.0016
24 | concrete vaults II | [9 empty] | 2007-05-21 08:00 | 10d |  |  |  | 0.0031 |  | 129748.9219 |  | 100% |  |  |  | 80 | 129748.9188 | 0.0031
50 | wind and water proof
25 | facades | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
26 | outside windows | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
49 | roof | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
62 | warehouse
28 | v0 concrete | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
30 | v0 sanitary | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
27 | v0 masonry | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
59 | v0 heating | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
29 | v0 electricity | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
35 | v0 floors | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
66 | construction leave
31 | construction leave | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
63 | level 1
52 | v1 sanitary | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
45 | v1 masonry | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
34 | v1 screed | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
60 | v1 heating | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
51 | v1 electricity | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
67 | v1 drying screed | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
57 | v1 flooring | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
64 | level 2
53 | v2 sanitary | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
55 | v2 masonry | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
56 | v2 screed | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
61 | v2 heating | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
54 | v2 electricity | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
68 | v2 drying screed | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
58 | v2 flooring | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
65 | completion
32 | stucco | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
36 | drywall | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
41 | kitchen and bar | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
37 | techniques | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
44 | stairs | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
42 | entrance doors | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
43 | elevator | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
38 | suspended ceiling | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
39 | painting | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
40 | furniture | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0

## TP5
| TP Status Date | 2007-06-29 17:00 |  | TP Name | Wind & waterproof
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Actual Duration [h] | PAC (calc) | PAC Dev (calc)
0 | PROJECT CLAEYS-VERHELST | [14 empty] | Paste values of PAC Dev (calc)
46 | preparation
2 | building permit | [9 empty] | 2006-04-17 08:00 | 60d |  |  |  | 0 |  | 75 |  | 100% |  |  |  | 480 | 75 | 0
3 | hire contractor | [9 empty] | 2006-09-04 08:00 | 30d |  |  |  | 0 |  | 210000 |  | 100% |  |  |  | 240 | 210000 | 0
4 | temporary offices | [9 empty] | 2006-04-17 08:00 | 20d |  |  |  | 0 |  | 3765.3101 |  | 100% |  |  |  | 160 | 3765.3101 | 0
5 | temporary facilities | [9 empty] | 2006-04-17 08:00 | 60d |  |  |  | 0 |  | 1876.54 |  | 100% |  |  |  | 480 | 1876.54 | 0
16 | preparation contractor | [9 empty] | 2006-09-04 08:00 | 60d |  |  |  | 0 |  | 0.01 |  | 100% |  |  |  | 480 | 0.01 | 0
6 | demolition | [9 empty] | 2006-11-27 08:00 | 54d |  |  |  | -0.0009 |  | 67701.7891 |  | 100% |  |  |  | 432 | 67701.79 | -0.0009
47 | foundation
17 | excavation | [9 empty] | 2007-02-08 08:00 | 10d |  |  |  | 0.0008 |  | 29084.8008 |  | 100% |  |  |  | 80 | 29084.8 | 0.0008
69 | soil analyses | [9 empty] | 2007-02-08 08:00 | 12d |  |  |  | 0.0003 |  | 5701.7603 |  | 100% |  |  |  | 96 | 5701.76 | 0.0003
18 | foundation beam | [9 empty] | 2007-02-28 08:00 | 22d |  |  |  | -0.0004 |  | 118883.4062 |  | 100% |  |  |  | 176 | 118883.4066 | -0.0004
21 | placing sewerage | [9 empty] | 2007-02-28 08:00 | 12d |  |  |  | -0.0002 |  | 12330.0098 |  | 100% |  |  |  | 96 | 12330.01 | -0.0002
23 | foundation plate | [9 empty] | 2007-03-16 08:00 | 1d |  |  |  | 0.0063 |  | 236361.8438 |  | 100% |  |  |  | 8 | 236361.8375 | 0.0063
48 | shell
19 | steelframe I | [9 empty] | 2007-04-02 08:00 | 15d |  |  |  | 0.0047 |  | 137501.3125 |  | 100% |  |  |  | 120 | 137501.3078 | 0.0047
20 | concrete vaults I | [9 empty] | 2007-04-23 08:00 | 5d |  |  |  | 0.0015 |  | 123579.3203 |  | 100% |  |  |  | 40 | 123579.3188 | 0.0015
22 | steelframe II | [9 empty] | 2007-04-30 08:00 | 15d |  |  |  | 0.0016 |  | 132874.1094 |  | 100% |  |  |  | 120 | 132874.1078 | 0.0016
24 | concrete vaults II | [9 empty] | 2007-05-21 08:00 | 10d |  |  |  | 0.0031 |  | 129748.9219 |  | 100% |  |  |  | 80 | 129748.9188 | 0.0031
50 | wind and water proof
25 | facades | [9 empty] | 2007-06-04 08:00 | 20d |  |  |  | -0.0125 |  | 351653.1875 |  | 100% |  |  |  | 160 | 351653.2 | -0.0125
26 | outside windows | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
49 | roof | [9 empty] | 2007-06-04 08:00 | 10d |  |  |  | 0 |  | 85523.5703 |  | 100% |  |  |  | 80 | 85523.5703 | 0
62 | warehouse
28 | v0 concrete | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
30 | v0 sanitary | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
27 | v0 masonry | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
59 | v0 heating | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
29 | v0 electricity | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
35 | v0 floors | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
66 | construction leave
31 | construction leave | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
63 | level 1
52 | v1 sanitary | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
45 | v1 masonry | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
34 | v1 screed | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
60 | v1 heating | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
51 | v1 electricity | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
67 | v1 drying screed | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
57 | v1 flooring | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
64 | level 2
53 | v2 sanitary | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
55 | v2 masonry | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
56 | v2 screed | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
61 | v2 heating | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
54 | v2 electricity | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
68 | v2 drying screed | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
58 | v2 flooring | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
65 | completion
32 | stucco | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
36 | drywall | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
41 | kitchen and bar | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
37 | techniques | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
44 | stairs | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
42 | entrance doors | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
43 | elevator | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
38 | suspended ceiling | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
39 | painting | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
40 | furniture | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0

## TP6
| TP Status Date | 2007-10-24 17:00 |  | TP Name | WH, L1, L2
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Actual Duration [h] | PAC (calc) | PAC Dev (calc)
0 | PROJECT CLAEYS-VERHELST | [14 empty] | Paste values of PAC Dev (calc)
46 | preparation
2 | building permit | [9 empty] | 2006-04-17 08:00 | 60d |  |  |  | 0 |  | 75 |  | 100% |  |  |  | 480 | 75 | 0
3 | hire contractor | [9 empty] | 2006-09-04 08:00 | 30d |  |  |  | 0 |  | 210000 |  | 100% |  |  |  | 240 | 210000 | 0
4 | temporary offices | [9 empty] | 2006-04-17 08:00 | 20d |  |  |  | 0 |  | 3765.3101 |  | 100% |  |  |  | 160 | 3765.3101 | 0
5 | temporary facilities | [9 empty] | 2006-04-17 08:00 | 60d |  |  |  | 0 |  | 1876.54 |  | 100% |  |  |  | 480 | 1876.54 | 0
16 | preparation contractor | [9 empty] | 2006-09-04 08:00 | 60d |  |  |  | 0 |  | 0.01 |  | 100% |  |  |  | 480 | 0.01 | 0
6 | demolition | [9 empty] | 2006-11-27 08:00 | 54d |  |  |  | -0.0009 |  | 67701.7891 |  | 100% |  |  |  | 432 | 67701.79 | -0.0009
47 | foundation
17 | excavation | [9 empty] | 2007-02-08 08:00 | 10d |  |  |  | 0.0008 |  | 29084.8008 |  | 100% |  |  |  | 80 | 29084.8 | 0.0008
69 | soil analyses | [9 empty] | 2007-02-08 08:00 | 12d |  |  |  | 0.0003 |  | 5701.7603 |  | 100% |  |  |  | 96 | 5701.76 | 0.0003
18 | foundation beam | [9 empty] | 2007-02-28 08:00 | 22d |  |  |  | -0.0004 |  | 118883.4062 |  | 100% |  |  |  | 176 | 118883.4066 | -0.0004
21 | placing sewerage | [9 empty] | 2007-02-28 08:00 | 12d |  |  |  | -0.0002 |  | 12330.0098 |  | 100% |  |  |  | 96 | 12330.01 | -0.0002
23 | foundation plate | [9 empty] | 2007-03-16 08:00 | 1d |  |  |  | 0.0063 |  | 236361.8438 |  | 100% |  |  |  | 8 | 236361.8375 | 0.0063
48 | shell
19 | steelframe I | [9 empty] | 2007-04-02 08:00 | 15d |  |  |  | 0.0047 |  | 137501.3125 |  | 100% |  |  |  | 120 | 137501.3078 | 0.0047
20 | concrete vaults I | [9 empty] | 2007-04-23 08:00 | 5d |  |  |  | 0.0015 |  | 123579.3203 |  | 100% |  |  |  | 40 | 123579.3188 | 0.0015
22 | steelframe II | [9 empty] | 2007-04-30 08:00 | 15d |  |  |  | 0.0016 |  | 132874.1094 |  | 100% |  |  |  | 120 | 132874.1078 | 0.0016
24 | concrete vaults II | [9 empty] | 2007-05-21 08:00 | 10d |  |  |  | 0.0031 |  | 129748.9219 |  | 100% |  |  |  | 80 | 129748.9188 | 0.0031
50 | wind and water proof
25 | facades | [9 empty] | 2007-06-04 08:00 | 20d |  |  |  | -0.0125 |  | 351653.1875 |  | 100% |  |  |  | 160 | 351653.2 | -0.0125
26 | outside windows | [9 empty] | 2007-07-02 08:00 | 83d |  |  |  | -0.0038 |  | 226446.59 |  | 90% |  |  |  | 664 | 226446.5938 | -0.0038
49 | roof | [9 empty] | 2007-06-04 08:00 | 10d |  |  |  | 0 |  | 85523.5703 |  | 100% |  |  |  | 80 | 85523.5703 | 0
62 | warehouse
28 | v0 concrete | [9 empty] | 2007-07-25 08:00 | 5d |  |  |  | 0 |  | 142112 |  | 100% |  |  |  | 40 | 142112 | 0
30 | v0 sanitary | [9 empty] | 2007-08-29 08:00 | 10d |  |  |  | 0 |  | 7673 |  | 100% |  |  |  | 80 | 7673 | 0
27 | v0 masonry | [9 empty] | 2007-08-29 08:00 | 10d |  |  |  | 0 |  | 37704.9609 |  | 100% |  |  |  | 80 | 37704.9609 | 0
59 | v0 heating | [9 empty] | 2007-08-29 08:00 | 20d |  |  |  | 0 |  | 18563 |  | 100% |  |  |  | 160 | 18563 | 0
29 | v0 electricity | [9 empty] | 2007-08-02 08:00 | 15d |  |  |  | 0 |  | 3840 |  | 100% |  |  |  | 120 | 3840 | 0
35 | v0 floors | [9 empty] | 2007-09-26 08:00 | 20d |  |  |  | 0.0016 |  | 81649.6016 |  | 100% |  |  |  | 160 | 81649.6 | 0.0016
66 | construction leave
31 | construction leave | [9 empty] | 2007-08-08 08:00 | 10d |  |  |  | 0 |  | 0.01 |  | 100% |  |  |  | 80 | 0.01 | 0
63 | level 1
52 | v1 sanitary | [9 empty] | 2007-08-29 08:00 | 10d |  |  |  | 0 |  | 7673 |  | 100% |  |  |  | 80 | 7673 | 0
45 | v1 masonry | [9 empty] | 2007-08-29 08:00 | 10d |  |  |  | 0 |  | 37704.9609 |  | 100% |  |  |  | 80 | 37704.9609 | 0
34 | v1 screed | [9 empty] | 2007-08-29 08:00 | 15d |  |  |  | 0 |  | 106140 |  | 100% |  |  |  | 120 | 106140 | 0
60 | v1 heating | [9 empty] | 2007-08-29 08:00 | 20d |  |  |  | 0 |  | 25475 |  | 100% |  |  |  | 160 | 25475 | 0
51 | v1 electricity | [9 empty] | 2007-08-29 08:00 | 25d |  |  |  | 0 |  | 6400 |  | 100% |  |  |  | 200 | 6400 | 0
67 | v1 drying screed | [9 empty] | 2007-09-19 08:00 | 5d |  |  |  | 0 |  | 0.01 |  | 100% |  |  |  | 40 | 0.01 | 0
57 | v1 flooring | [9 empty] | 2007-10-03 08:00 | 15d |  |  |  | 0 |  | 77487.2 |  | 80% |  |  |  | 120 | 77487.2 | 0
64 | level 2
53 | v2 sanitary | [9 empty] | 2007-08-29 08:00 | 10d |  |  |  | 0 |  | 7673 |  | 100% |  |  |  | 80 | 7673 | 0
55 | v2 masonry | [9 empty] | 2007-08-29 08:00 | 10d |  |  |  | 0 |  | 34452.9609 |  | 100% |  |  |  | 80 | 34452.9609 | 0
56 | v2 screed | [9 empty] | 2007-08-29 08:00 | 15d |  |  |  | 0 |  | 46116 |  | 100% |  |  |  | 120 | 46116 | 0
61 | v2 heating | [9 empty] | 2007-08-29 08:00 | 20d |  |  |  | 0 |  | 16771 |  | 100% |  |  |  | 160 | 16771 | 0
54 | v2 electricity | [9 empty] | 2007-08-29 08:00 | 20d |  |  |  | 0 |  | 5120 |  | 100% |  |  |  | 160 | 5120 | 0
68 | v2 drying screed | [9 empty] | 2007-09-19 08:00 | 5d |  |  |  | 0 |  | 0.01 |  | 100% |  |  |  | 40 | 0.01 | 0
58 | v2 flooring | [9 empty] | 2007-09-26 08:00 | 20d |  |  |  | 0.0016 |  | 38149.6016 |  | 100% |  |  |  | 160 | 38149.6 | 0.0016
65 | completion
32 | stucco | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
36 | drywall | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
41 | kitchen and bar | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
37 | techniques | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
44 | stairs | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
42 | entrance doors | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
43 | elevator | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
38 | suspended ceiling | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
39 | painting | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0
40 | furniture | [10 empty] | 0 |  |  |  | 0 |  | 0 |  | 0% |  |  |  | 0 | 0 | 0

## TP7
| TP Status Date | 2008-01-09 17:00 |  | TP Name | Completion
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | Actual Duration [h] | PAC (calc) | PAC Dev (calc)
0 | PROJECT CLAEYS-VERHELST | [14 empty] | Paste values of PAC Dev (calc)
46 | preparation
2 | building permit | [9 empty] | 2006-04-17 08:00 | 60d |  |  |  | 0 |  | 75 |  | 100% |  |  |  | 480 | 75 | 0
3 | hire contractor | [9 empty] | 2006-09-04 08:00 | 30d |  |  |  | 0 |  | 210000 |  | 100% |  |  |  | 240 | 210000 | 0
4 | temporary offices | [9 empty] | 2006-04-17 08:00 | 20d |  |  |  | 0 |  | 3765.3101 |  | 100% |  |  |  | 160 | 3765.3101 | 0
5 | temporary facilities | [9 empty] | 2006-04-17 08:00 | 60d |  |  |  | 0 |  | 1876.54 |  | 100% |  |  |  | 480 | 1876.54 | 0
16 | preparation contractor | [9 empty] | 2006-09-04 08:00 | 60d |  |  |  | 0 |  | 0.01 |  | 100% |  |  |  | 480 | 0.01 | 0
6 | demolition | [9 empty] | 2006-11-27 08:00 | 54d |  |  |  | -0.0009 |  | 67701.7891 |  | 100% |  |  |  | 432 | 67701.79 | -0.0009
47 | foundation
17 | excavation | [9 empty] | 2007-02-08 08:00 | 10d |  |  |  | 0.0008 |  | 29084.8008 |  | 100% |  |  |  | 80 | 29084.8 | 0.0008
69 | soil analyses | [9 empty] | 2007-02-08 08:00 | 12d |  |  |  | 0.0003 |  | 5701.7603 |  | 100% |  |  |  | 96 | 5701.76 | 0.0003
18 | foundation beam | [9 empty] | 2007-02-28 08:00 | 22d |  |  |  | -0.0004 |  | 118883.4062 |  | 100% |  |  |  | 176 | 118883.4066 | -0.0004
21 | placing sewerage | [9 empty] | 2007-02-28 08:00 | 12d |  |  |  | -0.0002 |  | 12330.0098 |  | 100% |  |  |  | 96 | 12330.01 | -0.0002
23 | foundation plate | [9 empty] | 2007-03-16 08:00 | 1d |  |  |  | 0.0063 |  | 236361.8438 |  | 100% |  |  |  | 8 | 236361.8375 | 0.0063
48 | shell
19 | steelframe I | [9 empty] | 2007-04-02 08:00 | 15d |  |  |  | 0.0047 |  | 137501.3125 |  | 100% |  |  |  | 120 | 137501.3078 | 0.0047
20 | concrete vaults I | [9 empty] | 2007-04-23 08:00 | 5d |  |  |  | 0.0015 |  | 123579.3203 |  | 100% |  |  |  | 40 | 123579.3188 | 0.0015
22 | steelframe II | [9 empty] | 2007-04-30 08:00 | 15d |  |  |  | 0.0016 |  | 132874.1094 |  | 100% |  |  |  | 120 | 132874.1078 | 0.0016
24 | concrete vaults II | [9 empty] | 2007-05-21 08:00 | 10d |  |  |  | 0.0031 |  | 129748.9219 |  | 100% |  |  |  | 80 | 129748.9188 | 0.0031
50 | wind and water proof
25 | facades | [9 empty] | 2007-06-04 08:00 | 20d |  |  |  | -0.0125 |  | 351653.1875 |  | 100% |  |  |  | 160 | 351653.2 | -0.0125
26 | outside windows | [9 empty] | 2007-07-02 08:00 | 92d |  |  |  | 0 |  | 234654.5938 |  | 100% |  |  |  | 736 | 234654.5938 | 0
49 | roof | [9 empty] | 2007-06-04 08:00 | 10d |  |  |  | 0 |  | 85523.5703 |  | 100% |  |  |  | 80 | 85523.5703 | 0
62 | warehouse
28 | v0 concrete | [9 empty] | 2007-07-25 08:00 | 5d |  |  |  | 0 |  | 142112 |  | 100% |  |  |  | 40 | 142112 | 0
30 | v0 sanitary | [9 empty] | 2007-08-29 08:00 | 10d |  |  |  | 0 |  | 7673 |  | 100% |  |  |  | 80 | 7673 | 0
27 | v0 masonry | [9 empty] | 2007-08-29 08:00 | 10d |  |  |  | 0 |  | 37704.9609 |  | 100% |  |  |  | 80 | 37704.9609 | 0
59 | v0 heating | [9 empty] | 2007-08-29 08:00 | 20d |  |  |  | 0 |  | 18563 |  | 100% |  |  |  | 160 | 18563 | 0
29 | v0 electricity | [9 empty] | 2007-08-02 08:00 | 15d |  |  |  | 0 |  | 3840 |  | 100% |  |  |  | 120 | 3840 | 0
35 | v0 floors | [9 empty] | 2007-09-26 08:00 | 20d |  |  |  | 0.0016 |  | 81649.6016 |  | 100% |  |  |  | 160 | 81649.6 | 0.0016
66 | construction leave
31 | construction leave | [9 empty] | 2007-08-08 08:00 | 10d |  |  |  | 0 |  | 0.01 |  | 100% |  |  |  | 80 | 0.01 | 0
63 | level 1
52 | v1 sanitary | [9 empty] | 2007-08-29 08:00 | 10d |  |  |  | 0 |  | 7673 |  | 100% |  |  |  | 80 | 7673 | 0
45 | v1 masonry | [9 empty] | 2007-08-29 08:00 | 10d |  |  |  | 0 |  | 37704.9609 |  | 100% |  |  |  | 80 | 37704.9609 | 0
34 | v1 screed | [9 empty] | 2007-08-29 08:00 | 15d |  |  |  | 0 |  | 106140 |  | 100% |  |  |  | 120 | 106140 | 0
60 | v1 heating | [9 empty] | 2007-08-29 08:00 | 20d |  |  |  | 0 |  | 25475 |  | 100% |  |  |  | 160 | 25475 | 0
51 | v1 electricity | [9 empty] | 2007-08-29 08:00 | 25d |  |  |  | 0 |  | 6400 |  | 100% |  |  |  | 200 | 6400 | 0
67 | v1 drying screed | [9 empty] | 2007-09-19 08:00 | 5d |  |  |  | 0 |  | 0.01 |  | 100% |  |  |  | 40 | 0.01 | 0
57 | v1 flooring | [9 empty] | 2007-10-03 08:00 | 20d |  |  |  | 0.0016 |  | 79149.6016 |  | 100% |  |  |  | 160 | 79149.6 | 0.0016
64 | level 2
53 | v2 sanitary | [9 empty] | 2007-08-29 08:00 | 10d |  |  |  | 0 |  | 7673 |  | 100% |  |  |  | 80 | 7673 | 0
55 | v2 masonry | [9 empty] | 2007-08-29 08:00 | 10d |  |  |  | 0 |  | 34452.9609 |  | 100% |  |  |  | 80 | 34452.9609 | 0
56 | v2 screed | [9 empty] | 2007-08-29 08:00 | 15d |  |  |  | 0 |  | 46116 |  | 100% |  |  |  | 120 | 46116 | 0
61 | v2 heating | [9 empty] | 2007-08-29 08:00 | 20d |  |  |  | 0 |  | 16771 |  | 100% |  |  |  | 160 | 16771 | 0
54 | v2 electricity | [9 empty] | 2007-08-29 08:00 | 20d |  |  |  | 0 |  | 5120 |  | 100% |  |  |  | 160 | 5120 | 0
68 | v2 drying screed | [9 empty] | 2007-09-19 08:00 | 5d |  |  |  | 0 |  | 0.01 |  | 100% |  |  |  | 40 | 0.01 | 0
58 | v2 flooring | [9 empty] | 2007-09-26 08:00 | 20d |  |  |  | 0.0016 |  | 38149.6016 |  | 100% |  |  |  | 160 | 38149.6 | 0.0016
65 | completion
32 | stucco | [9 empty] | 2007-11-05 08:00 | 15d |  |  |  | 0.0008 |  | 23538.8008 |  | 100% |  |  |  | 120 | 23538.8 | 0.0008
36 | drywall | [9 empty] | 2007-11-05 08:00 | 25d |  |  |  | 0 |  | 48000 |  | 100% |  |  |  | 200 | 48000 | 0
41 | kitchen and bar | [9 empty] | 2007-11-26 08:00 | 20d |  |  |  | 0 |  | 87000 |  | 100% |  |  |  | 160 | 87000 | 0
37 | techniques | [9 empty] | 2007-11-26 08:00 | 15d |  |  |  | 0 |  | 2156.0601 |  | 100% |  |  |  | 120 | 2156.0601 | 0
44 | stairs | [9 empty] | 2007-12-10 08:00 | 10d |  |  |  | 0 |  | 33000 |  | 100% |  |  |  | 80 | 33000 | 0
42 | entrance doors | [9 empty] | 2007-12-10 08:00 | 10d |  |  |  | 0 |  | 16000 |  | 100% |  |  |  | 80 | 16000 | 0
43 | elevator | [9 empty] | 2007-12-10 08:00 | 5d |  |  |  | 0 |  | 38817.8516 |  | 100% |  |  |  | 40 | 38817.8516 | 0
38 | suspended ceiling | [9 empty] | 2007-12-10 08:00 | 5d |  |  |  | 0 |  | 32000 |  | 100% |  |  |  | 40 | 32000 | 0
39 | painting | [9 empty] | 2007-12-17 08:00 | 15d |  |  |  | 0 |  | 99800 |  | 100% |  |  |  | 120 | 99800 | 0
40 | furniture | [9 empty] | 2008-01-03 08:00 | 5d |  |  |  | 0 |  | 138400 |  | 100% |  |  |  | 40 | 138400 | 0

## Agenda
Working Hours |  | Working Days |  | Holidays
0:00 - 1:00 | No | Monday | Yes | 2015-06-18
1:00 - 2:00 | No | Tuesday | Yes | 2015-06-19
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No