## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in days)
0 | Veterinary Exposition | 1 |  |  | 2010-11-17 08:00 | 2012-01-30 17:00 | 439d 9h |  | 0 | 54350 | 0 | 0 | 54350 | 439.375
1 | Planning phase | 1.1 |  |  | 2010-11-17 08:00 | 2011-05-11 17:00 | 175d 9h |  | 0 | 3000 | 0 | 0 | 3000 | 175.375
2 | Start-up meeting | 1.1.1 |  | FS13+0;FS14+0 | 2010-11-17 08:00 | 2010-11-17 17:00 | 1d | Previous Exposition Commission | 0 | 0 | 0 | 0 | 0 | 0.375
3 | Appointing a new Main Officer | 1.1.2 |  | FS4+0;FS20+0 | 2011-02-25 08:00 | 2011-02-25 17:00 | 1d | Core Staff | 0 | 0 | 0 | 0 | 0 | 0.375
4 | Composition of a new Exposition Commission | 1.1.3 | 3FS+0 | FS5+0;FS6+0;FS7+0;FS8+0;FS9+0 | 2011-02-28 08:00 | 2011-03-18 17:00 | 15d | Previous Exposition CommissionMain Officer | 0 | 0 | 0 | 0 | 0 | 18.375
5 | Meeting with Partner | 1.1.4 | 4FS+0 | FS10+0 | 2011-04-12 08:00 | 2011-04-12 17:00 | 1d | Conference Supervisor | 0 | 0 | 0 | 0 | 0 | 0.375
6 | Meeting with Exhibition Company | 1.1.5 | 4FS+0 | FS10+0;FS22+0 | 2011-04-14 08:00 | 2011-04-14 17:00 | 1d | Exhibition CompanyMain Officer | 0 | 0 | 0 | 0 | 0 | 0.375
7 | Meeting with the Layout Man | 1.1.6 | 4FS+0 | FS10+0 | 2011-04-19 08:00 | 2011-04-19 17:00 | 1d | Main OfficerCatering Supervisor | 0 | 3000 | 0 | 0 | 3000 | 0.375
8 | Meeting with the Event Caterer | 1.1.7 | 4FS+0 | FS10+0 | 2011-04-21 08:00 | 2011-04-21 17:00 | 1d | Catering Supervisor | 0 | 0 | 0 | 0 | 0 | 0.375
9 | Meeting with the Webmaster | 1.1.8 | 4FS+0 | FS10+0 | 2011-04-25 08:00 | 2011-04-25 17:00 | 1d | Finance Manager | 0 | 0 | 0 | 0 | 0 | 0.375
10 | Meeting with the Exposition Commission: division of tasks | 1.1.9 | 6FS+0;8FS+0;9FS+0;5FS+0;7FS+0 | FS11+0 | 2011-05-11 08:00 | 2011-05-11 17:00 | 1d | Main OfficerBar SupervisorPublic RelationsCatering SupervisorCatalogue SupervisorFinance ManagerConference Supervisor | 0 | 0 | 0 | 0 | 0 | 0.375
11 | Planning phase complete | 1.1.10 | 10FS+0 | FS23+0;FS28+0;FS29+0;FS30+0;FS31+0;FS32+0;FS38+0;FS46+0;FS47+0;FS54+0;FS56+0;FS61+0 | 2011-05-11 17:00 | 2011-05-11 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
12 | Registration brochure phase | 1.2 |  |  | 2010-12-06 08:00 | 2011-02-24 17:00 | 80d 9h |  | 0 | 0 | 0 | 0 | 0 | 80.375
13 | Finding a translator among staff | 1.2.1 | 2FS+0 | FS15+0 | 2010-12-06 08:00 | 2010-12-17 17:00 | 10d | Previous Exposition Commission | 0 | 0 | 0 | 0 | 0 | 11.375
14 | Preparing the registration brochure | 1.2.2 | 2FS+0 | FS15+0 | 2010-12-27 08:00 | 2010-12-31 17:00 | 5d | Previous Exposition Commission | 0 | 0 | 0 | 0 | 0 | 4.375
15 | Translating the registration brochure | 1.2.3 | 14FS+0;13FS+0 | FS16+0 | 2011-01-03 08:00 | 2011-01-06 17:00 | 4d | Translator | 0 | 0 | 0 | 0 | 0 | 3.375
16 | Layouting of the registration brochure | 1.2.4 | 15FS+0 | FS17+0 | 2011-02-03 08:00 | 2011-02-23 17:00 | 15d | Layouter | 0 | 0 | 0 | 0 | 0 | 20.375
17 | Mailing of the registration brochure | 1.2.5 | 16FS+0 | FS18+0 | 2011-02-24 08:00 | 2011-02-24 17:00 | 1d | Previous Exposition Commission | 0 | 0 | 0 | 0 | 0 | 0.375
18 | Registration brochure phase complete | 1.2.6 | 17FS+0 | FS20+0 | 2011-02-24 17:00 | 2011-02-24 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
19 | Contracting companies phase | 1.3 |  |  | 2011-02-28 08:00 | 2011-10-26 17:00 | 240d 9h |  | 0 | 750 | 0 | 0 | 750 | 240.375
20 | Contracting known companies | 1.3.1 | 3FS+0;18FS+0 | FS21+0;FS27+0 | 2011-02-28 08:00 | 2011-07-15 17:00 | 100d | Main Officer | 0 | 200 | 0 | 0 | 200 | 137.375
21 | Contracting new companies | 1.3.2 | 20FS+0 | FS25+0;FS49+0 | 2011-07-18 08:00 | 2011-10-07 17:00 | 60d | Main Officer | 0 | 300 | 0 | 0 | 300 | 81.375
22 | Sending the toolbox and invoicing | 1.3.3 | 6FS+0 | FS25+0 | 2011-04-26 08:00 | 2011-10-26 17:00 | 132d | Exhibition Company | 0 | 0 | 0 | 0 | 0 | 183.375
23 | Mailing sponsorship letters | 1.3.4 | 11FS+0 | FS24+0 | 2011-05-12 08:00 | 2011-05-13 17:00 | 2d | Public Relations | 0 | 150 | 0 | 0 | 150 | 1.375
24 | Active search for sponsors | 1.3.5 | 23FS+0 | FS25+0 | 2011-05-17 08:00 | 2011-10-25 17:00 | 116d | Public Relations | 0 | 100 | 0 | 0 | 100 | 161.375
25 | Contracting companies phase complete | 1.3.6 | 24FS+0;21FS+0;22FS+0 | FS68+0 | 2011-10-26 17:00 | 2011-10-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
26 | Exhibition catalogue phase | 1.4 |  |  | 2011-07-04 08:00 | 2011-10-26 17:00 | 114d 9h |  | 0 | 9150 | 0 | 0 | 9150 | 114.375
27 | Making a draft of the floor plan | 1.4.1 | 20FS+0 | FS33+0 | 2011-08-05 08:00 | 2011-08-05 17:00 | 1d | Finance Manager | 0 | 0 | 0 | 0 | 0 | 0.375
28 | Taking a picture of the Commission | 1.4.2 | 11FS+0 | FS33+0 | 2011-08-09 08:00 | 2011-08-09 17:00 | 1d | Main OfficerCatalogue Supervisor | 0 | 50 | 0 | 0 | 50 | 0.375
29 | Decision concerning the new layout | 1.4.3 | 11FS+0 | FS33+0 | 2011-07-18 08:00 | 2011-08-05 17:00 | 15d | Main Officer | 0 | 0 | 0 | 0 | 0 | 18.375
30 | Organisation of evening activities | 1.4.4 | 11FS+0 | FS33+0;FS60+0;FS63+0 | 2011-07-04 08:00 | 2011-08-10 17:00 | 28d | Main Officer | 0 | 0 | 0 | 0 | 0 | 37.375
31 | Organisation of the introductory day and retraining courses | 1.4.5 | 11FS+0 | FS33+0;FS63+0 | 2011-07-04 08:00 | 2011-08-10 17:00 | 28d | Conference Supervisor | 0 | 0 | 0 | 0 | 0 | 37.375
32 | Collecting articles and advertentions | 1.4.6 | 11FS+0 | FS33+0 | 2011-07-04 08:00 | 2011-08-17 17:00 | 33d | Catalogue Supervisor | 0 | 0 | 0 | 0 | 0 | 44.375
33 | Compiling the exhibition catalogue | 1.4.7 | 30FS+0;31FS+0;32FS+0;29FS+0;27FS+0;28FS+0 | FS34+0;SS43+0;SS44+0;SS50+0 | 2011-08-18 08:00 | 2011-08-24 17:00 | 5d | Main OfficerCatalogue Supervisor | 0 | 0 | 0 | 0 | 0 | 6.375
34 | Translating the exhibition catalogue | 1.4.8 | 33FS+0 | FS35+0;SS36+0 | 2011-08-25 08:00 | 2011-09-16 17:00 | 17d | Translator | 0 | 0 | 0 | 0 | 0 | 22.375
35 | Layouting of the French exhibition catalogue | 1.4.9 | 34FS+0 | FS40+0 | 2011-09-19 08:00 | 2011-09-30 17:00 | 10d | Layouter | 0 | 0 | 0 | 0 | 0 | 11.375
36 | Layouting of the Dutch exhibition catalogue, publicity and entrance tickets | 1.4.10 | 34SS+0 | FS37+0 | 2011-08-25 08:00 | 2011-09-07 17:00 | 10d | Layouter | 0 | 0 | 0 | 0 | 0 | 13.375
37 | Printing the Dutch exhibition catalogue and entrance tickets | 1.4.11 | 36FS+0 | FS39+0 | 2011-09-08 08:00 | 2011-09-19 17:00 | 8d | Printing Company | 0 | 5000 | 0 | 0 | 5000 | 11.375
38 | Gathering addresses and emails of vets | 1.4.12 | 11FS+0 | FS39+0;FS40+0 | 2011-07-04 08:00 | 2011-09-19 17:00 | 56d | Main OfficerCatalogue Supervisor | 0 | 0 | 0 | 0 | 0 | 77.375
39 | Mailing of the Dutch exhibition catalogue by email and postal service | 1.4.13 | 38FS+0;37FS+0 | FS41+160 | 2011-09-28 08:00 | 2011-09-28 17:00 | 1d | Printing CompanyCatalogue Supervisor | 0 | 4100 | 0 | 0 | 4100 | 0.375
40 | Mailing of the French exhibition catalogue by email | 1.4.14 | 35FS+0;38FS+0 | FS41+120 | 2011-10-03 08:00 | 2011-10-03 17:00 | 1d | Catalogue Supervisor | 0 | 0 | 0 | 0 | 0 | 0.375
41 | Exhibition catalogue phase complete | 1.4.15 | 40FS+120;39FS+160 | FS68+0 | 2011-10-26 17:00 | 2011-10-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
42 | Preparation phase | 1.5 |  |  | 2011-05-12 08:00 | 2011-10-26 17:00 | 167d 9h |  | 0 | 11200 | 0 | 0 | 11200 | 167.375
43 | Making a new website | 1.5.1 | 33SS+0 | FS66+0 | 2011-08-18 08:00 | 2011-08-31 17:00 | 10d | WebmasterTranslatorFinance Manager | 0 | 200 | 0 | 0 | 200 | 13.375
44 | Making the press release | 1.5.2 | 33SS+0 | FS45+0 | 2011-09-12 08:00 | 2011-09-23 17:00 | 10d | Main Officer | 0 | 0 | 0 | 0 | 0 | 11.375
45 | Mailing the press release | 1.5.3 | 44FS+0 | FS66+0 | 2011-09-26 08:00 | 2011-10-24 17:00 | 21d | Main Officer | 0 | 0 | 0 | 0 | 0 | 28.375
46 | Meeting with the wine merchant and wholesale business of beer | 1.5.4 | 11FS+0 | FS48+0 | 2011-09-12 08:00 | 2011-09-23 17:00 | 10d | Bar Supervisor | 0 | 0 | 0 | 0 | 0 | 11.375
47 | Compiling the menu | 1.5.5 | 11FS+0 | FS48+0 | 2011-09-12 08:00 | 2011-09-16 17:00 | 5d | Catering Supervisor | 0 | 0 | 0 | 0 | 0 | 4.375
48 | Determining prices of food and beverages | 1.5.6 | 46FS+0;47FS+0 | FS50+0;FS66+0 | 2011-10-10 08:00 | 2011-10-10 17:00 | 1d | Finance Manager | 0 | 0 | 0 | 0 | 0 | 0.375
49 | Making the final floor plan | 1.5.7 | 21FS+0 | FS50+0 | 2011-10-10 08:00 | 2011-10-10 17:00 | 1d | Finance Manager | 0 | 0 | 0 | 0 | 0 | 0.375
50 | Drafting badges, leaflet, food and drink vouchers | 1.5.8 | 49FS+0;48FS+0;33SS+0 | FS51+0 | 2011-10-11 08:00 | 2011-10-11 17:00 | 1d | Main Officer | 0 | 0 | 0 | 0 | 0 | 0.375
51 | Layouting of badges, leaflet, food and drink vouchers | 1.5.9 | 50FS+0 | FS52+0;FS66+0 | 2011-10-12 08:00 | 2011-10-18 17:00 | 5d | Layouter | 0 | 0 | 0 | 0 | 0 | 6.375
52 | Printing (and glueing) badges, leaflet, food and drink vouchers | 1.5.10 | 51FS+0 | FS53+0 | 2011-10-19 08:00 | 2011-10-25 17:00 | 5d | Printing Company | 0 | 500 | 0 | 0 | 500 | 6.375
53 | Assembling the exhibitors folder | 1.5.11 | 52FS+0 | FS66+0 | 2011-10-26 08:00 | 2011-10-26 17:00 | 1d | Main OfficerCatering SupervisorBar SupervisorConference SupervisorCatalogue SupervisorPublic RelationsFinance Manager | 0 | 0 | 0 | 0 | 0 | 0.375
54 | Sampling the polo shirts | 1.5.12 | 11FS+0 | FS55+72 | 2011-09-12 08:00 | 2011-09-12 17:00 | 1d | Public Relations | 0 | 0 | 0 | 0 | 0 | 0.375
55 | Placing an order for the polo shirts | 1.5.13 | 54FS+72 | FS66+120 | 2011-09-26 08:00 | 2011-09-26 17:00 | 1d | Public Relations | 0 | 3500 | 0 | 0 | 3500 | 0.375
56 | Composing a questionnaire for the collaborators | 1.5.14 | 11FS+0 | FS57+0 | 2011-09-19 08:00 | 2011-09-19 17:00 | 1d | Public Relations | 0 | 0 | 0 | 0 | 0 | 0.375
57 | Attracting collaborators | 1.5.15 | 56FS+0 | FS58+0 | 2011-09-26 08:00 | 2011-10-14 17:00 | 15d | Public Relations | 0 | 0 | 0 | 0 | 0 | 18.375
58 | Assigning the collaborators | 1.5.16 | 57FS+0 | FS59+0 | 2011-10-17 08:00 | 2011-10-21 17:00 | 5d | Public Relations | 0 | 0 | 0 | 0 | 0 | 4.375
59 | Mailing the collaborators | 1.5.17 | 58FS+0 | FS66+0 | 2011-10-24 08:00 | 2011-10-25 17:00 | 2d | Public Relations | 0 | 0 | 0 | 0 | 0 | 1.375
60 | Placing several orders | 1.5.18 | 30FS+0 | FS62+0;FS66+0 | 2011-08-11 08:00 | 2011-09-21 17:00 | 30d | Main OfficerCatalogue SupervisorBar Supervisor | 0 | 3000 | 0 | 0 | 3000 | 41.375
61 | Request for sponsored cars | 1.5.19 | 11FS+0 | FS62+0 | 2011-05-12 08:00 | 2011-05-18 17:00 | 5d | Main Officer | 0 | 0 | 0 | 0 | 0 | 6.375
62 | Final purchases | 1.5.20 | 61FS+0;60FS+0 | FS66+0 | 2011-10-10 08:00 | 2011-10-25 17:00 | 12d | Main OfficerBar SupervisorCatering Supervisor | 0 | 4000 | 0 | 0 | 4000 | 15.375
63 | Mailing of newsletter 1 | 1.5.21 | 30FS+0;31FS+0 | SS64+0;FS65+0 | 2011-09-26 08:00 | 2011-09-26 17:00 | 1d | TranslatorMain Officer | 0 | 0 | 0 | 0 | 0 | 0.375
64 | Final meeting with Exhibition Company | 1.5.22 | 63SS+0 | FS65+0 | 2011-10-11 08:00 | 2011-10-11 17:00 | 1d | Exhibition CompanyMain Officer | 0 | 0 | 0 | 0 | 0 | 0.375
65 | Mailing of newsletter 2 | 1.5.23 | 64FS+0;63FS+0 | FS66+0 | 2011-10-17 08:00 | 2011-10-17 17:00 | 1d | TranslatorMain Officer | 0 | 0 | 0 | 0 | 0 | 0.375
66 | Preparations phase complete | 1.5.24 | 53FS+0;62FS+0;59FS+0;65FS+0;51FS+0;60FS+0;55FS+120;43FS+0;45FS+0;48FS+0 | FS68+0 | 2011-10-26 17:00 | 2011-10-26 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
67 | Trade fair phase | 1.6 |  |  | 2011-10-27 08:00 | 2011-11-04 17:00 | 8d 9h |  | 0 | 250 | 0 | 0 | 250 | 8.375
68 | Exposition build up | 1.6.1 | 25FS+0;66FS+0;41FS+0 | FS69+0 | 2011-10-27 08:00 | 2011-10-27 17:00 | 1d | Bar SupervisorCatalogue SupervisorConference SupervisorCatering SupervisorMain OfficerFinance ManagerPublic RelationsExhibition CompanyCore StaffTreasurer | 0 | 100 | 0 | 0 | 100 | 0.375
69 | Exposition | 1.6.2 | 68FS+0 | FS70+0 | 2011-10-28 08:00 | 2011-10-28 17:00 | 1d | Bar SupervisorCatalogue SupervisorConference SupervisorCatering SupervisorMain OfficerFinance ManagerPublic RelationsExhibition CompanyCore StaffTreasurer | 0 | 0 | 0 | 0 | 0 | 0.375
70 | Breaking down of Exposition | 1.6.3 | 69FS+0 | FS71+32 | 2011-10-31 08:00 | 2011-10-31 17:00 | 1d | Bar SupervisorCatalogue SupervisorConference SupervisorCatering SupervisorMain OfficerFinance ManagerPublic RelationsCore StaffTreasurer | 0 | 150 | 0 | 0 | 150 | 0.375
71 | Trade fair phase complete | 1.6.4 | 70FS+32 | FS72+0;FS73+0;FS74+0;FS76+0 | 2011-11-04 17:00 | 2011-11-04 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0
83 | Follow-up phase | 1.7 |  |  | 2011-11-07 08:00 | 2012-01-30 17:00 | 84d 9h |  | 0 | 30000 | 0 | 0 | 30000 | 84.375
72 | Payments to suppliers | 1.7.1 | 71FS+0 | FS82+80 | 2011-11-07 08:00 | 2011-11-11 17:00 | 5d | Treasurer | 0 | 30000 | 0 | 0 | 30000 | 4.375
73 | Updating the website | 1.7.2 | 71FS+0 | FS82+0 | 2011-11-07 08:00 | 2011-11-11 17:00 | 5d | Finance Manager | 0 | 0 | 0 | 0 | 0 | 4.375
74 | Handing out a questionnaire to all companies and vets | 1.7.3 | 71FS+0 | FS75+0 | 2011-11-07 08:00 | 2011-11-18 17:00 | 10d | Finance Manager | 0 | 0 | 0 | 0 | 0 | 11.375
75 | Evaluation meeting | 1.7.4 | 74FS+0;77FS+0 | FS82+0 | 2011-11-23 08:00 | 2011-11-23 17:00 | 1d | Bar SupervisorCatalogue SupervisorConference SupervisorCatering SupervisorMain OfficerFinance ManagerPublic Relations | 0 | 0 | 0 | 0 | 0 | 0.375
76 | Counting food and drinkvouchers | 1.7.5 | 71FS+0 | FS77+0 | 2011-11-07 08:00 | 2011-11-08 17:00 | 2d | Bar SupervisorCatalogue SupervisorConference SupervisorCatering SupervisorMain OfficerFinance ManagerPublic RelationsCore StaffTreasurer | 0 | 0 | 0 | 0 | 0 | 1.375
77 | Constructing the income and expenditure report | 1.7.6 | 76FS+0 | FS75+0;FS78+0;FS79+0 | 2011-11-09 08:00 | 2011-11-11 17:00 | 3d | Main OfficerFinance ManagerTreasurer | 0 | 0 | 0 | 0 | 0 | 2.375
78 | Final invoice is sent to all companies | 1.7.7 | 77FS+0 | FS82+400 | 2011-11-14 08:00 | 2011-11-18 17:00 | 5d | Treasurer | 0 | 0 | 0 | 0 | 0 | 4.375
79 | Financial meeting with Exhibition Company | 1.7.8 | 77FS+0 | FS84+0 | 2011-11-14 08:00 | 2011-11-24 17:00 | 9d | Main OfficerFinance Manager | 0 | 0 | 0 | 0 | 0 | 10.375
84 | Invoice from Exposition to Exhibition Company | 1.7.9 | 79FS+0 | FS82+360 | 2011-11-25 08:00 | 2011-11-25 17:00 | 1d | Finance Manager | 0 | 0 | 0 | 0 | 0 | 0.375
82 | Follow-up phase complete | 1.7.10 | 78FS+400;84FS+360;72FS+80;73FS+0;75FS+0 |  | 2012-01-30 17:00 | 2012-01-30 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost
1 | Previous Exposition Commission | Renewable | 1 #1 | 0 | 0 | 2;4;13;14;17; | 0
2 | Core Staff | Renewable | 1 #1 | 0 | 0 | 3;68;69;70;76; | 0
3 | Main Officer | Renewable | 1 #1 | 0 | 0 | 4;6;7;10;20;21;28;29;30;33;38;44;45;50;53;60;61;62;63;64;65;68;69;70;75;76;77;79; | 0
4 | Conference Supervisor | Renewable | 1 #1 | 0 | 0 | 5;10;31;53;68;69;70;75;76; | 0
5 | Catalogue Supervisor | Renewable | 1 #1 | 0 | 0 | 10;28;32;33;38;39;40;53;60;68;69;70;75;76; | 0
6 | Catering Supervisor | Renewable | 1 #1 | 0 | 0 | 7;8;10;47;53;62;68;69;70;75;76; | 0
7 | Finance Manager | Renewable | 1 #1 | 0 | 0 | 9;10;27;43;48;49;53;68;69;70;73;74;75;76;77;79;84; | 0
8 | Translator | Renewable | 1 #1 | 0 | 0 | 15;34;43;63;65; | 0
9 | Layouter | Renewable | 1 #1 | 0 | 0 | 16;35;36;51; | 0
10 | Exhibition Company | Renewable | 1 #1 | 0 | 0 | 6;22;64;68;69; | 0
11 | Public Relations | Renewable | 1 #1 | 0 | 0 | 10;23;24;53;54;55;56;57;58;59;68;69;70;75;76; | 0
12 | Treasurer | Renewable | 1 #1 | 0 | 0 | 68;69;70;72;76;77;78; | 0
13 | Webmaster | Renewable | 1 #1 | 0 | 0 | 43; | 0
14 | Printing Company | Renewable | 1 #1 | 0 | 0 | 37;39;52; | 0
15 | Bar Supervisor | Renewable | 1 #1 | 0 | 0 | 10;46;53;60;62;68;69;70;75;76; | 0

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic | Most probable | Pessimistic
0 | Veterinary Exposition | 439d 9h | manual - absolute | 0 | 0 | 0 | 0 | 0 | 0
1 | Planning phase | 175d 9h | manual - absolute | 0 | 0 | 0 | 0 | 0 | 0
2 | Start-up meeting | 1d | standard - no risk | 99 | 100 | 101 | 7 | 8 | 8
3 | Appointing a new Main Officer | 1d | manual - absolute | 6 | 7 | 10 | 6 | 7 | 10
4 | Composition of a new Exposition Commission | 15d | standard - symmetric | 80 | 100 | 120 | 96 | 120 | 144
5 | Meeting with Partner | 1d | standard - skewed right | 80 | 90 | 120 | 6 | 7 | 9
6 | Meeting with Exhibition Company | 1d | standard - skewed right | 80 | 90 | 120 | 6 | 7 | 9
7 | Meeting with the Layout Man | 1d | standard - skewed right | 80 | 90 | 120 | 6 | 7 | 9
8 | Meeting with the Event Caterer | 1d | standard - skewed right | 80 | 90 | 120 | 6 | 7 | 9
9 | Meeting with the Webmaster | 1d | standard - skewed right | 80 | 90 | 120 | 6 | 7 | 9
10 | Meeting with the Exposition Commission: division of tasks | 1d | standard - no risk | 99 | 100 | 101 | 7 | 8 | 8
11 | Planning phase complete | 0 | standard - symmetric | 80 | 100 | 120 | 0 | 0 | 0
12 | Registration brochure phase | 80d 9h | manual - absolute | 0 | 0 | 0 | 0 | 0 | 0
13 | Finding a translator among staff | 10d | standard - symmetric | 80 | 100 | 120 | 64 | 80 | 96
14 | Preparing the registration brochure | 5d | standard - symmetric | 80 | 100 | 120 | 32 | 40 | 48
15 | Translating the registration brochure | 4d | standard - symmetric | 80 | 100 | 120 | 25 | 32 | 38
16 | Layouting of the registration brochure | 15d | standard - skewed right | 80 | 90 | 120 | 96 | 108 | 144
17 | Mailing of the registration brochure | 1d | standard - no risk | 99 | 100 | 101 | 7 | 8 | 8
18 | Registration brochure phase complete | 0 | standard - symmetric | 80 | 100 | 120 | 0 | 0 | 0
19 | Contracting companies phase | 240d 9h | manual - absolute | 0 | 0 | 0 | 0 | 0 | 0
20 | Contracting known companies | 100d | standard - skewed right | 80 | 90 | 120 | 640 | 720 | 960
21 | Contracting new companies | 60d | standard - skewed right | 80 | 90 | 120 | 384 | 432 | 576
22 | Sending the toolbox and invoicing | 132d | standard - no risk | 99 | 100 | 101 | 1045 | 1056 | 1066
23 | Mailing sponsorship letters | 2d | standard - no risk | 99 | 100 | 101 | 15 | 16 | 16
24 | Active search for sponsors | 116d | standard - no risk | 99 | 100 | 101 | 918 | 928 | 937
25 | Contracting companies phase complete | 0 | standard - symmetric | 80 | 100 | 120 | 0 | 0 | 0
26 | Exhibition catalogue phase | 114d 9h | manual - absolute | 0 | 0 | 0 | 0 | 0 | 0
27 | Making a draft of the floor plan | 1d | standard - no risk | 99 | 100 | 101 | 7 | 8 | 8
28 | Taking a picture of the Commission | 1d | standard - symmetric | 80 | 100 | 120 | 6 | 8 | 9
29 | Decision concerning the new layout | 15d | standard - symmetric | 80 | 100 | 120 | 96 | 120 | 144
30 | Organisation of evening activities | 28d | standard - symmetric | 80 | 100 | 120 | 179 | 224 | 268
31 | Organisation of the introductory day and retraining courses | 28d | standard - symmetric | 80 | 100 | 120 | 179 | 224 | 268
32 | Collecting articles and advertentions | 33d | standard - skewed right | 80 | 90 | 120 | 211 | 237 | 316
33 | Compiling the exhibition catalogue | 5d | standard - symmetric | 80 | 100 | 120 | 32 | 40 | 48
34 | Translating the exhibition catalogue | 17d | standard - skewed right | 80 | 90 | 120 | 108 | 122 | 163
35 | Layouting of the French exhibition catalogue | 10d | standard - skewed right | 80 | 90 | 120 | 64 | 72 | 96
36 | Layouting of the Dutch exhibition catalogue, publicity and entrance tickets | 10d | standard - skewed right | 80 | 90 | 120 | 64 | 72 | 96
37 | Printing the Dutch exhibition catalogue and entrance tickets | 8d | standard - symmetric | 80 | 100 | 120 | 51 | 64 | 76
38 | Gathering addresses and emails of vets | 56d | standard - symmetric | 80 | 100 | 120 | 358 | 448 | 537
39 | Mailing of the Dutch exhibition catalogue by email and postal service | 1d | standard - no risk | 99 | 100 | 101 | 7 | 8 | 8
40 | Mailing of the French exhibition catalogue by email | 1d | standard - no risk | 99 | 100 | 101 | 7 | 8 | 8
41 | Exhibition catalogue phase complete | 0 | standard - symmetric | 80 | 100 | 120 | 0 | 0 | 0
42 | Preparation phase | 167d 9h | manual - absolute | 0 | 0 | 0 | 0 | 0 | 0
43 | Making a new website | 10d | standard - symmetric | 80 | 100 | 120 | 64 | 80 | 96
44 | Making the press release | 10d | standard - no risk | 99 | 100 | 101 | 79 | 80 | 80
45 | Mailing the press release | 21d | standard - no risk | 99 | 100 | 101 | 166 | 168 | 169
46 | Meeting with the wine merchant and wholesale business of beer | 10d | standard - symmetric | 80 | 100 | 120 | 64 | 80 | 96
47 | Compiling the menu | 5d | standard - no risk | 99 | 100 | 101 | 39 | 40 | 40
48 | Determining prices of food and beverages | 1d | standard - no risk | 99 | 100 | 101 | 7 | 8 | 8
49 | Making the final floor plan | 1d | standard - no risk | 99 | 100 | 101 | 7 | 8 | 8
50 | Drafting badges, leaflet, food and drink vouchers | 1d | standard - symmetric | 80 | 100 | 120 | 6 | 8 | 9
51 | Layouting of badges, leaflet, food and drink vouchers | 5d | standard - skewed right | 80 | 90 | 120 | 32 | 36 | 48
52 | Printing (and glueing) badges, leaflet, food and drink vouchers | 5d | standard - symmetric | 80 | 100 | 120 | 32 | 40 | 48
53 | Assembling the exhibitors folder | 1d | standard - no risk | 99 | 100 | 101 | 7 | 8 | 8
54 | Sampling the polo shirts | 1d | standard - no risk | 99 | 100 | 101 | 7 | 8 | 8
55 | Placing an order for the polo shirts | 1d | standard - no risk | 99 | 100 | 101 | 7 | 8 | 8
56 | Composing a questionnaire for the collaborators | 1d | standard - no risk | 99 | 100 | 101 | 7 | 8 | 8
57 | Attracting collaborators | 15d | standard - skewed right | 80 | 90 | 120 | 96 | 108 | 144
58 | Assigning the collaborators | 5d | standard - symmetric | 80 | 100 | 120 | 32 | 40 | 48
59 | Mailing the collaborators | 2d | standard - no risk | 99 | 100 | 101 | 15 | 16 | 16
60 | Placing several orders | 30d | standard - symmetric | 80 | 100 | 120 | 192 | 240 | 288
61 | Request for sponsored cars | 5d | standard - skewed right | 80 | 90 | 120 | 32 | 36 | 48
62 | Final purchases | 12d | standard - symmetric | 80 | 100 | 120 | 76 | 96 | 115
63 | Mailing of newsletter 1 | 1d | standard - no risk | 99 | 100 | 101 | 7 | 8 | 8
64 | Final meeting with Exhibition Company | 1d | standard - symmetric | 80 | 100 | 120 | 6 | 8 | 9
65 | Mailing of newsletter 2 | 1d | standard - no risk | 99 | 100 | 101 | 7 | 8 | 8
66 | Preparations phase complete | 0 | standard - symmetric | 80 | 100 | 120 | 0 | 0 | 0
67 | Trade fair phase | 8d 9h | manual - absolute | 0 | 0 | 0 | 0 | 0 | 0
68 | Exposition build up | 1d | standard - no risk | 99 | 100 | 101 | 7 | 8 | 8
69 | Exposition | 1d | standard - no risk | 99 | 100 | 101 | 7 | 8 | 8
70 | Breaking down of Exposition | 1d | standard - no risk | 99 | 100 | 101 | 7 | 8 | 8
71 | Trade fair phase complete | 0 | standard - symmetric | 80 | 100 | 120 | 0 | 0 | 0
83 | Follow-up phase | 84d 9h | manual - absolute | 0 | 0 | 0 | 0 | 0 | 0
72 | Payments to suppliers | 5d | standard - symmetric | 80 | 100 | 120 | 32 | 40 | 48
73 | Updating the website | 5d | standard - symmetric | 80 | 100 | 120 | 32 | 40 | 48
74 | Handing out a questionnaire to all companies and vets | 10d | standard - symmetric | 80 | 100 | 120 | 64 | 80 | 96
75 | Evaluation meeting | 1d | standard - no risk | 99 | 100 | 101 | 7 | 8 | 8
76 | Counting food and drinkvouchers | 2d | standard - no risk | 99 | 100 | 101 | 15 | 16 | 16
77 | Constructing the income and expenditure report | 3d | standard - symmetric | 80 | 100 | 120 | 19 | 24 | 28
78 | Final invoice is sent to all companies | 5d | standard - symmetric | 80 | 100 | 120 | 32 | 40 | 48
79 | Financial meeting with Exhibition Company | 9d | standard - skewed right | 80 | 90 | 120 | 57 | 64 | 86
84 | Invoice from Exposition to Exhibition Company | 1d | standard - no risk | 99 | 100 | 101 | 7 | 8 | 8
82 | Follow-up phase complete | 0 | standard - symmetric | 80 | 100 | 120 | 0 | 0 | 0

## Agenda
Working Hours |  | Working Days |  | Holidays
0:00 - 1:00 | No | Monday | Yes | 80920110000
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI | CPI | SPI(t) | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold