## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost
0 | PROJECT CLAEYS-VERHELST | 1 |  |  | 2006-04-17 08:00 | 2007-12-26 10:00 | 442d 2h |  | 0 | 2700210.5 | 0 | 0 | 3027133.25
46 | preparation | 1.1 |  |  | 2006-04-17 08:00 | 2006-12-08 17:00 | 170d |  | 0 | 216786.9844 | 0 | 0 | 253804.5938
2 | building permit | 1.1.1 |  | FS3 | 2006-04-17 08:00 | 2006-07-07 17:00 | 60d |  | 0 | 75 | 0 | 0 | 75
3 | hire contractor | 1.1.2 | FS2 | FS16 | 2006-07-10 08:00 | 2006-08-04 17:00 | 20d |  | 0 | 210000 | 0 | 0 | 210000
4 | temporary offices | 1.1.3 |  |  | 2006-04-17 08:00 | 2006-05-12 17:00 | 20d |  | 0 | 3765.3101 | 0 | 0 | 3765.3101
5 | temporary facilities | 1.1.4 |  |  | 2006-04-17 08:00 | 2006-07-07 17:00 | 60d |  | 0 | 1876.54 | 0 | 0 | 1876.54
16 | preparation contractor | 1.1.5 | FS3 | FS6 | 2006-08-07 08:00 | 2006-10-27 17:00 | 60d |  | 0 | 0.01 | 0 | 0 | 0.01
6 | demolition | 1.1.6 | FS16 | FS17;FS69 | 2006-10-30 08:00 | 2006-12-08 17:00 | 30d | team subcontractor [4.0 #8] | 37017.6016 | 1070.11 | 0 | 0 | 38087.7109
47 | foundation | 1.2 |  |  | 2006-12-11 08:00 | 2007-02-01 17:00 | 39d |  | 0 | 362567.875 | 0 | 0 | 401436.375
17 | excavation | 1.2.1 | FS6 | FS18;FS21 | 2006-12-11 08:00 | 2006-12-28 17:00 | 14d | team subcontractor | 4318.7207 | 26000 | 0 | 0 | 30318.7207
69 | soil analyses | 1.2.2 | FS6 | FS18 | 2006-12-11 08:00 | 2006-12-12 17:00 | 2d | team subcontractor | 616.96 | 2000 | 0 | 0 | 2616.96
18 | foundation beam | 1.2.3 | 17FS;FS69 | FS19 | 2006-12-29 08:00 | 2007-02-01 17:00 | 25d | team subcontractor [3.0 #8] | 23136 | 98523.7266 | 0 | 0 | 121659.7266
21 | placing sewerage | 1.2.4 | FS17 | FS23 | 2006-12-29 08:00 | 2007-01-11 17:00 | 10d | team subcontractor [3.0 #8] | 9254.4004 | 1224.73 | 0 | 0 | 10479.1309
23 | foundation plate | 1.2.5 | FS21 | FS19 | 2007-01-12 08:00 | 2007-01-12 17:00 | 1d | team subcontractor [5.0 #8] | 1542.4062 | 234819.4375 | 0 | 0 | 236361.8438
48 | shell | 1.3 |  |  | 2007-02-02 08:00 | 2007-04-26 17:00 | 60d |  | 0 | 472804.4375 | 0 | 0 | 542212.4375
19 | steelframe I | 1.3.1 | 18FS;FS23 | FS20 | 2007-02-02 08:00 | 2007-03-01 17:00 | 20d | team subcontractor [4.0 #8] | 24678.3984 | 118992.5078 | 0 | 0 | 143670.9062
20 | concrete vaults I | 1.3.2 | FS19 | FS22 | 2007-03-02 08:00 | 2007-03-15 17:00 | 10d | team subcontractor [4.0 #8] | 12339.2031 | 117409.7188 | 0 | 0 | 129748.9219
22 | steelframe II | 1.3.3 | FS20 | FS24 | 2007-03-16 08:00 | 2007-04-05 17:00 | 15d | team subcontractor [3.0 #8] | 13881.6016 | 118992.5078 | 0 | 0 | 132874.1094
24 | concrete vaults II | 1.3.4 | FS22 | FS25;FS49 | 2007-04-06 08:00 | 2007-04-26 17:00 | 15d | team subcontractor [4.0 #8] | 18508.7969 | 117409.7188 | 0 | 0 | 135918.5156
50 | wind and water proof | 1.4 |  |  | 2007-04-27 08:00 | 2007-06-07 17:00 | 30d |  | 0 | 560844.1875 | 0 | 0 | 597047.375
25 | facades | 1.4.1 | FS24 | FS26 | 2007-04-27 08:00 | 2007-05-24 17:00 | 20d | team subcontractor [2.0 #8] | 12339.1875 | 339314 | 0 | 0 | 351653.1875
26 | outside windows | 1.4.2 | FS25 | FS28;FS29 | 2007-05-25 08:00 | 2007-06-07 17:00 | 10d | carpenter [3.0 #3] | 9120 | 150750.5938 | 0 | 0 | 159870.5938
49 | roof | 1.4.3 | FS24 |  | 2007-04-27 08:00 | 2007-05-10 17:00 | 10d | roofer [4.0 #4] | 11520 | 70779.5703 | 40.3 | 3224 | 85523.5703
62 | warehouse | 1.5 |  |  | 2007-06-08 08:00 | 2007-10-31 10:00 | 103d 2h |  | 0 | 257044.9688 | 0 | 0 | 301814.5625
28 | v0 concrete | 1.5.1 | FS26 | FS30;FS27;FS59;FS52;FS45;FS34;FS60;FS51 | 2007-06-08 08:00 | 2007-06-21 17:00 | 10d | team subcontractor [5.0 #8] | 15424 | 134400 | 0 | 0 | 149824
30 | v0 sanitary | 1.5.2 | 31FS;FS28 | FS35 | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673
27 | v0 masonry | 1.5.3 | 31FS;FS28 |  | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 40.65 | 3252 | 37704.9609
59 | v0 heating | 1.5.4 | 31FS;FS28 | FS35 | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | heating engineer | 6912 | 11651 | 0 | 0 | 18563
29 | v0 electricity | 1.5.5 | 26FS;FS31 | FS35 | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400
35 | v0 floors | 1.5.6 | 59FS;29FS;FS30 | FS41;FS37 | 2007-10-03 10:00 | 2007-10-31 10:00 | 20d | floor layer | 6649.6016 | 75000 | 0 | 0 | 81649.6016
66 | construction leave | 1.6 |  |  | 2007-08-15 10:00 | 2007-08-29 10:00 | 10d |  | 0 | 0.01 | 0 | 0 | 0.01
31 | construction leave | 1.6.1 |  | FS53;FS55;FS56;FS61;FS54;FS30;FS27;FS59;FS52;FS45;FS34;FS60;FS51;FS29 | 2007-08-15 10:00 | 2007-08-29 10:00 | 10d |  | 0 | 0.01 | 0 | 0 | 0.01
63 | level 1 | 1.7 |  |  | 2007-08-29 10:00 | 2007-10-24 10:00 | 40d |  | 0 | 226284.9844 | 0 | 0 | 262542.5938
52 | v1 sanitary | 1.7.1 | 31FS;FS28 |  | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673
45 | v1 masonry | 1.7.2 | 31FS;FS28 |  | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 40.65 | 3252 | 37704.9609
34 | v1 screed | 1.7.3 | 31FS;FS28 | FS67 | 2007-08-29 10:00 | 2007-09-19 10:00 | 15d | screed layer [2.0 #3] | 0 | 106140 | 0 | 0 | 106140
60 | v1 heating | 1.7.4 | 31FS;FS28 |  | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | heating engineer | 6912 | 11651 | 43.2 | 6912 | 25475
51 | v1 electricity | 1.7.5 | 31FS;FS28 |  | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400
67 | v1 drying screed | 1.7.6 | FS34 | FS57;FS32 | 2007-09-19 10:00 | 2007-09-26 10:00 | 5d |  | 0 | 0.01 | 0 | 0 | 0.01
57 | v1 flooring | 1.7.7 | FS67 | FS41;FS37;FS36 | 2007-09-26 10:00 | 2007-10-24 10:00 | 20d | floor layer | 6649.6016 | 72500 | 0 | 0 | 79149.6016
64 | level 2 | 1.8 |  |  | 2007-08-29 10:00 | 2007-10-24 10:00 | 40d |  | 0 | 125260.9688 | 0 | 0 | 149562.5625
53 | v2 sanitary | 1.8.1 | FS31 |  | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | plumber | 2880 | 4793 | 0 | 0 | 7673
55 | v2 masonry | 1.8.2 | FS31 |  | 2007-08-29 10:00 | 2007-09-12 10:00 | 10d | mason | 3252 | 31200.9609 | 0 | 0 | 34452.9609
56 | v2 screed | 1.8.3 | FS31 | FS68;FS36 | 2007-08-29 10:00 | 2007-09-19 10:00 | 15d | screed layer | 0 | 46116 | 0 | 0 | 46116
61 | v2 heating | 1.8.4 | FS31 |  | 2007-08-29 10:00 | 2007-09-26 10:00 | 20d | electrician | 5120 | 11651 | 0 | 0 | 16771
54 | v2 electricity | 1.8.5 | FS31 |  | 2007-08-29 10:00 | 2007-10-03 10:00 | 25d | electrician | 6400 | 0 | 0 | 0 | 6400
68 | v2 drying screed | 1.8.6 | FS56 | FS58;FS32 | 2007-09-19 10:00 | 2007-09-26 10:00 | 5d |  | 0 | 0.01 | 0 | 0 | 0.01
58 | v2 flooring | 1.8.7 | FS68 | FS41;FS37;FS36 | 2007-09-26 10:00 | 2007-10-24 10:00 | 20d | floor layer | 6649.6016 | 31500 | 0 | 0 | 38149.6016
65 | completion | 1.9 |  |  | 2007-09-26 10:00 | 2007-12-26 10:00 | 65d |  | 0 | 478615.9062 | 0 | 0 | 518712.7188
32 | stucco | 1.9.1 | 68FS;FS67 | FS41;FS37 | 2007-09-26 10:00 | 2007-10-17 10:00 | 15d | plasterer [3.0 #4] | 14896.8008 | 8642 | 0 | 0 | 23538.8008
36 | drywall | 1.9.2 | 58FS;57FS;FS56 |  | 2007-10-24 10:00 | 2007-11-28 10:00 | 25d |  | 0 | 48000 | 0 | 0 | 48000
41 | kitchen and bar | 1.9.3 | 32FS;58FS;57FS;FS35 |  | 2007-10-31 10:00 | 2007-11-21 10:00 | 15d |  | 0 | 87000 | 0 | 0 | 87000
37 | techniques | 1.9.4 | 32FS;58FS;57FS;FS35 | FS38;FS42;FS43;FS44 | 2007-10-31 10:00 | 2007-11-21 10:00 | 15d |  | 0 | 2156.0601 | 0 | 0 | 2156.0601
44 | stairs | 1.9.5 | FS37 |  | 2007-11-21 10:00 | 2007-12-05 10:00 | 10d |  | 0 | 33000 | 0 | 0 | 33000
42 | entrance doors | 1.9.6 | FS37 |  | 2007-11-21 10:00 | 2007-12-05 10:00 | 10d |  | 0 | 16000 | 0 | 0 | 16000
43 | elevator | 1.9.7 | FS37 |  | 2007-11-21 10:00 | 2007-11-28 10:00 | 5d |  | 0 | 38817.8516 | 0 | 0 | 38817.8516
38 | suspended ceiling | 1.9.8 | FS37 | FS39 | 2007-11-21 10:00 | 2007-11-28 10:00 | 5d |  | 0 | 32000 | 0 | 0 | 32000
39 | painting | 1.9.9 | FS38 | FS40 | 2007-11-28 10:00 | 2007-12-19 10:00 | 15d | painter [4.0 #6] | 16800 | 83000 | 0 | 0 | 99800
40 | furniture | 1.9.10 | FS39 |  | 2007-12-19 10:00 | 2007-12-26 10:00 | 5d | joiner [5.0 #5] | 8400 | 130000 | 0 | 0 | 138400

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost
11 | painter | Renewable | 6 #6 | 0 | 35 | 39[4 #6]; | 16800
12 | joiner | Renewable | 5 #5 | 0 | 42 | 40[5 #5]; | 8400
6 | roofer | Renewable | 4 #4 | 0 | 36 | 49[4 #4]; | 11520
5 | heating engineer | Renewable | 2 #2 | 0 | 43.2 | 59;60; | 13824
10 | plasterer | Renewable | 4 #4 | 0 | 41.38 | 32[3 #4]; | 14896.8
4 | mason | Renewable | 4 #4 | 0 | 40.65 | 27;45;55; | 9756
9 | screed layer | Renewable | 3 #3 | 0 | 0 | 34[2 #3];56; | 0
1 | plumber | Renewable | 4 #4 | 0 | 36 | 30;52;53; | 8640
3 | team subcontractor | Renewable | 8 #8 | 0 | 38.56 | 6[4 #8];17;69;18[3 #8];21[3 #8];23[5 #8];19[4 #8];20[4 #8];22[3 #8];24[4 #8];25[2 #8];28[5 #8]; | 173057.28
7 | carpenter | Renewable | 3 #3 | 0 | 38 | 26[3 #3]; | 9120
8 | floor layer | Renewable | 4 #4 | 0 | 41.56 | 35;57;58; | 19948.8
2 | electrician | Renewable | 4 #4 | 0 | 32 | 29;51;61;54; | 24320

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic
0 | PROJECT CLAEYS-VERHELST | 442d 2h
46 | preparation | 170d
2 | building permit | 60d | manual - absolute | 402 | 480 | 812
3 | hire contractor | 20d | manual - absolute | 127 | 160 | 326
4 | temporary offices | 20d | standard - symmetric | 80 | 100 | 120
5 | temporary facilities | 60d | standard - symmetric | 80 | 100 | 120
16 | preparation contractor | 60d | standard - no risk | 99 | 100 | 101
6 | demolition | 30d | manual - absolute | 219 | 240 | 302
47 | foundation | 39d
17 | excavation | 14d | standard - symmetric | 80 | 100 | 120
69 | soil analyses | 2d | standard - symmetric | 80 | 100 | 120
18 | foundation beam | 25d | manual - absolute | 159 | 200 | 363
21 | placing sewerage | 10d | manual - absolute | 63 | 80 | 98
23 | foundation plate | 1d | manual - absolute | 6 | 8 | 10
48 | shell | 60d
19 | steelframe I | 20d | manual - absolute | 104 | 120 | 166
20 | concrete vaults I | 10d | manual - absolute | 32 | 40 | 48
22 | steelframe II | 15d | manual - absolute | 64 | 80 | 113
24 | concrete vaults II | 15d | manual - absolute | 66 | 80 | 121
50 | wind and water proof | 30d
25 | facades | 20d | manual - absolute | 128 | 160 | 463
26 | outside windows | 10d | manual - absolute | 64 | 80 | 175
49 | roof | 10d | standard - symmetric | 80 | 100 | 120
62 | warehouse | 103d 2h
28 | v0 concrete | 10d | standard - symmetric | 80 | 100 | 120
30 | v0 sanitary | 10d | standard - no risk | 99 | 100 | 101
27 | v0 masonry | 10d | standard - no risk | 99 | 100 | 101
59 | v0 heating | 20d | standard - no risk | 99 | 100 | 101
29 | v0 electricity | 25d | standard - no risk | 99 | 100 | 101
35 | v0 floors | 20d | manual - absolute | 128 | 163 | 543
66 | construction leave | 10d
31 | construction leave | 10d | standard - no risk | 99 | 100 | 101
63 | level 1 | 40d
52 | v1 sanitary | 10d | standard - no risk | 99 | 100 | 101
45 | v1 masonry | 10d | standard - no risk | 99 | 100 | 101
34 | v1 screed | 15d | standard - no risk | 99 | 100 | 101
60 | v1 heating | 20d | standard - no risk | 99 | 100 | 101
51 | v1 electricity | 25d | standard - no risk | 99 | 100 | 101
67 | v1 drying screed | 5d | standard - skewed left | 80 | 110 | 120
57 | v1 flooring | 20d | manual - absolute | 128 | 160 | 577
64 | level 2 | 40d
53 | v2 sanitary | 10d | standard - no risk | 99 | 100 | 101
55 | v2 masonry | 10d | standard - no risk | 99 | 100 | 101
56 | v2 screed | 15d | standard - skewed left | 80 | 110 | 120
61 | v2 heating | 20d | standard - skewed left | 80 | 110 | 120
54 | v2 electricity | 25d | standard - no risk | 99 | 100 | 101
68 | v2 drying screed | 5d | standard - skewed left | 80 | 110 | 120
58 | v2 flooring | 20d | manual - absolute | 128 | 160 | 556
65 | completion | 65d
32 | stucco | 15d | manual - absolute | 96 | 120 | 451
36 | drywall | 25d | manual - absolute | 160 | 200 | 528
41 | kitchen and bar | 15d | standard - symmetric | 80 | 100 | 120
37 | techniques | 15d | standard - symmetric | 80 | 100 | 120
44 | stairs | 10d | standard - symmetric | 80 | 100 | 120
42 | entrance doors | 10d | standard - symmetric | 80 | 100 | 120
43 | elevator | 5d | standard - symmetric | 80 | 100 | 120
38 | suspended ceiling | 5d | standard - symmetric | 80 | 100 | 120
39 | painting | 15d | standard - symmetric | 80 | 100 | 120
40 | furniture | 5d | standard - symmetric | 80 | 100 | 120