## Baseline Schedule
General |  | Relations |  | Baseline |  |  | Resource Demand | Baseline Costs
ID | Name | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Fixed Cost | Cost/Hour | Variable Cost
0 | Claeys-Verhelst Premises |  |  | 2006-04-17 08:00 | 2007-12-25 17:00 | 617d 9h |  | 2700210.3057 | 0 | 0
46 | preparation |  |  | 2006-04-17 08:00 | 2006-12-08 17:00 | 235d 9h |  | 216786.9701 | 0 | 0
2 | building permit |  | FS3+0 | 2006-04-17 08:00 | 2006-07-07 17:00 | 60d |  | 75 | 0 | 0
3 | hire contractor | 2FS+0 | FS16+0 | 2006-07-10 08:00 | 2006-08-04 17:00 | 20d |  | 210000 | 0 | 0
4 | temporary offices |  |  | 2006-04-17 08:00 | 2006-05-12 17:00 | 20d |  | 3765.3101 | 0 | 0
5 | temporary facilities |  |  | 2006-04-17 08:00 | 2006-07-07 17:00 | 60d |  | 1876.54 | 0 | 0
16 | preparation contractor | 3FS+0 | FS6+0 | 2006-08-07 08:00 | 2006-10-27 17:00 | 60d |  | 0.01 | 0 | 0
6 | demolition | 16FS+0 | FS17+0;FS69+0 | 2006-10-30 08:00 | 2006-12-08 17:00 | 30d | team VDW[4.0 #8] | 1070.11 | 0 | 0
47 | foundation |  |  | 2006-12-11 08:00 | 2007-02-01 17:00 | 52d 9h |  | 362567.894 | 0 | 0
17 | excavation | 6FS+0 | FS18+0;FS21+0 | 2006-12-11 08:00 | 2006-12-28 17:00 | 14d | team VDW | 26000 | 0 | 0
69 | soil analyses | 6FS+0 | FS18+0 | 2006-12-11 08:00 | 2006-12-12 17:00 | 2d | team VDW | 2000 | 0 | 0
18 | foundation beam | 17FS+0;69FS+0 | FS19+0 | 2006-12-29 08:00 | 2007-02-01 17:00 | 25d | team VDW[3.0 #8] | 98523.7266 | 0 | 0
21 | placing sewerage | 17FS+0 | FS23+0 | 2006-12-29 08:00 | 2007-01-11 17:00 | 10d | team VDW[3.0 #8] | 1224.73 | 0 | 0
23 | foundation plate | 21FS+0 | FS19+0 | 2007-01-12 08:00 | 2007-01-12 17:00 | 1d | team VDW[5.0 #8] | 234819.4375 | 0 | 0
48 | shell |  |  | 2007-02-02 08:00 | 2007-04-26 17:00 | 83d 9h |  | 472804.4531 | 0 | 0
19 | steelframe I | 18FS+0;23FS+0 | FS20+0 | 2007-02-02 08:00 | 2007-03-01 17:00 | 20d | team VDW[4.0 #8] | 118992.5078 | 0 | 0
20 | concrete vaults I | 19FS+0 | FS22+0 | 2007-03-02 08:00 | 2007-03-15 17:00 | 10d | team VDW[4.0 #8] | 117409.7188 | 0 | 0
22 | steelframe II | 20FS+0 | FS24+0 | 2007-03-16 08:00 | 2007-04-05 17:00 | 15d | team VDW[3.0 #8] | 118992.5078 | 0 | 0
24 | concrete volt II | 22FS+0 | FS25+0;FS49+0 | 2007-04-06 08:00 | 2007-04-26 17:00 | 15d | team VDW[4.0 #8] | 117409.7188 | 0 | 0
50 | wind and water proof |  |  | 2007-04-27 08:00 | 2007-06-07 17:00 | 41d 9h |  | 560844.1641 | 0 | 0
25 | facades | 24FS+0 | FS26+0 | 2007-04-27 08:00 | 2007-05-24 17:00 | 20d | team VDW[2.0 #8] | 339314 | 0 | 0
26 | outside windows | 25FS+0 | FS28+0;FS29+0 | 2007-05-25 08:00 | 2007-06-07 17:00 | 10d | windows[3.0 #3] | 150750.5938 | 0 | 0
49 | roof | 24FS+0 |  | 2007-04-27 08:00 | 2007-05-10 17:00 | 10d | roofing[4.0 #4] | 70779.5703 | 40.3 | 3223.9999
62 | warehouse |  |  | 2007-06-08 08:00 | 2007-10-30 17:00 | 144d 9h |  | 257044.9609 | 0 | 0
28 | v0 polierbeton | 26FS+0 | FS30+0;FS27+0;FS59+0;FS52+0;FS45+0;FS34+0;FS60+0;FS51+0 | 2007-06-08 08:00 | 2007-06-21 17:00 | 10d | team VDW[5.0 #8] | 134400 | 0 | 0
30 | v0 sanitary | 31FS+0;28FS+0 | FS35+0 | 2007-08-29 10:00 | 2007-09-11 17:00 | 10d | plumber | 4793 | 0 | 0
27 | v0 -masonry | 31FS+0;28FS+0 |  | 2007-08-29 10:00 | 2007-09-11 17:00 | 10d | mason | 31200.9609 | 40.65 | 3252.0001
59 | v0 heating | 31FS+0;28FS+0 | FS35+0 | 2007-08-29 10:00 | 2007-09-25 17:00 | 20d | heating | 11651 | 0 | 0
29 | v0 electricity | 26FS+0;31FS+0 | FS35+0 | 2007-08-29 10:00 | 2007-10-02 17:00 | 25d | electrician | 0 | 0 | 0
35 | v0 floors | 59FS+0;29FS+0;30FS+0 | FS41+0;FS37+0 | 2007-10-03 10:00 | 2007-10-30 17:00 | 20d | flooring | 75000 | 0 | 0
66 | construction leave |  |  | 2007-08-15 10:00 | 2007-08-28 17:00 | 13d 7h |  | 0.01 | 0 | 0
31 | construction leave |  | FS53+0;FS55+0;FS56+0;FS61+0;FS54+0;FS30+0;FS27+0;FS59+0;FS52+0;FS45+0;FS34+0;FS60+0;FS51+0;FS29+0 | 2007-08-15 10:00 | 2007-08-28 17:00 | 10d |  | 0.01 | 0 | 0
63 | level 1 |  |  | 2007-08-29 10:00 | 2007-10-23 17:00 | 55d 7h |  | 226284.9709 | 0 | 0
52 | vI sanitary | 31FS+0;28FS+0 |  | 2007-08-29 10:00 | 2007-09-11 17:00 | 10d | plumber | 4793 | 0 | 0
45 | vI masonry | 31FS+0;28FS+0 |  | 2007-08-29 10:00 | 2007-09-11 17:00 | 10d | mason | 31200.9609 | 40.65 | 3252.0001
34 | v1screed | 31FS+0;28FS+0 | FS67+0 | 2007-08-29 10:00 | 2007-09-18 17:00 | 15d | chapen[2.0 #3] | 106140 | 0 | 0
60 | v1 heating | 31FS+0;28FS+0 |  | 2007-08-29 10:00 | 2007-09-25 17:00 | 20d | heating | 11651 | 43.2 | 6912.0001
51 | vI electricity | 31FS+0;28FS+0 |  | 2007-08-29 10:00 | 2007-10-02 17:00 | 25d | electrician | 0 | 0 | 0
67 | v1 drying screed | 34FS+0 | FS57+0;FS32+0 | 2007-09-19 10:00 | 2007-09-25 17:00 | 5d |  | 0.01 | 0 | 0
57 | v1flooring | 67FS+0 | FS41+0;FS37+0;FS36+0 | 2007-09-26 10:00 | 2007-10-23 17:00 | 20d | flooring | 72500 | 0 | 0
64 | level 2 |  |  | 2007-08-29 10:00 | 2007-10-23 17:00 | 55d 7h |  | 125260.9709 | 0 | 0
53 | v2 sanitary | 31FS+0 |  | 2007-08-29 10:00 | 2007-09-11 17:00 | 10d | plumber | 4793 | 0 | 0
55 | v2 masonry | 31FS+0 |  | 2007-08-29 10:00 | 2007-09-11 17:00 | 10d | mason | 31200.9609 | 0 | 0
56 | v2 screed | 31FS+0 | FS68+0;FS36+0 | 2007-08-29 10:00 | 2007-09-18 17:00 | 15d | chapen | 46116 | 0 | 0
61 | v2 heating | 31FS+0 |  | 2007-08-29 10:00 | 2007-09-25 17:00 | 20d | electrician | 11651 | 0 | 0
54 | v2 electricity | 31FS+0 |  | 2007-08-29 10:00 | 2007-10-02 17:00 | 25d | electrician | 0 | 0 | 0
68 | v2 drying screed | 56FS+0 | FS58+0;FS32+0 | 2007-09-19 10:00 | 2007-09-25 17:00 | 5d |  | 0.01 | 0 | 0
58 | v2 flooring | 68FS+0 | FS41+0;FS37+0;FS36+0 | 2007-09-26 10:00 | 2007-10-23 17:00 | 20d | flooring | 31500 | 0 | 0
65 | completion |  |  | 2007-09-26 10:00 | 2007-12-25 17:00 | 90d 7h |  | 478615.9116 | 0 | 0
32 | stucco | 68FS+0;67FS+0 | FS41+0;FS37+0 | 2007-09-26 10:00 | 2007-10-16 17:00 | 15d | stucco[3.0 #4] | 8642 | 0 | 0
36 | drywall | 58FS+0;57FS+0;56FS+0 |  | 2007-10-24 10:00 | 2007-11-27 17:00 | 25d |  | 48000 | 0 | 0
41 | kitchen and bar | 32FS+0;58FS+0;57FS+0;35FS+0 |  | 2007-10-31 10:00 | 2007-11-20 17:00 | 15d |  | 87000 | 0 | 0
37 | techniques | 32FS+0;58FS+0;57FS+0;35FS+0 | FS38+0;FS42+0;FS43+0;FS44+0 | 2007-10-31 10:00 | 2007-11-20 17:00 | 15d |  | 2156.0601 | 0 | 0
44 | stairs | 37FS+0 |  | 2007-11-21 10:00 | 2007-12-04 17:00 | 10d |  | 33000 | 0 | 0
42 | entrance doors | 37FS+0 |  | 2007-11-21 10:00 | 2007-12-04 17:00 | 10d |  | 16000 | 0 | 0
43 | elevator | 37FS+0 |  | 2007-11-21 10:00 | 2007-11-27 17:00 | 5d |  | 38817.8516 | 0 | 0
38 | suspended ceiling | 37FS+0 | FS39+0 | 2007-11-21 10:00 | 2007-11-27 17:00 | 5d |  | 32000 | 0 | 0
39 | painting | 38FS+0 | FS40+0 | 2007-11-28 10:00 | 2007-12-18 17:00 | 15d | painter[4.0 #6] | 83000 | 0 | 0
40 | furniture | 39FS+0 |  | 2007-12-19 10:00 | 2007-12-25 17:00 | 5d | furniture[5.0 #5] | 130000 | 0 | 0

## Resources
General |  |  |  | Resource Cost
ID | Name | Type | Availability | Cost/Use | Cost/Unit
1 | plumber | Renewable | 4 #4 | 0 | 36
2 | electrician | Renewable | 4 #4 | 0 | 32
3 | team VDW | Renewable | 8 #8 | 0 | 38.56
4 | mason | Renewable | 4 #4 | 0 | 40.65
5 | heating | Renewable | 2 #2 | 0 | 43.2
6 | roofing | Renewable | 4 #4 | 0 | 36
7 | windows | Renewable | 3 #3 | 0 | 38
8 | flooring | Renewable | 4 #4 | 0 | 41.56
9 | chapen | Renewable | 3 #3 | 0 | 0
10 | stucco | Renewable | 4 #4 | 0 | 41.38
11 | painter | Renewable | 6 #6 | 0 | 35
12 | furniture | Renewable | 5 #5 | 0 | 42

## Risk Analysis
General |  | Activity Duration Distribution Profiles
ID | Name | Description | Optimistic | Most Probable | Pessimistic
0 | Claeys-Verhelst Premises | manual - absolute | 0 | 0 | 0
46 | preparation | manual - absolute | 0 | 0 | 0
2 | building permit | manual - absolute | 402 | 480 | 812
3 | hire contractor | manual - absolute | 127 | 160 | 326
4 | temporary offices | standard - symmetric | 80 | 100 | 120
5 | temporary facilities | standard - symmetric | 80 | 100 | 120
16 | preparation contractor | standard - no risk | 99 | 100 | 101
6 | demolition | manual - absolute | 219 | 240 | 302
47 | foundation | manual - absolute | 0 | 0 | 0
17 | excavation | standard - symmetric | 80 | 100 | 120
69 | soil analyses | standard - symmetric | 80 | 100 | 120
18 | foundation beam | manual - absolute | 159 | 200 | 363
21 | placing sewerage | manual - absolute | 63 | 80 | 98
23 | foundation plate | manual - absolute | 6 | 8 | 10
48 | shell | manual - absolute | 0 | 0 | 0
19 | steelframe I | manual - absolute | 104 | 120 | 166
20 | concrete vaults I | manual - absolute | 32 | 40 | 48
22 | steelframe II | manual - absolute | 64 | 80 | 113
24 | concrete volt II | manual - absolute | 66 | 80 | 121
50 | wind and water proof | manual - absolute | 0 | 0 | 0
25 | facades | manual - absolute | 128 | 160 | 463
26 | outside windows | manual - absolute | 64 | 80 | 175
49 | roof | standard - symmetric | 80 | 100 | 120
62 | warehouse | manual - absolute | 0 | 0 | 0
28 | v0 polierbeton | standard - symmetric | 80 | 100 | 120
30 | v0 sanitary | standard - no risk | 99 | 100 | 101
27 | v0 -masonry | standard - no risk | 99 | 100 | 101
59 | v0 heating | standard - no risk | 99 | 100 | 101
29 | v0 electricity | standard - no risk | 99 | 100 | 101
35 | v0 floors | manual - absolute | 128 | 163 | 543
66 | construction leave | manual - absolute | 0 | 0 | 0
31 | construction leave | standard - no risk | 99 | 100 | 101
63 | level 1 | manual - absolute | 0 | 0 | 0
52 | vI sanitary | standard - no risk | 99 | 100 | 101
45 | vI masonry | standard - no risk | 99 | 100 | 101
34 | v1screed | standard - no risk | 99 | 100 | 101
60 | v1 heating | standard - no risk | 99 | 100 | 101
51 | vI electricity | standard - no risk | 99 | 100 | 101
67 | v1 drying screed | standard - skewed left | 80 | 110 | 120
57 | v1flooring | manual - absolute | 128 | 160 | 577
64 | level 2 | manual - absolute | 0 | 0 | 0
53 | v2 sanitary | manual - absolute | 99 | 100 | 101
55 | v2 masonry | manual - absolute | 99 | 100 | 101
56 | v2 screed | manual - absolute | 80 | 110 | 120
61 | v2 heating | manual - absolute | 80 | 110 | 120
54 | v2 electricity | manual - absolute | 99 | 100 | 101
68 | v2 drying screed | manual - absolute | 80 | 110 | 120
58 | v2 flooring | manual - absolute | 128 | 160 | 556
65 | completion | manual - absolute | 0 | 0 | 0
32 | stucco | manual - absolute | 96 | 120 | 451
36 | drywall | manual - absolute | 160 | 200 | 528
41 | kitchen and bar | standard - symmetric | 80 | 100 | 120
37 | techniques | standard - symmetric | 80 | 100 | 120
44 | stairs | standard - symmetric | 80 | 100 | 120
42 | entrance doors | standard - symmetric | 80 | 100 | 120
43 | elevator | standard - symmetric | 80 | 100 | 120
38 | suspended ceiling | standard - symmetric | 80 | 100 | 120
39 | painting | standard - symmetric | 80 | 100 | 120
40 | furniture | standard - symmetric | 80 | 100 | 120

## Project Control - TP1
| TP Status Date | 2006-07-07 08:00 | TP Name | Preparation1
General |  | Tracking
ID | Name | Actual Start | Actual Duration | Actual Cost | Percentage Completed
2 | building permit | 2006-04-17 08:00 | 100d | 74.2574 | 99.0099012851715%
3 | hire contractor | 2958466 | 0 | 0 | 0.0%
4 | temporary offices | 2006-04-17 08:00 | 20d | 3765.3101 | 100.0%
5 | temporary facilities | 2006-04-17 08:00 | 60d | 1845.7779 | 98.3606994152069%
6 | demolition | 2958466 | 0 | 0 | 0.0%
16 | preparation contractor | 2958466 | 0 | 0 | 0.0%
17 | excavation | 2958466 | 0 | 0 | 0.0%
18 | foundation beam | 2958466 | 0 | 0 | 0.0%
19 | steelframe I | 2958466 | 0 | 0 | 0.0%
20 | concrete vaults I | 2958466 | 0 | 0 | 0.0%
21 | placing sewerage | 2958466 | 0 | 0 | 0.0%
22 | steelframe II | 2958466 | 0 | 0 | 0.0%
23 | foundation plate | 2958466 | 0 | 0 | 0.0%
24 | concrete volt II | 2958466 | 0 | 0 | 0.0%
25 | facades | 2958466 | 0 | 0 | 0.0%
26 | outside windows | 2958466 | 0 | 0 | 0.0%
27 | v0 -masonry | 2958466 | 0 | 0 | 0.0%
28 | v0 polierbeton | 2958466 | 0 | 0 | 0.0%
29 | v0 electricity | 2958466 | 0 | 0 | 0.0%
30 | v0 sanitary | 2958466 | 0 | 0 | 0.0%
31 | construction leave | 2958466 | 0 | 0 | 0.0%
32 | stucco | 2958466 | 0 | 0 | 0.0%
34 | v1screed | 2958466 | 0 | 0 | 0.0%
35 | v0 floors | 2958466 | 0 | 0 | 0.0%
36 | drywall | 2958466 | 0 | 0 | 0.0%
37 | techniques | 2958466 | 0 | 0 | 0.0%
38 | suspended ceiling | 2958466 | 0 | 0 | 0.0%
39 | painting | 2958466 | 0 | 0 | 0.0%
40 | furniture | 2958466 | 0 | 0 | 0.0%
41 | kitchen and bar | 2958466 | 0 | 0 | 0.0%
42 | entrance doors | 2958466 | 0 | 0 | 0.0%
43 | elevator | 2958466 | 0 | 0 | 0.0%
44 | stairs | 2958466 | 0 | 0 | 0.0%
45 | vI masonry | 2958466 | 0 | 0 | 0.0%
49 | roof | 2958466 | 0 | 0 | 0.0%
51 | vI electricity | 2958466 | 0 | 0 | 0.0%
52 | vI sanitary | 2958466 | 0 | 0 | 0.0%
53 | v2 sanitary | 2958466 | 0 | 0 | 0.0%
54 | v2 electricity | 2958466 | 0 | 0 | 0.0%
55 | v2 masonry | 2958466 | 0 | 0 | 0.0%
56 | v2 screed | 2958466 | 0 | 0 | 0.0%
57 | v1flooring | 2958466 | 0 | 0 | 0.0%
58 | v2 flooring | 2958466 | 0 | 0 | 0.0%
59 | v0 heating | 2958466 | 0 | 0 | 0.0%
60 | v1 heating | 2958466 | 0 | 0 | 0.0%
61 | v2 heating | 2958466 | 0 | 0 | 0.0%
67 | v1 drying screed | 2958466 | 0 | 0 | 0.0%
68 | v2 drying screed | 2958466 | 0 | 0 | 0.0%
69 | soil analyses | 2958466 | 0 | 0 | 0.0%

## TP2
| TP Status Date | 2007-02-08 08:00 | TP Name | Preparation2
General |  | Tracking
ID | Name | Actual Start | Actual Duration | Actual Cost | Percentage Completed
2 | building permit | 2006-04-17 08:00 | 100d | 75 | 100.0%
3 | hire contractor | 2006-09-04 08:00 | 30d | 210000 | 100.0%
4 | temporary offices | 2006-04-17 08:00 | 20d | 3765.3101 | 100.0%
5 | temporary facilities | 2006-04-17 08:00 | 60d | 1876.54 | 100.0%
6 | demolition | 2006-11-27 08:00 | 54d | 38087.71 | 100.0%
16 | preparation contractor | 2006-09-04 08:00 | 60d | 0.01 | 100.0%
17 | excavation | 2958466 | 0 | 0 | 0.0%
18 | foundation beam | 2958466 | 0 | 0 | 0.0%
19 | steelframe I | 2958466 | 0 | 0 | 0.0%
20 | concrete vaults I | 2958466 | 0 | 0 | 0.0%
21 | placing sewerage | 2958466 | 0 | 0 | 0.0%
22 | steelframe II | 2958466 | 0 | 0 | 0.0%
23 | foundation plate | 2958466 | 0 | 0 | 0.0%
24 | concrete volt II | 2958466 | 0 | 0 | 0.0%
25 | facades | 2958466 | 0 | 0 | 0.0%
26 | outside windows | 2958466 | 0 | 0 | 0.0%
27 | v0 -masonry | 2958466 | 0 | 0 | 0.0%
28 | v0 polierbeton | 2958466 | 0 | 0 | 0.0%
29 | v0 electricity | 2958466 | 0 | 0 | 0.0%
30 | v0 sanitary | 2958466 | 0 | 0 | 0.0%
31 | construction leave | 2958466 | 0 | 0 | 0.0%
32 | stucco | 2958466 | 0 | 0 | 0.0%
34 | v1screed | 2958466 | 0 | 0 | 0.0%
35 | v0 floors | 2958466 | 0 | 0 | 0.0%
36 | drywall | 2958466 | 0 | 0 | 0.0%
37 | techniques | 2958466 | 0 | 0 | 0.0%
38 | suspended ceiling | 2958466 | 0 | 0 | 0.0%
39 | painting | 2958466 | 0 | 0 | 0.0%
40 | furniture | 2958466 | 0 | 0 | 0.0%
41 | kitchen and bar | 2958466 | 0 | 0 | 0.0%
42 | entrance doors | 2958466 | 0 | 0 | 0.0%
43 | elevator | 2958466 | 0 | 0 | 0.0%
44 | stairs | 2958466 | 0 | 0 | 0.0%
45 | vI masonry | 2958466 | 0 | 0 | 0.0%
49 | roof | 2958466 | 0 | 0 | 0.0%
51 | vI electricity | 2958466 | 0 | 0 | 0.0%
52 | vI sanitary | 2958466 | 0 | 0 | 0.0%
53 | v2 sanitary | 2958466 | 0 | 0 | 0.0%
54 | v2 electricity | 2958466 | 0 | 0 | 0.0%
55 | v2 masonry | 2958466 | 0 | 0 | 0.0%
56 | v2 screed | 2958466 | 0 | 0 | 0.0%
57 | v1flooring | 2958466 | 0 | 0 | 0.0%
58 | v2 flooring | 2958466 | 0 | 0 | 0.0%
59 | v0 heating | 2958466 | 0 | 0 | 0.0%
60 | v1 heating | 2958466 | 0 | 0 | 0.0%
61 | v2 heating | 2958466 | 0 | 0 | 0.0%
67 | v1 drying screed | 2958466 | 0 | 0 | 0.0%
68 | v2 drying screed | 2958466 | 0 | 0 | 0.0%
69 | soil analyses | 2958466 | 0 | 0 | 0.0%

## TP3
| TP Status Date | 2007-03-17 08:00 | TP Name | Foundation
General |  | Tracking
ID | Name | Actual Start | Actual Duration | Actual Cost | Percentage Completed
2 | building permit | 2006-04-17 08:00 | 100d | 75 | 100.0%
3 | hire contractor | 2006-09-04 08:00 | 30d | 210000 | 100.0%
4 | temporary offices | 2006-04-17 08:00 | 20d | 3765.3101 | 100.0%
5 | temporary facilities | 2006-04-17 08:00 | 60d | 1876.54 | 100.0%
6 | demolition | 2006-11-27 08:00 | 54d | 38087.71 | 100.0%
16 | preparation contractor | 2006-09-04 08:00 | 60d | 0.01 | 100.0%
17 | excavation | 2007-02-08 08:00 | 10d | 30318.72 | 100.0%
18 | foundation beam | 2007-02-28 08:00 | 22d | 78721.0239 | 64.705902338028%
19 | steelframe I | 2958466 | 0 | 0 | 0.0%
20 | concrete vaults I | 2958466 | 0 | 0 | 0.0%
21 | placing sewerage | 2007-02-28 08:00 | 12d | 10479.13 | 100.0%
22 | steelframe II | 2958466 | 0 | 0 | 0.0%
23 | foundation plate | 2007-03-16 08:00 | 1d | 236361.8375 | 100.0%
24 | concrete volt II | 2958466 | 0 | 0 | 0.0%
25 | facades | 2958466 | 0 | 0 | 0.0%
26 | outside windows | 2958466 | 0 | 0 | 0.0%
27 | v0 -masonry | 2958466 | 0 | 0 | 0.0%
28 | v0 polierbeton | 2958466 | 0 | 0 | 0.0%
29 | v0 electricity | 2958466 | 0 | 0 | 0.0%
30 | v0 sanitary | 2958466 | 0 | 0 | 0.0%
31 | construction leave | 2958466 | 0 | 0 | 0.0%
32 | stucco | 2958466 | 0 | 0 | 0.0%
34 | v1screed | 2958466 | 0 | 0 | 0.0%
35 | v0 floors | 2958466 | 0 | 0 | 0.0%
36 | drywall | 2958466 | 0 | 0 | 0.0%
37 | techniques | 2958466 | 0 | 0 | 0.0%
38 | suspended ceiling | 2958466 | 0 | 0 | 0.0%
39 | painting | 2958466 | 0 | 0 | 0.0%
40 | furniture | 2958466 | 0 | 0 | 0.0%
41 | kitchen and bar | 2958466 | 0 | 0 | 0.0%
42 | entrance doors | 2958466 | 0 | 0 | 0.0%
43 | elevator | 2958466 | 0 | 0 | 0.0%
44 | stairs | 2958466 | 0 | 0 | 0.0%
45 | vI masonry | 2958466 | 0 | 0 | 0.0%
49 | roof | 2958466 | 0 | 0 | 0.0%
51 | vI electricity | 2958466 | 0 | 0 | 0.0%
52 | vI sanitary | 2958466 | 0 | 0 | 0.0%
53 | v2 sanitary | 2958466 | 0 | 0 | 0.0%
54 | v2 electricity | 2958466 | 0 | 0 | 0.0%
55 | v2 masonry | 2958466 | 0 | 0 | 0.0%
56 | v2 screed | 2958466 | 0 | 0 | 0.0%
57 | v1flooring | 2958466 | 0 | 0 | 0.0%
58 | v2 flooring | 2958466 | 0 | 0 | 0.0%
59 | v0 heating | 2958466 | 0 | 0 | 0.0%
60 | v1 heating | 2958466 | 0 | 0 | 0.0%
61 | v2 heating | 2958466 | 0 | 0 | 0.0%
67 | v1 drying screed | 2958466 | 0 | 0 | 0.0%
68 | v2 drying screed | 2958466 | 0 | 0 | 0.0%
69 | soil analyses | 2007-02-08 08:00 | 12d | 2616.96 | 100.0%

## TP4
| TP Status Date | 2007-06-04 08:00 | TP Name | Shell
General |  | Tracking
ID | Name | Actual Start | Actual Duration | Actual Cost | Percentage Completed
2 | building permit | 2006-04-17 08:00 | 100d | 75 | 100.0%
3 | hire contractor | 2006-09-04 08:00 | 30d | 210000 | 100.0%
4 | temporary offices | 2006-04-17 08:00 | 20d | 3765.3101 | 100.0%
5 | temporary facilities | 2006-04-17 08:00 | 60d | 1876.54 | 100.0%
6 | demolition | 2006-11-27 08:00 | 54d | 38087.71 | 100.0%
16 | preparation contractor | 2006-09-04 08:00 | 60d | 0.01 | 100.0%
17 | excavation | 2007-02-08 08:00 | 10d | 30318.72 | 100.0%
18 | foundation beam | 2007-02-28 08:00 | 22d | 121659.7266 | 100.0%
19 | steelframe I | 2007-04-02 08:00 | 15d | 61794.0084 | 43.010801076889%
20 | concrete vaults I | 2007-04-23 08:00 | 5d | 129748.9187 | 100.0%
21 | placing sewerage | 2007-02-28 08:00 | 12d | 10479.13 | 100.0%
22 | steelframe II | 2007-04-30 08:00 | 15d | 132874.1078 | 100.0%
23 | foundation plate | 2007-03-16 08:00 | 1d | 236361.8375 | 100.0%
24 | concrete volt II | 2007-05-21 08:00 | 10d | 135918.5187 | 100.0%
25 | facades | 2958466 | 0 | 0 | 0.0%
26 | outside windows | 2958466 | 0 | 0 | 0.0%
27 | v0 -masonry | 2958466 | 0 | 0 | 0.0%
28 | v0 polierbeton | 2958466 | 0 | 0 | 0.0%
29 | v0 electricity | 2958466 | 0 | 0 | 0.0%
30 | v0 sanitary | 2958466 | 0 | 0 | 0.0%
31 | construction leave | 2958466 | 0 | 0 | 0.0%
32 | stucco | 2958466 | 0 | 0 | 0.0%
34 | v1screed | 2958466 | 0 | 0 | 0.0%
35 | v0 floors | 2958466 | 0 | 0 | 0.0%
36 | drywall | 2958466 | 0 | 0 | 0.0%
37 | techniques | 2958466 | 0 | 0 | 0.0%
38 | suspended ceiling | 2958466 | 0 | 0 | 0.0%
39 | painting | 2958466 | 0 | 0 | 0.0%
40 | furniture | 2958466 | 0 | 0 | 0.0%
41 | kitchen and bar | 2958466 | 0 | 0 | 0.0%
42 | entrance doors | 2958466 | 0 | 0 | 0.0%
43 | elevator | 2958466 | 0 | 0 | 0.0%
44 | stairs | 2958466 | 0 | 0 | 0.0%
45 | vI masonry | 2958466 | 0 | 0 | 0.0%
49 | roof | 2958466 | 0 | 0 | 0.0%
51 | vI electricity | 2958466 | 0 | 0 | 0.0%
52 | vI sanitary | 2958466 | 0 | 0 | 0.0%
53 | v2 sanitary | 2958466 | 0 | 0 | 0.0%
54 | v2 electricity | 2958466 | 0 | 0 | 0.0%
55 | v2 masonry | 2958466 | 0 | 0 | 0.0%
56 | v2 screed | 2958466 | 0 | 0 | 0.0%
57 | v1flooring | 2958466 | 0 | 0 | 0.0%
58 | v2 flooring | 2958466 | 0 | 0 | 0.0%
59 | v0 heating | 2958466 | 0 | 0 | 0.0%
60 | v1 heating | 2958466 | 0 | 0 | 0.0%
61 | v2 heating | 2958466 | 0 | 0 | 0.0%
67 | v1 drying screed | 2958466 | 0 | 0 | 0.0%
68 | v2 drying screed | 2958466 | 0 | 0 | 0.0%
69 | soil analyses | 2007-02-08 08:00 | 12d | 2616.96 | 100.0%

## TP5
| TP Status Date | 2007-07-02 08:00 | TP Name | Wind&Waterproof
General |  | Tracking
ID | Name | Actual Start | Actual Duration | Actual Cost | Percentage Completed
2 | building permit | 2006-04-17 08:00 | 100d | 75 | 100.0%
3 | hire contractor | 2006-09-04 08:00 | 30d | 210000 | 100.0%
4 | temporary offices | 2006-04-17 08:00 | 20d | 3765.3101 | 100.0%
5 | temporary facilities | 2006-04-17 08:00 | 60d | 1876.54 | 100.0%
6 | demolition | 2006-11-27 08:00 | 54d | 38087.71 | 100.0%
16 | preparation contractor | 2006-09-04 08:00 | 60d | 0.01 | 100.0%
17 | excavation | 2007-02-08 08:00 | 10d | 30318.72 | 100.0%
18 | foundation beam | 2007-02-28 08:00 | 22d | 121659.7266 | 100.0%
19 | steelframe I | 2007-04-02 08:00 | 15d | 143670.9078 | 100.0%
20 | concrete vaults I | 2007-04-23 08:00 | 5d | 129748.9187 | 100.0%
21 | placing sewerage | 2007-02-28 08:00 | 12d | 10479.13 | 100.0%
22 | steelframe II | 2007-04-30 08:00 | 15d | 132874.1078 | 100.0%
23 | foundation plate | 2007-03-16 08:00 | 1d | 236361.8375 | 100.0%
24 | concrete volt II | 2007-05-21 08:00 | 10d | 135918.5187 | 100.0%
25 | facades | 2007-06-04 08:00 | 20d | 251180.8631 | 71.42857313156131%
26 | outside windows | 2007-07-02 08:00 | 92d | 144373.9326 | 90.30674695968631%
27 | v0 -masonry | 2958466 | 0 | 0 | 0.0%
28 | v0 polierbeton | 2958466 | 0 | 0 | 0.0%
29 | v0 electricity | 2958466 | 0 | 0 | 0.0%
30 | v0 sanitary | 2958466 | 0 | 0 | 0.0%
31 | construction leave | 2958466 | 0 | 0 | 0.0%
32 | stucco | 2958466 | 0 | 0 | 0.0%
34 | v1screed | 2958466 | 0 | 0 | 0.0%
35 | v0 floors | 2958466 | 0 | 0 | 0.0%
36 | drywall | 2958466 | 0 | 0 | 0.0%
37 | techniques | 2958466 | 0 | 0 | 0.0%
38 | suspended ceiling | 2958466 | 0 | 0 | 0.0%
39 | painting | 2958466 | 0 | 0 | 0.0%
40 | furniture | 2958466 | 0 | 0 | 0.0%
41 | kitchen and bar | 2958466 | 0 | 0 | 0.0%
42 | entrance doors | 2958466 | 0 | 0 | 0.0%
43 | elevator | 2958466 | 0 | 0 | 0.0%
44 | stairs | 2958466 | 0 | 0 | 0.0%
45 | vI masonry | 2958466 | 0 | 0 | 0.0%
49 | roof | 2007-06-04 08:00 | 10d | 85523.5703 | 100.0%
51 | vI electricity | 2958466 | 0 | 0 | 0.0%
52 | vI sanitary | 2958466 | 0 | 0 | 0.0%
53 | v2 sanitary | 2958466 | 0 | 0 | 0.0%
54 | v2 electricity | 2958466 | 0 | 0 | 0.0%
55 | v2 masonry | 2958466 | 0 | 0 | 0.0%
56 | v2 screed | 2958466 | 0 | 0 | 0.0%
57 | v1flooring | 2958466 | 0 | 0 | 0.0%
58 | v2 flooring | 2958466 | 0 | 0 | 0.0%
59 | v0 heating | 2958466 | 0 | 0 | 0.0%
60 | v1 heating | 2958466 | 0 | 0 | 0.0%
61 | v2 heating | 2958466 | 0 | 0 | 0.0%
67 | v1 drying screed | 2958466 | 0 | 0 | 0.0%
68 | v2 drying screed | 2958466 | 0 | 0 | 0.0%
69 | soil analyses | 2007-02-08 08:00 | 12d | 2616.96 | 100.0%

## TP6
| TP Status Date | 2007-10-24 08:00 | TP Name | WH, L1, L2
General |  | Tracking
ID | Name | Actual Start | Actual Duration | Actual Cost | Percentage Completed
2 | building permit | 2006-04-17 08:00 | 100d | 75 | 100.0%
3 | hire contractor | 2006-09-04 08:00 | 30d | 210000 | 100.0%
4 | temporary offices | 2006-04-17 08:00 | 20d | 3765.3101 | 100.0%
5 | temporary facilities | 2006-04-17 08:00 | 60d | 1876.54 | 100.0%
6 | demolition | 2006-11-27 08:00 | 54d | 38087.71 | 100.0%
16 | preparation contractor | 2006-09-04 08:00 | 60d | 0.01 | 100.0%
17 | excavation | 2007-02-08 08:00 | 10d | 30318.72 | 100.0%
18 | foundation beam | 2007-02-28 08:00 | 22d | 121659.7266 | 100.0%
19 | steelframe I | 2007-04-02 08:00 | 15d | 143670.9078 | 100.0%
20 | concrete vaults I | 2007-04-23 08:00 | 5d | 129748.9187 | 100.0%
21 | placing sewerage | 2007-02-28 08:00 | 12d | 10479.13 | 100.0%
22 | steelframe II | 2007-04-30 08:00 | 15d | 132874.1078 | 100.0%
23 | foundation plate | 2007-03-16 08:00 | 1d | 236361.8375 | 100.0%
24 | concrete volt II | 2007-05-21 08:00 | 10d | 135918.5187 | 100.0%
25 | facades | 2007-06-04 08:00 | 20d | 351653.2 | 100.0%
26 | outside windows | 2007-07-02 08:00 | 92d | 144373.9326 | 90.30674695968631%
27 | v0 -masonry | 2007-08-29 08:00 | 10d | 37704.9611 | 100.0%
28 | v0 polierbeton | 2007-07-25 08:00 | 5d | 149824 | 100.0%
29 | v0 electricity | 2007-08-02 08:00 | 15d | 6400 | 100.0%
30 | v0 sanitary | 2007-08-29 08:00 | 10d | 7673 | 100.0%
31 | construction leave | 2007-08-08 08:00 | 10d | 0.01 | 100.0%
32 | stucco | 2958466 | 0 | 0 | 0.0%
34 | v1screed | 2007-08-29 08:00 | 15d | 106140 | 100.0%
35 | v0 floors | 2007-09-26 08:00 | 20d | 81649.6 | 100.0%
36 | drywall | 2958466 | 0 | 0 | 0.0%
37 | techniques | 2958466 | 0 | 0 | 0.0%
38 | suspended ceiling | 2958466 | 0 | 0 | 0.0%
39 | painting | 2958466 | 0 | 0 | 0.0%
40 | furniture | 2958466 | 0 | 0 | 0.0%
41 | kitchen and bar | 2958466 | 0 | 0 | 0.0%
42 | entrance doors | 2958466 | 0 | 0 | 0.0%
43 | elevator | 2958466 | 0 | 0 | 0.0%
44 | stairs | 2958466 | 0 | 0 | 0.0%
45 | vI masonry | 2007-08-29 08:00 | 10d | 37704.9611 | 100.0%
49 | roof | 2007-06-04 08:00 | 10d | 85523.5703 | 100.0%
51 | vI electricity | 2007-08-29 08:00 | 25d | 6400 | 100.0%
52 | vI sanitary | 2007-08-29 08:00 | 10d | 7673 | 100.0%
53 | v2 sanitary | 2007-08-29 08:00 | 10d | 7673 | 100.0%
54 | v2 electricity | 2007-08-29 08:00 | 20d | 6400 | 100.0%
55 | v2 masonry | 2007-08-29 08:00 | 10d | 34452.9609 | 100.0%
56 | v2 screed | 2007-08-29 08:00 | 15d | 46116 | 100.0%
57 | v1flooring | 2007-10-03 08:00 | 20d | 63319.6809 | 80.0000011920929%
58 | v2 flooring | 2007-09-26 08:00 | 20d | 38149.6 | 100.0%
59 | v0 heating | 2007-08-29 08:00 | 20d | 18563 | 100.0%
60 | v1 heating | 2007-08-29 08:00 | 20d | 25475.0001 | 100.0%
61 | v2 heating | 2007-08-29 08:00 | 20d | 16771 | 100.0%
67 | v1 drying screed | 2007-09-19 08:00 | 5d | 0.01 | 100.0%
68 | v2 drying screed | 2007-09-19 08:00 | 5d | 0.01 | 100.0%
69 | soil analyses | 2007-02-08 08:00 | 12d | 2616.96 | 100.0%

## TP7
| TP Status Date | 2008-01-10 08:00 | TP Name | Completion
General |  | Tracking
ID | Name | Actual Start | Actual Duration | Actual Cost | Percentage Completed
2 | building permit | 2006-04-17 08:00 | 100d | 75 | 100.0%
3 | hire contractor | 2006-09-04 08:00 | 30d | 210000 | 100.0%
4 | temporary offices | 2006-04-17 08:00 | 20d | 3765.3101 | 100.0%
5 | temporary facilities | 2006-04-17 08:00 | 60d | 1876.54 | 100.0%
6 | demolition | 2006-11-27 08:00 | 54d | 38087.71 | 100.0%
16 | preparation contractor | 2006-09-04 08:00 | 60d | 0.01 | 100.0%
17 | excavation | 2007-02-08 08:00 | 10d | 30318.72 | 100.0%
18 | foundation beam | 2007-02-28 08:00 | 22d | 121659.7266 | 100.0%
19 | steelframe I | 2007-04-02 08:00 | 15d | 143670.9078 | 100.0%
20 | concrete vaults I | 2007-04-23 08:00 | 5d | 129748.9187 | 100.0%
21 | placing sewerage | 2007-02-28 08:00 | 12d | 10479.13 | 100.0%
22 | steelframe II | 2007-04-30 08:00 | 15d | 132874.1078 | 100.0%
23 | foundation plate | 2007-03-16 08:00 | 1d | 236361.8375 | 100.0%
24 | concrete volt II | 2007-05-21 08:00 | 10d | 135918.5187 | 100.0%
25 | facades | 2007-06-04 08:00 | 20d | 351653.2 | 100.0%
26 | outside windows | 2007-07-02 08:00 | 92d | 159870.5938 | 100.0%
27 | v0 -masonry | 2007-08-29 08:00 | 10d | 37704.9611 | 100.0%
28 | v0 polierbeton | 2007-07-25 08:00 | 5d | 149824 | 100.0%
29 | v0 electricity | 2007-08-02 08:00 | 15d | 6400 | 100.0%
30 | v0 sanitary | 2007-08-29 08:00 | 10d | 7673 | 100.0%
31 | construction leave | 2007-08-08 08:00 | 10d | 0.01 | 100.0%
32 | stucco | 2007-11-05 08:00 | 15d | 23538.8 | 100.0%
34 | v1screed | 2007-08-29 08:00 | 15d | 106140 | 100.0%
35 | v0 floors | 2007-09-26 08:00 | 20d | 81649.6 | 100.0%
36 | drywall | 2007-11-05 08:00 | 25d | 48000 | 100.0%
37 | techniques | 2007-11-26 08:00 | 15d | 2156.0601 | 100.0%
38 | suspended ceiling | 2007-12-10 08:00 | 5d | 32000 | 100.0%
39 | painting | 2007-12-17 08:00 | 15d | 99800 | 100.0%
40 | furniture | 2008-01-03 08:00 | 5d | 138400 | 100.0%
41 | kitchen and bar | 2007-11-26 08:00 | 20d | 87000 | 100.0%
42 | entrance doors | 2007-12-10 08:00 | 10d | 16000 | 100.0%
43 | elevator | 2007-12-10 08:00 | 5d | 38817.8516 | 100.0%
44 | stairs | 2007-12-10 08:00 | 10d | 33000 | 100.0%
45 | vI masonry | 2007-08-29 08:00 | 10d | 37704.9611 | 100.0%
49 | roof | 2007-06-04 08:00 | 10d | 85523.5703 | 100.0%
51 | vI electricity | 2007-08-29 08:00 | 25d | 6400 | 100.0%
52 | vI sanitary | 2007-08-29 08:00 | 10d | 7673 | 100.0%
53 | v2 sanitary | 2007-08-29 08:00 | 10d | 7673 | 100.0%
54 | v2 electricity | 2007-08-29 08:00 | 20d | 6400 | 100.0%
55 | v2 masonry | 2007-08-29 08:00 | 10d | 34452.9609 | 100.0%
56 | v2 screed | 2007-08-29 08:00 | 15d | 46116 | 100.0%
57 | v1flooring | 2007-10-03 08:00 | 20d | 79149.6 | 100.0%
58 | v2 flooring | 2007-09-26 08:00 | 20d | 38149.6 | 100.0%
59 | v0 heating | 2007-08-29 08:00 | 20d | 18563 | 100.0%
60 | v1 heating | 2007-08-29 08:00 | 20d | 25475.0001 | 100.0%
61 | v2 heating | 2007-08-29 08:00 | 20d | 16771 | 100.0%
67 | v1 drying screed | 2007-09-19 08:00 | 5d | 0.01 | 100.0%
68 | v2 drying screed | 2007-09-19 08:00 | 5d | 0.01 | 100.0%
69 | soil analyses | 2007-02-08 08:00 | 12d | 2616.96 | 100.0%

## TP8
| TP Status Date | 2008-01-11 08:00 | TP Name | Finish
General |  | Tracking
ID | Name | Actual Start | Actual Duration | Actual Cost | Percentage Completed
2 | building permit | 2006-04-17 08:00 | 100d | 75 | 100.0%
3 | hire contractor | 2006-09-04 08:00 | 30d | 210000 | 100.0%
4 | temporary offices | 2006-04-17 08:00 | 20d | 3765.3101 | 100.0%
5 | temporary facilities | 2006-04-17 08:00 | 60d | 1876.54 | 100.0%
6 | demolition | 2006-11-27 08:00 | 54d | 38087.71 | 100.0%
16 | preparation contractor | 2006-09-04 08:00 | 60d | 0.01 | 100.0%
17 | excavation | 2007-02-08 08:00 | 10d | 30318.72 | 100.0%
18 | foundation beam | 2007-02-28 08:00 | 22d | 121659.7266 | 100.0%
19 | steelframe I | 2007-04-02 08:00 | 15d | 143670.9078 | 100.0%
20 | concrete vaults I | 2007-04-23 08:00 | 5d | 129748.9187 | 100.0%
21 | placing sewerage | 2007-02-28 08:00 | 12d | 10479.13 | 100.0%
22 | steelframe II | 2007-04-30 08:00 | 15d | 132874.1078 | 100.0%
23 | foundation plate | 2007-03-16 08:00 | 1d | 236361.8375 | 100.0%
24 | concrete volt II | 2007-05-21 08:00 | 10d | 135918.5187 | 100.0%
25 | facades | 2007-06-04 08:00 | 20d | 351653.2 | 100.0%
26 | outside windows | 2007-07-02 08:00 | 92d | 159870.5938 | 100.0%
27 | v0 -masonry | 2007-08-29 08:00 | 10d | 37704.9611 | 100.0%
28 | v0 polierbeton | 2007-07-25 08:00 | 5d | 149824 | 100.0%
29 | v0 electricity | 2007-08-02 08:00 | 15d | 6400 | 100.0%
30 | v0 sanitary | 2007-08-29 08:00 | 10d | 7673 | 100.0%
31 | construction leave | 2007-08-08 08:00 | 10d | 0.01 | 100.0%
32 | stucco | 2007-11-05 08:00 | 15d | 23538.8 | 100.0%
34 | v1screed | 2007-08-29 08:00 | 15d | 106140 | 100.0%
35 | v0 floors | 2007-09-26 08:00 | 20d | 81649.6 | 100.0%
36 | drywall | 2007-11-05 08:00 | 25d | 48000 | 100.0%
37 | techniques | 2007-11-26 08:00 | 15d | 2156.0601 | 100.0%
38 | suspended ceiling | 2007-12-10 08:00 | 5d | 32000 | 100.0%
39 | painting | 2007-12-17 08:00 | 15d | 99800 | 100.0%
40 | furniture | 2008-01-03 08:00 | 5d | 138400 | 100.0%
41 | kitchen and bar | 2007-11-26 08:00 | 20d | 87000 | 100.0%
42 | entrance doors | 2007-12-10 08:00 | 10d | 16000 | 100.0%
43 | elevator | 2007-12-10 08:00 | 5d | 38817.8516 | 100.0%
44 | stairs | 2007-12-10 08:00 | 10d | 33000 | 100.0%
45 | vI masonry | 2007-08-29 08:00 | 10d | 37704.9611 | 100.0%
49 | roof | 2007-06-04 08:00 | 10d | 85523.5703 | 100.0%
51 | vI electricity | 2007-08-29 08:00 | 25d | 6400 | 100.0%
52 | vI sanitary | 2007-08-29 08:00 | 10d | 7673 | 100.0%
53 | v2 sanitary | 2007-08-29 08:00 | 10d | 7673 | 100.0%
54 | v2 electricity | 2007-08-29 08:00 | 20d | 6400 | 100.0%
55 | v2 masonry | 2007-08-29 08:00 | 10d | 34452.9609 | 100.0%
56 | v2 screed | 2007-08-29 08:00 | 15d | 46116 | 100.0%
57 | v1flooring | 2007-10-03 08:00 | 20d | 79149.6 | 100.0%
58 | v2 flooring | 2007-09-26 08:00 | 20d | 38149.6 | 100.0%
59 | v0 heating | 2007-08-29 08:00 | 20d | 18563 | 100.0%
60 | v1 heating | 2007-08-29 08:00 | 20d | 25475.0001 | 100.0%
61 | v2 heating | 2007-08-29 08:00 | 20d | 16771 | 100.0%
67 | v1 drying screed | 2007-09-19 08:00 | 5d | 0.01 | 100.0%
68 | v2 drying screed | 2007-09-19 08:00 | 5d | 0.01 | 100.0%
69 | soil analyses | 2007-02-08 08:00 | 12d | 2616.96 | 100.0%

## Agenda
Working Hours |  | Working Days |  | Holidays
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor
Preparation1 | 2006-04-17 08:00 | 2006-07-07 08:00 | 3027133.1861 | 5716.8501 | 5685.3454 | 2006-04-17 08:00 | -3021416.336 | 0% | 31.5047 | 101% | -59d | 0%
Preparation2 | 2006-07-07 08:00 | 2007-02-08 08:00 | 3027133.1861 | 253804.5701 | 253804.5701 | 2006-04-17 08:00 | -2773328.616 | 8% | 0 | 100% | -213d | 0%
Foundation | 2007-02-08 08:00 | 2007-03-17 08:00 | 3027133.1861 | 647075.3017 | 612302.2414 | 2006-04-17 08:00 | -2380057.8844 | 21% | 34773.0603 | 106% | -240d | 0%
Shell | 2007-03-17 08:00 | 2007-06-04 08:00 | 3027133.1861 | 1183389.3748 | 1115576.4978 | 2006-04-17 08:00 | -1843743.8113 | 39% | 67812.877 | 106% | -295d | 0%
Wind&Waterproof | 2007-06-04 08:00 | 2007-07-02 08:00 | 3027133.1861 | 1819107.2505 | 1678531.7632 | 2006-04-17 08:00 | -1208025.9355 | 60% | 140575.4873 | 108% | -315d | 0%
WH, L1, L2 | 2007-07-02 08:00 | 2007-10-24 08:00 | 3027133.1861 | 2725086.5338 | 2477093.8942 | 2006-04-17 08:00 | -302046.6523 | 90% | 247992.6396 | 110% | -397d | 0%
Completion | 2007-10-24 08:00 | 2008-01-10 08:00 | 3027133.1861 | 3246013.19 | 3027133.1861 | 2006-12-08 17:00 | 218880.004 | 107% | 218880.004 | 107% | -283d | 38%
Finish | 2008-01-10 08:00 | 2008-01-11 08:00 | 3027133.1861 | 3246013.19 | 3027133.1861 | 2006-12-08 17:00 | 218880.004 | 107% | 218880.004 | 107% | -284d | 37%