## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost
0 | Claeys-Verhelst Premises | 1 |  |  | 2015-04-22 11:10 | 2015-05-02 11:10 | 10d |  | 0 | 0 | 0 | 0 | 0
46 | preparation | 1.1 |  |  | 2015-04-22 11:10 | 2015-05-02 11:10 | 10d |  | 0 | 0 | 0 | 0 | 0
2 | building permit | 1.1.1 |  | FS3+0 | 2006-04-17 08:00 | 2015-05-02 11:10 | 20d |  | 0 | 75 | 0 | 0 | 75
3 | hire contractor | 1.1.2 | FS2+0 | FS16+0 | 2006-07-10 08:00 | 2015-05-02 11:10 | 6d 16h |  | 0 | 210000 | 0 | 0 | 210000
4 | temporary offices | 1.1.3 |  |  | 2006-04-17 08:00 | 2015-05-02 11:10 | 6d 16h |  | 0 | 3765.3101 | 0 | 0 | 3765.3101
5 | temporary facilities | 1.1.4 |  |  | 2006-04-17 08:00 | 2015-05-02 11:10 | 20d |  | 0 | 1876.54 | 0 | 0 | 1876.54
16 | preparation contractor | 1.1.5 | FS3+0 | FS6+0 | 2006-08-07 08:00 | 2015-05-02 11:10 | 20d |  | 0 | 0.01 | 0 | 0 | 0.01
6 | demolition | 1.1.6 | FS16+0 | FS17+0;FS69+0 | 2006-10-30 08:00 | 2015-05-02 11:10 | 10d | team VDW [4.0 #8] | 12339.2 | 1070.11 | 0 | 0 | 13409.31
47 | foundation | 1.2 |  |  | 2015-04-22 11:10 | 2015-05-02 11:10 | 10d |  | 0 | 0 | 0 | 0 | 0
17 | excavation | 1.2.1 | FS6+0 | FS18+0;FS21+0 | 2006-12-11 08:00 | 2015-05-02 11:10 | 4d 16h | team VDW | 1850.88 | 26000 | 0 | 0 | 27850.88
69 | soil analyses | 1.2.2 | FS6+0 | FS18+0 | 2006-12-11 08:00 | 2015-05-02 11:10 | 0d 16h | team VDW | 616.96 | 2000 | 0 | 0 | 2616.96
18 | foundation beam | 1.2.3 | 17FS+0;FS69+0 | FS19+0 | 2006-12-29 08:00 | 2015-05-02 11:10 | 8d 8h | team VDW [3.0 #8] | 8328.96 | 98523.7266 | 0 | 0 | 106852.6866
21 | placing sewerage | 1.2.4 | FS17+0 | FS23+0 | 2006-12-29 08:00 | 2015-05-02 11:10 | 3d 8h | team VDW [3.0 #8] | 3701.76 | 1224.73 | 0 | 0 | 4926.49
23 | foundation plate | 1.2.5 | FS21+0 | FS19+0 | 2007-01-12 08:00 | 2015-05-02 11:10 | 0d 8h | team VDW [5.0 #8] | 1542.4 | 234819.4375 | 0 | 0 | 236361.8375
48 | shell | 1.3 |  |  | 2015-04-22 11:10 | 2015-05-02 11:10 | 10d |  | 0 | 0 | 0 | 0 | 0
19 | steelframe I | 1.3.1 | 18FS+0;FS23+0 | FS20+0 | 2007-02-02 08:00 | 2015-05-02 11:10 | 6d 16h | team VDW [4.0 #8] | 9871.36 | 118992.5078 | 0 | 0 | 128863.8678
20 | concrete vaults I | 1.3.2 | FS19+0 | FS22+0 | 2007-03-02 08:00 | 2015-05-02 11:10 | 3d 8h | team VDW [4.0 #8] | 4935.68 | 117409.7188 | 0 | 0 | 122345.3987
22 | steelframe II | 1.3.3 | FS20+0 | FS24+0 | 2007-03-16 08:00 | 2015-05-02 11:10 | 5d | team VDW [3.0 #8] | 4627.2 | 118992.5078 | 0 | 0 | 123619.7078
24 | concrete volt II | 1.3.4 | FS22+0 | FS25+0;FS49+0 | 2007-04-06 08:00 | 2015-05-02 11:10 | 5d | team VDW [4.0 #8] | 6169.6 | 117409.7188 | 0 | 0 | 123579.3188
50 | wind and water proof | 1.4 |  |  | 2015-04-22 11:10 | 2015-05-02 11:10 | 10d |  | 0 | 0 | 0 | 0 | 0
25 | facades | 1.4.1 | FS24+0 | FS26+0 | 2007-04-27 08:00 | 2015-05-02 11:10 | 6d 16h | team VDW [2.0 #8] | 4935.68 | 339314 | 0 | 0 | 344249.68
26 | outside windows | 1.4.2 | FS25+0 | FS28+0;FS29+0 | 2007-05-25 08:00 | 2015-05-02 11:10 | 3d 8h | windows [3.0 #3] | 3648 | 150750.5938 | 0 | 0 | 154398.5938
49 | roof | 1.4.3 | FS24+0 |  | 2007-04-27 08:00 | 2015-05-02 11:10 | 3d 8h | roofing [4.0 #4] | 4608 | 70779.5703 | 40.3 | 25791.9995 | 101179.5698
62 | warehouse | 1.5 |  |  | 2015-04-22 11:10 | 2015-05-02 11:10 | 10d |  | 0 | 0 | 0 | 0 | 0
28 | v0 polierbeton | 1.5.1 | FS26+0 | FS30+0;FS27+0;FS59+0;FS52+0;FS45+0;FS34+0;FS60+0;FS51+0 | 2007-06-08 08:00 | 2015-05-02 11:10 | 3d 8h | team VDW [5.0 #8] | 6169.6 | 134400 | 0 | 0 | 140569.6
30 | v0 sanitary | 1.5.2 | 31FS+0;FS28+0 | FS35+0 | 2007-08-29 10:00 | 2015-05-02 11:10 | 3d 8h | plumber | 1152 | 4793 | 0 | 0 | 5945
27 | v0 -masonry | 1.5.3 | 31FS+0;FS28+0 |  | 2007-08-29 10:00 | 2015-05-02 11:10 | 3d 8h | mason | 1300.8 | 31200.9609 | 40.65 | 26016.001 | 58517.7619
59 | v0 heating | 1.5.4 | 31FS+0;FS28+0 | FS35+0 | 2007-08-29 10:00 | 2015-05-02 11:10 | 6d 16h | heating | 2764.8 | 11651 | 0 | 0 | 14415.8
29 | v0 electricity | 1.5.5 | 26FS+0;FS31+0 | FS35+0 | 2007-08-29 10:00 | 2015-05-02 11:10 | 8d 8h | electrician | 2304 | 0 | 0 | 0 | 2304
35 | v0 floors | 1.5.6 | 59FS+0;29FS+0;FS30+0 | FS41+0;FS37+0 | 2007-10-03 10:00 | 2015-05-02 11:10 | 6d 16h | flooring | 2659.84 | 75000 | 0 | 0 | 77659.84
66 | construction leave | 1.6 |  |  | 2015-04-22 11:10 | 2015-05-02 11:10 | 10d |  | 0 | 0 | 0 | 0 | 0
31 | construction leave | 1.6.1 |  | FS53+0;FS55+0;FS56+0;FS61+0;FS54+0;FS30+0;FS27+0;FS59+0;FS52+0;FS45+0;FS34+0;FS60+0;FS51+0;FS29+0 | 2007-08-15 10:00 | 2015-05-02 11:10 | 3d 8h |  | 0 | 0.01 | 0 | 0 | 0.01
63 | level 1 | 1.7 |  |  | 2015-04-22 11:10 | 2015-05-02 11:10 | 10d |  | 0 | 0 | 0 | 0 | 0
52 | vI sanitary | 1.7.1 | 31FS+0;FS28+0 |  | 2007-08-29 10:00 | 2015-05-02 11:10 | 3d 8h | plumber | 1152 | 4793 | 0 | 0 | 5945
45 | vI masonry | 1.7.2 | 31FS+0;FS28+0 |  | 2007-08-29 10:00 | 2015-05-02 11:10 | 3d 8h | mason | 1300.8 | 31200.9609 | 40.65 | 26016.001 | 58517.7619
34 | v1screed | 1.7.3 | 31FS+0;FS28+0 | FS67+0 | 2007-08-29 10:00 | 2015-05-02 11:10 | 5d | chapen [2.0 #3] | 0 | 106140 | 0 | 0 | 106140
60 | v1 heating | 1.7.4 | 31FS+0;FS28+0 |  | 2007-08-29 10:00 | 2015-05-02 11:10 | 6d 16h | heating | 2764.8 | 11651 | 43.2 | 55296.001 | 69711.801
51 | vI electricity | 1.7.5 | 31FS+0;FS28+0 |  | 2007-08-29 10:00 | 2015-05-02 11:10 | 8d 8h | electrician | 2304 | 0 | 0 | 0 | 2304
67 | v1 drying screed | 1.7.6 | FS34+0 | FS57+0;FS32+0 | 2007-09-19 10:00 | 2015-05-02 11:10 | 1d 16h |  | 0 | 0.01 | 0 | 0 | 0.01
57 | v1flooring | 1.7.7 | FS67+0 | FS41+0;FS37+0;FS36+0 | 2007-09-26 10:00 | 2015-05-02 11:10 | 6d 16h | flooring | 2659.84 | 72500 | 0 | 0 | 75159.84
64 | level 2 | 1.8 |  |  | 2015-04-22 11:10 | 2015-05-02 11:10 | 10d |  | 0 | 0 | 0 | 0 | 0
53 | v2 sanitary | 1.8.1 | FS31+0 |  | 2007-08-29 10:00 | 2015-05-02 11:10 | 3d 8h | plumber | 1152 | 4793 | 0 | 0 | 5945
55 | v2 masonry | 1.8.2 | FS31+0 |  | 2007-08-29 10:00 | 2015-05-02 11:10 | 3d 8h | mason | 1300.8 | 31200.9609 | 0 | 0 | 32501.7609
56 | v2 screed | 1.8.3 | FS31+0 | FS68+0;FS36+0 | 2007-08-29 10:00 | 2015-05-02 11:10 | 5d | chapen | 0 | 46116 | 0 | 0 | 46116
61 | v2 heating | 1.8.4 | FS31+0 |  | 2007-08-29 10:00 | 2015-05-02 11:10 | 6d 16h | electrician | 2048 | 11651 | 0 | 0 | 13699
54 | v2 electricity | 1.8.5 | FS31+0 |  | 2007-08-29 10:00 | 2015-05-02 11:10 | 8d 8h | electrician | 2304 | 0 | 0 | 0 | 2304
68 | v2 drying screed | 1.8.6 | FS56+0 | FS58+0;FS32+0 | 2007-09-19 10:00 | 2015-05-02 11:10 | 1d 16h |  | 0 | 0.01 | 0 | 0 | 0.01
58 | v2 flooring | 1.8.7 | FS68+0 | FS41+0;FS37+0;FS36+0 | 2007-09-26 10:00 | 2015-05-02 11:10 | 6d 16h | flooring | 2659.84 | 31500 | 0 | 0 | 34159.84
65 | completion | 1.9 |  |  | 2015-04-22 11:10 | 2015-05-02 11:10 | 10d |  | 0 | 0 | 0 | 0 | 0
32 | stucco | 1.9.1 | 68FS+0;FS67+0 | FS41+0;FS37+0 | 2007-09-26 10:00 | 2015-05-02 11:10 | 5d | stucco [3.0 #4] | 4965.6 | 8642 | 0 | 0 | 13607.6
36 | drywall | 1.9.2 | 58FS+0;57FS+0;FS56+0 |  | 2007-10-24 10:00 | 2015-05-02 11:10 | 8d 8h |  | 0 | 48000 | 0 | 0 | 48000
41 | kitchen and bar | 1.9.3 | 32FS+0;58FS+0;57FS+0;FS35+0 |  | 2007-10-31 10:00 | 2015-05-02 11:10 | 5d |  | 0 | 87000 | 0 | 0 | 87000
37 | techniques | 1.9.4 | 32FS+0;58FS+0;57FS+0;FS35+0 | FS38+0;FS42+0;FS43+0;FS44+0 | 2007-10-31 10:00 | 2015-05-02 11:10 | 5d |  | 0 | 2156.0601 | 0 | 0 | 2156.0601
44 | stairs | 1.9.5 | FS37+0 |  | 2007-11-21 10:00 | 2015-05-02 11:10 | 3d 8h |  | 0 | 33000 | 0 | 0 | 33000
42 | entrance doors | 1.9.6 | FS37+0 |  | 2007-11-21 10:00 | 2015-05-02 11:10 | 3d 8h |  | 0 | 16000 | 0 | 0 | 16000
43 | elevator | 1.9.7 | FS37+0 |  | 2007-11-21 10:00 | 2015-05-02 11:10 | 1d 16h |  | 0 | 38817.8516 | 0 | 0 | 38817.8516
38 | suspended ceiling | 1.9.8 | FS37+0 | FS39+0 | 2007-11-21 10:00 | 2015-05-02 11:10 | 1d 16h |  | 0 | 32000 | 0 | 0 | 32000
39 | painting | 1.9.9 | FS38+0 | FS40+0 | 2007-11-28 10:00 | 2015-05-02 11:10 | 5d | painter [4.0 #6] | 5600 | 83000 | 0 | 0 | 88600
40 | furniture | 1.9.10 | FS39+0 |  | 2007-12-19 10:00 | 2015-05-02 11:10 | 1d 16h | furniture [5.0 #5] | 5040 | 130000 | 0 | 0 | 135040